## Sheet1
TX SET Meeting Notes / Action Items
2017-03-21
Agenda Item: | Decision / Resolution | Action Items :
February 2016 Meeting Notes | Minor Changes were noted and updated. | The Texas SET Chair will have the notes posted to the February meeting page.
RMS Updates-No Update Meeting Next Week | No updates
Flight Update | The ERCOT Flight Administrator presented the Flight updates.
Action Item: Update on Sharyland Utilities combined Tariff testing requirements expected for exisiting CRs that are certified in one of the Sharyland territories, but not the other. | 1. Some CRs at the meeting stated that they plan to complete the additional testing during the June Flight. 2. Sharyland stated that they preferred that any CRs testing the additional territories to do so during the regular testing portion of a flight as opposed to the Ad-Hoc portion. 3. Sharyland will provide another update at the April meeting.
Zip Code Issue during flight set up. | 1. It was noted that a zip code change on an ESI ID that had been made in one TDSP's system had not been updated in the ERCOT CERT environment and that this caused a failure when attempting to set this up for the flight. 2. It was also noted that this was the first issue of this kind and that the ERCOT Flight administrator will check the ESI IDs in the future to be sure the zip codes are up to date.
No Change Control Call-This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
2017-805, Update all the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | Review Implementation Guide Redlines in April depending on Approval of Change Control at March 28, 2017 RMS meeting.
2017-806, Update all the TX SET Implementation Guides to replace “MCTDSP” with “MOU/EC TDSP” | Review Implementation Guide Redlines in April depending on Approval of Change Control at March 28, 2017 RMS meeting.
Discussion Items
796NPRR-05_ERCOT_Comments_121416, Extended Character Set Clean Up. • 2016-I143, Validation processes when a character is included in the customer name on a switch or MVI transaction – Review ERCOT Options; provide feedback • Option 1: Continue With Existing Manual Workaround—Short Term • Option 2: Update ERCOT’s Systems to Reject Any Transaction Containing Special Language Characters—Long Term • Option 3: Update ERCOT’s Systems to Translate Special Language Characters into Normal Characters • Option 4: Implement Option 3 in the Short Term, Followed by Option 2 During the Next TX SET Release | Texas SET agreed to request RMS to move forward on this NPRR at the March 28th RMS meeting.
CNP Method for grouping SAC segments under the SLN loops within their 810_02 TDSP Invoice transactions.--Update from Market Participant Feedback | 1. It was noted that some attendees did not believe it would be an issue to have this change since the change is according to the ANSI Standards. 2. CRs in attendance stated that they will provide feedback at the April meeting.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
2017-I145, Standardization of all 820_02’s received from CRs and their Banks--Review Examples to reach consensus for possible Change Control | 1. CRs in attendance stated that they will be sure to follow the format as shown in the 820_02 Implementation Guide. 2. Attendees agreed to the changes made to the Examples. | 1. The updated examples will be sent to the market for review and feedback to be discussed at the April 18th meeting. 2. ERCOT will verify that the examples are not considered Other Binding Documents and that no change control will be necessary to post the changes on the ERCOT Website.
2017_I147, Original, cancel, and replacement transactions are being handled differently between TDSPs which is causing exceptions for the CR--Update from Examples sent to TDSPs | It was noted that there have been no examples so far to send to TDSPs, but the issue will be held open for another month.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location Continue New Entrant Outline Document Review and Update As Needed | No action taken this month.
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to TX SET Submitting Changes to RMS Discuss any updates offered from CRs | Texas SET reviewed and updated changes to the Retail Market Guide. | The Texas SET Chair to send the updated changes to the Texas SET email distribution list for futher review and feedback to be given next month.
Safety-net Spreadsheet Format--Review Appendix changes. | Texas SET attendees proposed that Appendix A1 and A2 be eliminated from the Retail Market Guide since the tables within the guide contain the same information.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | April 18, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Lindsay Butterfield ERCOT
Becky Taylor CNP | Jim Lee AEP | Paul Yockey ERCOT
Kyle Patrick NRG | Kathy Scott CNP | Monsherra Blank ONCOR
Sam Pak ONCOR | Kaci Jacobs TXU | Monica Jones NRG
Carolyn Reed CNP
Attendees Webex
Deb Belin Aurea
Deborah Croce ECInfoSystems
Teresa Rodriquez Stream Energy
Michael Glass SU