## Slide 1
Retail Project Update
May 2, 2016

## Slide 2
Project Portfolio Update
  Retail Project Update
  2017 Release Targets
  2018 Release Targets
  2017 Project Spending Forecast
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Retail Project Update
Rev Request | Description | Results / Status
RMGRR126 | Additional ERCOT Validations for CBCI File | Delivered in July 2016 with Mass Transition Acquisition Enhancements project
RMGRR137 | Timeline and Completion Process for Correcting CBCI Files | Delivered in July 2016 with Mass Transition Acquisition Enhancements project
RMGRR127 | Efficiencies for Acquisition Transfer | Delivered in December 2016 with Mass Transition Acquisition Enhancements project
RMGRR140 | Efficiencies for Acquisition Transfer Process | Delivered in December 2016 with Mass Transition Acquisition Enhancements project
N/A | Mass Transition/Acquisition Enhancements | Currently in Execution Go-live expected in June 2017 Initial releases delivered RRs noted above
SCR786 | Retail Market Test Environment | Delivered in December 2016
RMGRR134 | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | Delivered in March 2017 – in stabilization
N/A | MarkeTrak Upgrade | Delivered in March 2017 – in stabilization
N/A | EDI Translator and Mapping Replacement Assessment | Initiated in February Recommendation expected in late 2017
NPRR778 | Modifications to Date Change and Cancellation Evaluation Window | Scheduled to initiate on 5/3/2017 Targeted for go-live in October 2017

## Slide 4: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/1 – 5/11 | June 6/27 – 6/29 | August 8/29 – 8/31 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR753 NPRR764 NPRR785 RMGRR134 NPRR790 | SCR790 NPRR746 NPRR786 NPRR792 NOGRR164 PGRR051 RRGRR003 RRGRR006 RRGRR007 RRGRR009 PGRR046 | NPRR573 NPRR789 NPRR797 NPRR801 NPRR744 | NPRR758 NPRR775 NPRR782 | NPRR778 | SCR789
7 | 11 | 5 | 3 | 1 | 1
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NPRR664 | None | SCR781 P | NPRR702 P, NPRR776, NPRR808, NPRR809, NPRR810, NPRR812, PGRR052
12/9 – 12/10 (Retail)
5/8 – NMMS Upgrade
5/15
6/1
11/11 – 11/12 (Retail)
E
E
E
E
E
E
E
E
E
E
E
E
E
P
NS
NS
9/16 – 9/17
(Retail)
2/1
E
E
E
E
E
ü
ü
ü
ü
ü
ü
ü

## Slide 5: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March Dates TBD | May Dates TBD | June Dates TBD | August Dates TBD | October Dates TBD | December Dates TBD
NPRR749 SCR777 | NPRR519 NPRR620 NPRR683 NPRR741 NPRR743 NPRR755 NPRR760 NPRR800 |  |  |  | 
2 | 8 | 0 | 0 | 0 | 0
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
E
E
E
E
E
E
E
E
Dates TBD
(Retail)
NS
E
Dates TBD
(Retail)
CMM Release 1
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold

## Slide 6: 2017 Project Spending – Forecast
2017 PPL Budget = $20.5M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Questions?
?