## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Meeting Material
April 26, 2017
Omar A. Urquidez
PGDTF Chairman

## Slide 2: 2017 PGDTF Goals
R1 PGRR Approval
  Target: ROS Approved, PRS Endorsed at April Meetings & On TAC Agenda for ?? Board Approval at June Meeting
  NERC Enforceable from July 1, 2017
PGDTF Contact List
GIC Model Completion & Review
Assessment/Model Building Timeline Recommendation
Procedure Manual Update
Vulnerability Assessment Scope/Criteria Recommendation
Corrective Action Plan development and “approval” process Recommendation

## Slide 3
PGRR057 posted on 02-06-2017
02-22-2017
03-22-2017
04-06-2017
04-27-2017 ???
06-13-2017

## Slide 4: Last Schedule for GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
4/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT.
6/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs.
7/1/2017 – TSPs and REs Provide Changes to GIC System Model to ERCOT.
Subsequent Model Review Passes Will be Scheduled as Needed.
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases.

## Slide 5: Updated Schedule for GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
6/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT. Delayed…
6/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs. Delayed to when? Discuss…
7/1/2017 – TSPs and REs Provide GIC Model Changes/Updates to ERCOT. Delayed to when? Discuss…
Subsequent Model Review Passes Will be Scheduled as Needed.
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases. Possible Delay- NERC Deadline 7/1/2018 Discuss…

## Slide 6: GIC Data Questions
On our transformer test data report, the vector group on our transformer is YyN (auto) d1, what is PTI equivalent name for this?

## Slide 7: GIC Submission Questions
What is the expectation of the TSPs role in providing the RE’s GMD related data in their RARF?
  Substation submission overlap in coordinates, grounding resistance, & number?

## Slide 8: GIC Data Workshop
Background: At its April meeting, ROS requested that the PGDTF revisit GIC data items for those that are still/beginning the data acquisition process
When: Wednesday, May 10th 9:30 am -12:00 pm
Where: PDCWG Meeting, Rm 206A & WebEx
What: Review of GIC Procedure Manual and select presentations on data items
PGDTF member volunteers requested…
Suggested Presentation Topics:
Substation Grounding
Transformer/Shunt Data

## Slide 9: Data Validation Topics
GIC Data File Creation
Bus Assignments to Stations
  All buses assigned
  Physically located non-electrically connected buses
  TSP-RE connected stations
Sanity checks
  Coordinates
  DC Resistance range values
  Vector Groups
RARF Business Rules

## Slide 10: Example

## Slide 11: Brainstorming Session: Criteria & Vulnerability Assessment Documents
Guiding Questions:
What form does the R3 Criteria document take and what is the expected process for approval?
What form does the R4 Vulnerability Assessment Process/Scope/Assumptions document take and what is the expected process for approval?

## Slide 12: TPL-007-1 Table 1

## Slide 13: Vulnerability Assessment Process Overview
Preliminary CAP
R7
R6
24 Months
R2
R3
R5
R4

## Slide 14
  R3
  Determine System Steady State Voltage Criteria for System Performance
  Per Table 1.
  To be completed by
  07/01/2018
  Enforceable as of 01/01/2022
  R7
  Corrective Action
  Plan
  To be completed by
  TBD
  Enforceable as of
  01/01/2022
PDGTF Implementation Plan to meet NERC Requirements
  R1
Identify Individual and Joint Responsibilities
  To be completed by 07/01/2017
  Enforceable as of 07/01/2017
  R2
  Develop System Models and GIC System Models
  To be completed by 01/01/2018
  Enforceable as of 07/01/2018
  R5
  Determine GIC Flow Information to be used for the transformers thermal assessment
  To be completed by
  07/01/2018
  Enforceable as of 01/01/2019
  R6
  Perform Thermal Assessment for Transformers Experiencing ≥75 A GIC
  To be completed by
  07/01/2019
  Enforceable as of 01/01/2021
  R4
Complete GMD Vulnerability Assessment every 60 month
  To be completed by
  TBD
  Enforceable as of 01/01/2022
PDGTF Implementation Plan to Meet the Requirements of NERC TPL-007-1

## Slide 15: PGDTF Meeting Schedule
Next Meetings:
May or June?
July
August