## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to the ROS
May 4, 2017
Omar Urquidez
PGDTF Chairman
<number>
5/4/2017 ROS Meeting

## Slide 2: Activities of the PGDTF in April
ROS voted to approve 057PGRR, PRS endorsed the recommended priority and rank, next to May TAC meeting
Met on April 26, 2017
  Discussed GIC System Model Data Workshop, Wednesday May 10th
  Updated GIC System Model Building Schedule
  Planned In-person GIC System Model reviews set for July & August
  Decided direction for Vulnerability Assessment Scope/Criteria (TPL-007-1 R3/R4)
    PGDTF recommends the criteria to be included in Section 4 of the Planning Guide
    PGDTF recommends creation of a Vulnerability Assessment scope document to be approved by ROS
    Draft language for both the scope and criteria will be discussed at June meeting
  Discussed National and State Activities Related to GMD.
PGDTF will meet next on June 9th
Omar Urquidez – 5/4/2017 ROS Meeting
<number>

## Slide 3: GIC System Model Workshop
What: PGDTF will sponsor a Workshop to walk through the GIC System Model Procedure Manual and share experiences with gathering GIC System Model Data
When: Wednesday, May 10th, 9:30 am – 12:00 pm
Where: Morning session of the May PDCWG Meeting
    Open Session (morning only), Rm 206A & WebEx
Agenda:
    GIC System Model Procedure Manual Walkthrough 30 min
    Transformer Data Presentation 30-45 min
    Substation Grounding Resistance Presentation 30-45 min
    GIC System Model Supplemental Guidance 30 min
Omar Urquidez – 5/4/2017 ROS Meeting
<number>

## Slide 4: Updated Schedule for GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
6/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT. Updated…
9/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs. In-person meetings for review of model. Updated…
10/1/2017 – TSPs and REs Provide GIC Model Changes/Updates to ERCOT. Updated…
Subsequent Model Review Passes Will be Scheduled as Needed.
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases. NERC Enforceable from 7/1/2018
<number>
Omar Urquidez – 5/4/2017 ROS Meeting

## Slide 5: Questions and Answers
<number>
Omar Urquidez – 5/4/2017 ROS Meeting