## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
May 11, 2016

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
  2017 Release Targets
  2018 Release Targets
  2017 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Appendix
  Project Portfolio Gantt Chart p. 9-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2017 May Release – 5/1/2017-5/11/2017 In Flight
  SCR790 – Wind Resource Power Production and Forecast Transparency
  NPRR746 – Adjustments Due to Negative Load
  NPRR786 – Consumption Data Adjustments for Negative Load
  NPRR792 – Changing Special Protection System (SPS) to Remedial Action Scheme (RAS)
  NOGRR164 – Alignment with NPRR792, Removing SPS and adding (RAS)
  PGRR051 – Alignment with NPRR792, Changing SPS to RAS
  RRGRR003 – Modifications to Improve Wind Forecasting
  RRGRR006 – Clarification of Descriptions and Alignment with RARF Forms
  RRGRR007 – Adding Solar Resource Registration Inputs
  RRGRR009 – Adding Voltage Limit Sets, Relay Loadability, MLSE, and GMD Data
  RRGRR010 – Seasonal Net Max Sustainable Rating Definitions
  PGRR046 – Addition of Geomagnetically Induced Current (GIC) Model Building Reqs
5/8/2017 In Flight
  NMMS Upgrade project
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/1 – 5/11 | June 6/27 – 6/29 | August 8/29 – 8/31 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR753 NPRR764 NPRR785 RMGRR134 NPRR790 | SCR790 NPRR746 NPRR786 NPRR792 NOGRR164 PGRR051 RRGRR003 RRGRR006 RRGRR007 RRGRR009 RRGRR010 PGRR046 | NPRR573 NPRR789 NPRR797 NPRR801 NPRR744 | NPRR758 NPRR775 NPRR782 NPRR812 | NPRR778 NPRR808 | SCR789 PGRR052
7 | 12 | 5 | 4 | 2 | 2
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NPRR664 | None | SCR781 P | NPRR702 P, NPRR776, NPRR808, NPRR809, NPRR810, NPRR812, PGRR052
12/9 – 12/10 (Retail)
5/8 – NMMS Upgrade
5/29 – 6/2
11/11 – 11/12 (Retail)
E
E
E
E
E
E
E
E
E
E
E
E
E
P
NS
NS
NS
NS
NS
9/16 – 9/17
(Retail)
2/1
E
E
E
E
E
E
ü
ü
ü
ü
ü
ü
ü

## Slide 5: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March Dates TBD | May Dates TBD | June Dates TBD | August Dates TBD | October Dates TBD | December Dates TBD
NPRR749 NPRR776 SCR777 | NPRR519 NPRR620 NPRR683 NPRR741 NPRR743 NPRR755 NPRR760 NPRR800 NPRR810 |  |  |  | 
3 | 9 | 0 | 0 | 0 | 0
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
E
E
E
E
E
E
E
E
NS
Dates TBD
(Retail)
NS
NS
E
Dates TBD
(Retail)
CMM Release 1
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold

## Slide 6: 2017 Project Spending
2017 PPL Budget = $20.5M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2017, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2017
YTD Actuals | $0.65M
Approved – In-Flight / Complete | $2.03M
Approved – On Hold | $0.00M
Approved – Not Started | $0.26M
Remaining Funding | $1.71M
Total Allocation | $4.00M
As of 3/31/2017

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
 | No items to rank |  |  | 
Options for…
PPL Rank Information
Next available Rank in Business Strategy = 2010
Next available Rank in Regulatory = 170

## Slide 9
Appendix
  4/30/2017 Project Gantt
    In-flight items sorted by Project End Date
    “On Hold” projects listed separately
      None at this time
    “Not Started” items sorted by Project Start Date

## Slide 10: Project Portfolio Status – as of 4/30/2017

## Slide 11: Project Portfolio Status – as of 4/30/2017

## Slide 12: Project Portfolio Status – as of 4/30/2017

## Slide 13: Project Portfolio Status – as of 4/30/2017

## Slide 14: Project Portfolio Status – as of 4/30/2017

## Slide 15: Project Portfolio Status – as of 4/30/2017

## Slide 16: Project Portfolio Status – as of 4/30/2017

## Slide 17: Project Portfolio Status – as of 4/30/2017