## Sheet1
TX SET Meeting Notes / Action Items
2017-04-18
Agenda Item: | Decision / Resolution | Action Items :
March 2016 Meeting Notes | No changes were made to the notes. | The Texas SET Chair will have ERCOT post the finalized notes to the March 21, 2017 meeting page.
RMS Updates
NPRR796, Extended Character Set Clean Up | RMS voted to endorse.
Change Control 2017-805, Special Characters | RMS voted to approve.
Change Control 2017-806, MOU/EC TDSP Standardization | RMS voted to approve.
Impact Analysis for RMGRR145, Appendix for a Mass Customer List (MCL) | RMS voted to approve--it was noted that TAC cancelled their April meeting and that this RMGRR will be considered at the May TAC meeting.
RMGRR147, Stand Alone Discretionary Meter Tampering Charges and Impact Analysis | RMS voted to approve--it was noted that TAC cancelled their April meeting and that this RMGRR will be considered at the May TAC meeting.
Flight Update | The Texas SET vice chair presented the flight update.
Action Item: Update on Sharyland Utilities combined Tariff testing requirements expected for exisiting CRs that are certified in one of the Sharyland territories, but not the other. | Sharyland stated that they are conducting a workshop to discuss operational requirements of proposed system-wide rates and will provide an update at a future Texas SET meeting.
No Change Control Call-This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
TX SET Procedures | Redlines contained within the change controls listed below.
2017-805, Update all the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | 1. Texas SET reached consensus on the redlines. 2. Texas SET conducted a discussion on how to determine versions and when the version number should be updated. 3. Texas SET agreed that the language in the Texas SET Working Group Procedures needs to be updated to reflect the process. The group will continue the discussions next month. 4. Texas SET agreed that this Change Control should be implemented in a future version and that the Texas SET Chair should request that RMS re-open the Change Control to change the approval to a future version.
2017-806, Update all the TX SET Implementation Guides to replace “MCTDSP” with “MOU/EC TDSP” | 1. Texas SET reached consensus on the redlines. 2. Texas SET conducted a discussion on how to determine versions and when the version number should be updated. 3. Texas SET agreed that the language in the Texas SET Working Group Procedures needs to be updated to reflect the process. The group will continue the discussions next month. 4. Texas SET agreed that this Change Control should be implemented in a future version and that the Texas SET Chair should request that RMS re-open the Change Control to change the approval to a future version.
Discussion Items
CNP Method for grouping SAC segments under the SLN loops within their 810_02 TDSP Invoice transactions.--Update from Market Participant Feedback | 1. One CR stated that their company cannot support the change at this time. 2. One CR stated that their company is still conducting testing and will provide an update at the May meeting.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
2017-I145, Standardization of all 820_02’s received from CRs and their Banks--Review Examples to reach consensus for possible Change Control --Review updated Implementation Guide examples --Market Rules update OBD Question | 1. ERCOT stated that the examples are not considered OBDs 2. Texas SET reached consensus on the examples provided. | The Texas SET chair will box the highlighted items within each transaction and send the updated examples to ERCOT to post to the website.
2017_I147, Original, cancel, and replacement transactions are being handled differently between TDSPs which is causing exceptions for the CR--Update from Examples sent to TDSPs | The CR stated that there have been no new examples to provide to the TDSPs and agreed to close the issue.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location Continue New Entrant Outline Document Review and Update As Needed | Texas SET reviewed and agreed that the New Entrant Document outline is complete. Texas SET members will ask ERCOT to determine where this document should reside on the ERCOT website. | The Texas SET Chair will send the document to ERCOT for posting to the ERCOT website.
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to TX SET Submitting Changes to RMS Review updates made to RMG | 1. Texas SET continued to review and update the RMG. 2. Market Participants will continue to review the timelines internally and provide feedback at the next meeting. 3. The RMS Chair requested that a related update to RMG Section 7.6.3.3, Completing Orders be added to this draft of changes. | The Texas SET Chair will put the changes made to date into a draft RMGRR to be reviewed at the next meeting.
Safety-net Spreadsheet Format--Review Appendix changes.--Review Feedback for removing A1 & A2 and updating the RMG corresponding tables. | Texas SET agreed to remove these two appendices from the RMG. | This change will be included in the draft of the Safety net changes as shown above.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | May 16, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Monica Jones NRG
Lindsay Butterfield ERCOT | Monsherra Blank ONCOR
Kaci Jacobs TXU | Carolyn Reed CNP
Kyle Patrick NRG | Jim Lee AEP
Kathy Scott CNP
Sam Pak ONCOR
Attendees Webex
Becky Taylor CNP | Kim Wall Hansen Technologies
Christy Dvorak Infinite Electric | Stephen Wilson SU
Deb Belin Aurea | Michael Glass SU
Deborah Croce EC InfoSystems
Kathryn Thurman ERCOT
Teresa Rodriquez Stream Energy
Dave Michelsen ERCOT