## Sheet1
TX SET Meeting Notes / Action Items
2017-05-16
Agenda Item: | Decision / Resolution | Action Items :
April 2016 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will have these posted to the April meeting page key documents.
RMS Updates
Change Control 2017-805, Special Characters | RMS voted to waive notice and change the original Change Control to be approved for a future release.
Change Control 2017-806, MOU/EC TDSP Standardization | RMS voted to waive notice and change the original Change Control to be approved for a future release.
Impact Analysis for RMGRR146, Retail Market Guide Revision Request Process | RMS voted to approve.
Flight Update | The ERCOT Flight Administrator presented the flight update.
Revisit Banking Scripts Language For Payments-- IBANK and MBANK Scripts Criteria and Success | Texas SET reviewed the Banking and other scripts to determine the language changes. | The Texas SET Chair sent the updated scripts to the Texas SET email distribution list. Market Participants to provide feedback at the June meeting.
No Change Control Call-This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Discussion Items
CNP Method for grouping SAC segments under the SLN loops within their 810_02 TDSP Invoice transactions.--Update from Market Participant Feedback | 1. Some of the CRs stated that they experienced issues caused by this change related to their ability to bill their customers. 2. It was determined that further discussion will take place between the Market Participants outside of Texas SET.
Change Control Process Language Update—Add process for determining versions. | Discussion for this will be delayed until the June meeting.
Texas Data Transport and MarkeTrak Systems (TDTMS) Working Group Request—Change to Testing Worksheet (Certification to RMTE) | Texas SET reviewed and agreed to the changes to the Testing Worksheet. | The Texas SET Chair will send the updated document to ERCOT for review and feedback to be provided at the next Texas SET meeting.
SAC04 Spreadsheet, SER001 Market Description alignment with Texas SET Implementation Guide SAC15 Gray Box | Texas SET determined that no changes need to be made at this time.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues- | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
2017-I148, Cancel Due Date Example Alignment Issue | Texas SET reviewed and agreed to the change in the examples. | The Texas SET Chair will send the updated Issue and example documents to ERCOT for posting.
RMS assignments:
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Review updates made to the RMG—Language, Remove AppendixA1 and A2, and add Section 7.6.3.3, Competing Orders changes. | Texas SET reviewed and made some minor changes to the language. | The Texas SET Chair will send the updated document to the Texas SET email distribution list for feedback to be provided at the next Texas SET meeting.
Left in Hot Process Discussion—PUCT Rule 25.489, Treatment of Premises With No Retail Electric Provider of Record. | Texas SET reviewed and updated the language in the Retail Market Guide Section 7.9, No Retail Electric Provider Of Record Or Left In Hot. | The Texas SET Chair will send the updated document to the Texas SET email distribution list for feedback to be provided at the next Texas SET meeting.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | June 20, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Jim Lee AEP
Kyle Patrick NRG | Monica Jones NRG
Kaci Jacobs TXU | Carolyn Reed CNP
Lindsay Butterfield ERCOT | Rebecca Zerwas NRG
Kathy Scott CNP
Sam Pak ONCOR
Attendees Webex
Becky Taylor CNP | Teresa Rodriquez Stream
Deb Belin Aurea | Stephen Wilson SU
Deborah Croce ECInforSystems
Kathryn Thurman ERCOT
Kim Wall Hensen Technologies
Mark Ruane ERCOT
Paul Yockey ERCOT