## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to the ROS
August 3, 2017
Omar Urquidez
PGDTF Chairman
<number>
8/3/2017 ROS Meeting

## Slide 2: 2017 PGDTF Goals
R1 PGRR Approval
PGDTF Contact List
GIC Model Completion & Review
Assessment/Model Building Timeline Recommendation
Vulnerability Assessment Scope/Criteria Recommendation
Procedure Manual Update
Corrective Action Plan development and “approval” process Recommendation
***Current Active Items
8/3/2017 ROS Meeting
<number>

## Slide 3: Activities of the PGDTF – June/July
ERCOT Board approved 057PGRR – Addresses TPL-007-1 R1
Met June 9th and July 6th
  RE RARF Submission FAQs discussed and updated
  Updated GIC System Model Building Schedule
  Planned In-person GIC System Model reviews set for August 25th & September 28th
  Discussed TSP/RE interface reconciliation strategies
  Vulnerability Assessment Scope/Criteria (TPL-007-1 R3/R4)
    Draft outlines for both the scope and criteria have been presented and discussed
  Discussed National and State Activities Related to GMD.
    TPL-007-2 Comment Period/Ballot open until August 11th
PGDTF will meet next on August 24th
<number>
8/3/2017 ROS Meeting

## Slide 4: Updated Schedule for GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
6/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT. Incomplete
11/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs. Delayed due to insufficient data…
12/1/2017 – TSPs and REs Provide GIC Model Changes/Updates to ERCOT. Delayed due to insufficient data…
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases. NERC Enforceable from 7/1/2018
<number>
8/3/2017 ROS Meeting

## Slide 5: TPL-007-2 - Major Revisions
TPL-007-2 Comment Period/Ballot open until August 11th
Addition of a Supplemental GMD Event
  1.5 times stronger event, local area impact only, no Corrective Action Plan required
Deadlines added for implementation of Corrective Action Plan (CAP) for benchmark GMD event
  1 year for development of CAP
  2 years for implementing operating procedure mitigation
  4 years for implementing hardware mitigation
  Update procedure allowed in Requirement 7.4
Addition of an access requirement for GIC & magnetometer data
  Requirement 11 requires a process to obtain GIC data from at least one monitor
  Requirement 12 requires a process to obtain geomagnetic field data for Planning Coordinator’s planning area
<number>
8/3/2017 ROS Meeting

## Slide 6: Questions and Answers
<number>
8/3/2017 ROS Meeting