## CON01
Script ID | CON01 |  | Power Point
Script Name | ERCOT and TDSP Test Bed Load
Script Storyline | TDSP sends Test Bed Load to ERCOT. ERCOT successfully receives and sets up.
Success Criteria | Test Bed set up successfully
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
Operating Rule |  |  | TRACK | Connectivity
Simulated Entity
Duns Number
Number of CR's
| ERCOT | TDSP
PreTest Setup
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Pre-Day 1 | ERCOT | TDSP | email | Relationship Matrix | ERCOT sends TDSP the final testing Relationship Matrix.
Pre-Day 1 | TDSP | CR | email | ESI ID Spreadsheet | TDSP emails ESI ID spreadsheet to primary and secondary contacts.
Pre-Day 1 | TDSP | ERCOT | email | ESI ID List | TDSP emails ESI ID spreadsheet to ERCOT flight testing team.
Pre-Day 1 | TDSP | ERCOT | 814_20 | Create ESI ID | TDSP transmits 814_20 Create ESI ID transactions to ERCOT BY THE DATE SPECIFIED IN THE PUBLISHED FLIGHT CALENDAR. No 814_21 or 997 transactions are returned.

## CON05
Script ID | CON05 |  | Power Point
Script Name | NAESB connectivity with ERCOT and CR
Script Storyline | Test NAESB connectivity; successful exchange of standard X12-encrypted handshake files. Note: the 814_01 sent by the CR is sent with an incorrect value in the REF*SU segment of the transaction in order to force it to automatically create an outbound 814_02 in ERCOT's system.
Success Criteria | CR and ERCOT successfully send and receive encrypted files.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
Operating Rule |  |  | TRACK | Connectivity
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | CR
PreTest Setup
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Pre-Day 1 | ERCOT | CR | email | Encryption Keys | ERCOT emails encryption keys along with username and password to CR and schedules connectivity testing
Pre-Day 1 | CR | ERCOT | email | Encryption Keys | CR emails encryption keys along with username and password to ERCOT and schedules connectivity testing
Pre-Day 1 | CR | ERCOT | 814_01 | encrypted file | CR sends an encrypted X12 formatted 814_01 file containing an ESI ID of "CONNECTIVITYTESTESIID" and a "REF*SU*I". CR emails ERCOT results of successful posting from their NAESB log.
Pre-Day 1 | ERCOT | CR | 814_02 | Encrypted file | ERCOT sends an encrypted X12 formatted 814_02 containing an ESI ID of "CONNECTIVITYTESTESIID". ERCOT emails CR successful NAESB response message

## NPRR778_SWCNCL Day Prior
Script ID | NPRR778_SWCNCL Day Prior |  | Power Point
Script Name | Self Selected Switch - With Cancel 1 day prior to Scheduled Date
Script Storyline | CR1 initiates a Self Selected Switch Transaction Requesting 3 Days out. The TDSP schedules the Self Selected Switch. The CR sends a Cancel Request one day prior to the scheduled Switch date. ERCOT forwards the Cancel to the TDSP. The TDSP accepts the Cancel, cancels the Self Selected Switch and responds with an Accept.
Success Criteria | TDSPs with either Standard or Non-standard meter The Self Selected Switch Cancel Request is Accepted.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None | Sim CR? | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_01 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
Day 02 | CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested for Customer A | 1
| ERCOT | TDSP | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested for Customer A | 1
| TDSP | ERCOT | 814_09 | ASI~WQ~024 | SW Cancelled | 1
| ERCOT | CR1 | 814_09 | ASI~WQ~024 | SW Cancelled | 1
Day 03
Day 04
Day 05
Day 06

## NPRR778_SWCNCL Day Of
Script ID | NPRR778_SWCNCL Day Of |  | Power Point
Script Name | Self Selected Switch - With Cancel Day of Scheduled Date
Script Storyline | CR1 initiates a Self Selected Switch Transaction Requesting 3 Days out. The TDSP schedules the Self Selected Switch. The CR sends a Cancel Request on the scheduled Switch date. ERCOT Rejects the Cancel.
Success Criteria | TDSPs with either Standard or Non-standard meter The Self Selected Switch Cancel Request is Rejected by ERCOT.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None | Sim CR? | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_01 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Day 3 Switch Effectuates | 1 | SW |  | CR1
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested for Customer A | 1
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | SW Not Cancelled | 1
Day 04
Day 05
Day 06

## NPRR778_SWCNCL Past
Script ID | NPRR778_SWCNCL Past |  | Power Point
Script Name | Self Selected Switch - With Cancel for SW Scheduled Date In the Past
Script Storyline | CR1 initiates a Self Selected Switch Transaction Requesting 3 Days out. The TDSP schedules the Self Selected Switch. The Self Selected Switch effectuates on Day 3. The CR sends a Cancel Request on the Day after the Self Selected Switch Effectuates (Day 4). ERCOT Rejects the Cancel.
Success Criteria | TDSPs with either Standard or Non-standard meter The Self Selected Switch Cancel Request is Rejected by ERCOT.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None | Sim CR? | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_01 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~201710xx | SW requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | SW scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Day 3 Switch Effectuates | 1 | SW |  | CR1
Day 04 | CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested for Customer A | 1
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | SW Not Cancelled | 1
Day 05
Day 06

## NPRR778_MVICNCL Day Prior
Script ID | NPRR778_MVICNCL Day Prior |  | Power Point
Script Name | Move In - With Cancel 1 day prior to Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Cancel Request one day prior to the scheduled MVI date. ERCOT forwards the Cancel to the TDSP. The TDSP accepts the Cancel, cancels the MVI and responds with an Accept.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Cancel Request is Accepted.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02 | CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested for Customer A | 1
| ERCOT | TDSP | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested for Customer A | 1
| TDSP | ERCOT | 814_09 | ASI~WQ~024 | MVI Cancelled | 1
| ERCOT | CR1 | 814_09 | ASI~WQ~024 | MVI Cancelled | 1
Day 03
Day 04
Day 05
Day 06
Day 07
Day 08
Day 09

## NPRR778_MVICNCL Day Of
Script ID | NPRR778_MVICNCL Day Of |  | Power Point
Script Name | Move In - With Cancel Day of Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Cancel Request on the day of the scheduled MVI date. ERCOT sends a Reject response to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Cancel Request is Rejected.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested for Customer A | 1
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVI Not Cancelled | 1
Day 04
Day 05
Day 06

## NPRR778_MVICNCL Past
Script ID | NPRR778_MVICNCL Past |  | Power Point
Script Name | Move In - With Cancel of MVI Scheduled Date In the Past
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Cancel Request on the day after the scheduled MVI date. ERCOT sends a Reject response to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Cancel Request is Rejected.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested for Customer A | 1
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVI Not Cancelled | 1
Day 05
Day 06

## NPRR778_MVIDTCH Day Prior
Script ID | NPRR778_MVIDTCH Day Prior |  | Power Point
Script Name | Move In - With Date Change 1 day prior to Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Date Request one day prior to the scheduled MVI date. ERCOT forwards the Date Change Requestl to the TDSP. The TDSP accepts the Date Change Request, Schedules the MVI for Day 6 and responds with an Accept.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Date Change Request is Accepted.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02 | CR1 | ERCOT | 814_12 | RMRD = Day 6 (DTM~375) | MVI Date Change requested for Customer A | 1
| ERCOT | TDSP | 814_12 | RMRD = Day 6 (DTM~375) | MVI Date Change requested for Customer A | 1
| TDSP | ERCOT | 814_13 | SMRD = Day 6 | MVI Scheduled for Day 6 | 1
| ERCOT | CR1 | 814_13 | SMRD = Day 6 | MVI Scheduled for Day 6 | 1
Day 03
Day 04
Day 05
Day 06
Day 07

## NPRR778_MVIDTCH Day Of
Script ID | NPRR778_MVIDTCH Day Of |  | Power Point
Script Name | Move In - With Date Change Requested Day of Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Date Change Request on the day of the scheduled MVI date. ERCOT sends a Reject response to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Date Change Request is Rejected.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
| CR1 | ERCOT | 814_12 | RMRD = Day 6 (DTM~375) | MVI Date Change requested for Customer A | 1
| ERCOT | CR1 | 814_13 | ASI~U~001 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVI SMRD Not Changed | 1
Day 04
Day 05
Day 06

## NPRR778_MVIDTCH Past
Script ID | NPRR778_MVIDTCH Past |  | Power Point
Script Name | Move In - With Date Change of MVI Scheduled Date In the Past
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI for Day 3. The CR sends a Date Change Request on the day after the scheduled MVI date. ERCOT sends a Reject response to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI Date Change Request is Rejected.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04
| CR1 | ERCOT | 814_12 | RMRD = Day 6 (DTM~375) | MVI Date Change requested for Customer A | 1
| ERCOT | CR1 | 814_13 | ASI~U~001 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVI SMRD Not Changed | 1
Day 05
Day 06

## NPRR778_MVOCNCL Day Prior
Script ID | NPRR778_MVOCNCL Day Prior |  | Power Point
Script Name | Move Out - With Cancel 1 day prior to Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Cancel Request one day prior to the scheduled MVO date. ERCOT forwards the Cancel to the TDSP. The TDSP accepts the Cancel, cancels the MVO and responds with an Accept. ERCOT forwards the Accept to the CR
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Cancel Request is Accepted.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05 | CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 2
| ERCOT | TDSP | 814_12 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 2
| TDSP | ERCOT | 814_13 | ASI~WQ~024 | MVO Cancelled | 2
| ERCOT | CR1 | 814_13 | ASI~WQ~024 | MVO Cancelled | 2
Day 06
Day 07

## NPRR778_MVOCNCL Day Of
Script ID | NPRR778_MVOCNCL Day Of |  | Power Point
Script Name | Move Out - With Cancel on Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Cancel Request on the scheduled MVO date. ERCOT sends a Reject to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Cancel Request is Rejected
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05
Day 06 |  |  |  |  | Move-out Effectuates | 1 | MVI |  | CR1
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 2
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVO Not Cancelled | 2
Day 07

## NPRR778_MVOCNCL Past
Script ID | NPRR778_MVOCNCL Past |  | Power Point
Script Name | Move Out - With Cancel of MVO Scheduled Date In the Past
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Cancel Request on the day after the scheduled MVO date. ERCOT sends a Reject to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Cancel Request is Rejected
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05
Day 06 |  |  |  |  | Move-out Effectuates | 1 | MVI |  | CR1
Day 07
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 2
| ERCOT | CR1 | 814_09 | ASI~U~024 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVO Not Cancelled | 2

## NPRR778_MVODTCH Day Prior
Script ID | NPRR778_MVODTCH Day Prior |  | Power Point
Script Name | Move Out - With Date Change Requested 1 day prior to Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Date Change Request one day prior to the scheduled MVO date. ERCOT forwards the Date Change Request to the TDSP. The TDSP accepts the Date Change; schedules the MVO for Day 9 and responds with an Accept. ERCOT forwards the Accept to the CR
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Date Change Request is Accepted.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05 | CR1 | ERCOT | 814_12 | RMRD - Day 9 (DTM~376) | MVI Date Change requested for Customer A | 2
| ERCOT | TDSP | 814_12 | RMRD - Day 9 (DTM~376) | MVI Date Change requested for Customer A | 2
| TDSP | ERCOT | 814_13 | SMRD = Day 9 | MVI Scheduled for Day 9 | 2
| ERCOT | CR1 | 814_13 | SMRD = Day 9 | MVI Scheduled for Day 9 | 2
Day 06
Day 07

## NPRR778_MVODTCH Day Of
Script ID | NPRR778_MVODTCH Day Of |  | Power Point
Script Name | Move Out - With Date Change Requested on Scheduled Date
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Date Change Request on the scheduled MVO date. ERCOT sends a Reject to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Date Changel Request is Rejected
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05
Day 06 |  |  |  |  | Move-out Effectuates | 1 | MVI |  | CR1
| CR1 | ERCOT | 814_12 | RMRD - Day 9 (DTM~376) | MVO Date Change requested for Customer A | 2
| ERCOT | CR1 | 814_13 | ASI~U~001 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVO Date Not Changed | 2
Day 07

## NPRR778_MVODTCH Past
Script ID | NPRR778_MVODTCH Past |  | Power Point
Script Name | Move Out - With Date Change Requested of MVO Scheduled Date In the Past
Script Storyline | CR1 initiates a MVI Transaction Requesting 3 Days out. The TDSP schedules the MVI. The MVI Effectuates on Day 3. The CR initiates a MVO Requesting 3 days out. The TDSP schedules the MVO for Day 6. The CR sends a Date Change Request on the day after the scheduled MVO date. ERCOT sends a Reject to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter The MVI completes and the MVO Date Change Request is Rejected
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 for Customer A | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI scheduled for Day 3 | 1 |  |  | CR1
Day 02
Day 03 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 04 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1
| CR1 | ERCOT | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 6 (DTM~376) | MVO for Customer A | 2 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 6 | MVO for Customer A | 2 |  |  | CR1
Day 05
Day 06 |  |  |  |  | Move-out Effectuates | 1 | MVI |  | CR1
Day 07
| CR1 | ERCOT | 814_12 | RMRD - Day 10 (DTM~376) | MVO Date Change requested for Customer A | 2
| ERCOT | CR1 | 814_13 | ASI~U~001 REF~7G~CW1~Cannot Cancel on the Day of Scheduled Meter Read Date or in the past. | MVO Date Not Changed | 2