## Slide 1
CMM Tech Refresh Project Update
August 16, 2017

## Slide 2: CMM Tech Refresh Project
2015 CMM NPRRs and Tech Refresh – Combines CMM NPRRs, a technical refresh and new Treasury functionality into a single project to gain efficiencies
Phase 1 is in Execution and includes delivery of the CMM technical refresh along with the majority of the Credit-related NPRRs. The team has completed a re-plan effort to address departure of two key team resources and has taken actions to mitigate impacts to the planned delivery date.
  Phase 1A will deliver NPRRs 648, 683, 743, 760 and 800 via the existing CMM application. The estimated completion date is targeted for Q1 2018.
  Phase 1B will continue to focus on delivery of the technical refresh along with delivery of the full scope of NPRRs in Phase 1. Development has been re-planned and is on track; FAT testing will start in August. The team continues to assess schedule impacts to confirm the go-live date.
Phase 2 will deliver Financial Transfer functionality and additional Credit/Treasury efficiencies. Team continues to document Requirements and User Interface designs and workflows. The go-live date will be set once re-plan efforts for Phase 1 are complete.
Phase 3 will deliver any remaining low-priority scope. The go-live date for this phase will be addressed following completion of Planning for Phase 2.

## Slide 3: CMM Tech Refresh Project
NPRR Implementation Schedule
Phase 1A
  NPRR800 Revisions to Credit Exposure Calculation to Use Electricity Future Market Prices
  NPRR760 Calculation of Exposure Variables For Days With No Activity
  NPRR648 Remove Reference to Flowgate Rights
  NPRR683 Revision to Available Credit Limit Calculation
  NPRR743 Revision to MCE to have a Floor for Load Exposure
Phase 1B
  NPRR660 Remove CRR State Change Adder
  NPRR519 Exemption of ERS-Only QSEs from Collateral and Capitalization Requirements
  NPRR755 Agent-Only QSE Registration
  NPRR620 Collateral Requirements for Counter-Parties with No Load or Generation
  NPRR741 Clarifications to TPE and EAL Credit Exposure Calculations
Phase 2 will include the implementation of NPRR 702.
  NPRR702 Flexible Accounts, Payment of invoices, and Disposition of Interest on Cash Collateral
Phase 3 will include the implementation of NPRR484 (1B)
  NPRR484 (1B) Revisions to Congestion Revenue Rights Credit Calculations and Payments

## Slide 4: Credit Updates
Approved Revision / Change Requests
* Estimated Target Release Date is May 2018 (will be firmed up in the near future)
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
TBD = To Be Determined

## Slide 5: CMM Tech Refresh Project
Questions