## Sheet1
TX SET Meeting Notes / Action Items
2017-06-20
Agenda Item: | Decision / Resolution | Action Items :
May 2017 Meeting Notes | No changes were made to the notes. | The Texas SET Chair will have the notes posted to the May meeting page.
RMS Updates--No Meeting June
Flight Update | ERCOT Staff provided the Flight update which contained very little changes from the last update.
Revisit Banking Scripts Language For Payments-- IBANK and MBANK Scripts Criteria and Success -- Market Participant Feedback | Texas SET discussed questions raised by some members and decided the Scripts were ready to be posted. | The ERCOT Flight Administrator agreed to update the change log and have the finalized scripts posted to the testing webpage.
Testing Needed for NPRR778, Modifications to Date Change / Cancellation Evaluation Window | Texas SET determined that some testing will be needed between Market Participants to insure that the changes being implemented in October are successful. | Texas SET will begin to develop testing requirmenets at the August meeting.
No Change Control Call-This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Discussion Items
CNP Method for grouping SAC segments under the SLN loops within their 810_02 TDSP Invoice transactions.--Update from Market Participant Feedback | 1. Texas SET discussed a documented response from a group of Competitive Retailers (CRs) that voiced their concerns. 2. CNP will review the response document internally and respond directly to the CRs. 3. Later in the meeting CNP stated that they could offer a second option to separate the unmetered services into multiple ESI IDs to accommodate each tariff rate. 4. TX SET also determined that no further discussion is needed for the topic within the working group and that further discussion will take place directly between CNP and the CRs.
Change Control Process Language Update—Add process for determining versions. | 1.Texas SET discussed and offered suggestions for versioning o Version .Process/System Impacts. Administrative. • Exp: Nueces 650_04 changes. V4.1.0 or V4.1 for possible system impacts. • Exp. 814_04 spelling correction V4.0.1 or V4.0A for administrative changes • Exp: Full market Cerification changes V5.0 for market wide changes and testing. 2. Current Texas SET Implementation Guides Webpage would reflect the most current version; then only the individual guide(s) under each transaction grouping would contain the changed version number. 3. Versioning structure remains unchanged; but how we apply those changes needs to be updated in the Change Control Process document. 4. ERCOT stated that they will need to review any final changes proposed to determine if ERCOT will experience any impacts from these changes. | Market Participants to review with their internal IT departments and provide feedback at the next TX SET meeting.
Texas Data Transport and MarkeTrak Systems (TDTMS) Working Group Request—Change to Testing Worksheet (Certification to RMTE)--ERCOT Feedback | ERCOT agreed to make the change in the testing worksheet, but will bring any issues found back to the working group if needed.
820_02 Bank Remarks section NTE*ZZZ*--Discuss need to update Implementation Guide and Examples. | 1. TX SET agreed that some of the information that a bank sends may be out of the control of the Market Participant. 2. NRG and CNP agreed to reviewed the TX SET Implementation Guide and examples to determine if any updates will be needed. | NRG and CNP will provided an update to the group at the next meeting if changes are needed.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues- | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
RMS assignments:
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Review updates made to the RMG—Language, Remove AppendixA1 and A2, and add Section 7.6.3.3, Competing Orders changes.--Feedback | 1. TX SET reviewed the previous changes made to the draft RMGRR as well as comments provided by CNP and ONCOR. 2. TX SET determined that the three documents should be combined into one draft RMGRR. 3. AEP agreed to combine the three documents and will work with NRG, CNP and ONCOR for any needed assistance to provide an updated copy for review at the next TX SET meeting. | The Texas Set Chair will send the three documents to AEP to be combined into one draft RMGRR; then send to the TX SET email distribution list by July 14th for all to review prior to the August meeting.
Left in Hot Process Discussion—PUCT Rule 25.489, Treatment of Premises With No Retail Electric Provider of Record.--Feedback | TX SET discussed the previous changes made to the Retail Market Guide and made a few minor additional changes. | The Texas SET Chair will put the changes into a Revision Request document and submit to Market Rules for posting and review at the next RMS meeting.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | July 25, 2017 RM 168--Cancelled August 15, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Monica Jones NRG
Kyle Patrick NRG | Kathy Scott CNP
Kaci Jacobs TXU | Kim Wall Hansen Technologies
Lindsay Butterfield ERCOT | Carolyn Reed CNP
Jim Lee AEP | Rebecca Zerwas NRG
Sam Pak ONCOR
Attendees Webex
Becky Taylor CNP | Deb Belin Aurea
Kathryn Thurman ERCOT | Crystal Luna Stream
Kelly Tidwell Direct Energy | Mary Sithahao
Paul Yockey ERCOT
Mark Ruane ERCOT
Dave Michelsen ERCOT
Deborah Croce ECInfoSystem