## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to ROS
September 7, 2017
Dylan Preas
PGDTF Vice-Chairman
<number>
9/7/2017 ROS Meeting

## Slide 2: 2017 PGDTF Goals
R1 PGRR Approval
PGDTF Contact List
GIC Model Completion & Review
Assessment/Model Building Timeline Recommendation
Vulnerability Assessment Scope/Criteria Recommendation
Procedure Manual Update
Corrective Action Plan development and “approval” process recommendation
***Current Active Items
9/7/2017 ROS Meeting
<number>

## Slide 3: Activities of the PGDTF – August
Met on August 24th
NERC TPL-007-1 R3 Criteria Discussion (NERC enforceable 1/01/2022)
    System Steady State Voltage Performance during the benchmark GMD event
    Proposed criteria paper presented and discussed
    ERCOT to develop draft language (target 10/1) – future PGRR
GIC System Model Procedure Manual Updates
GIC Data Protection
Draft Vulnerability Assessment Scope Discussion
GIC model work session on August 25th canceled due to incomplete RARF submissions
<number>
9/7/2017 ROS Meeting

## Slide 4: Next PGDTF Meeting
7/9/2015 ROS Meeting
<number>

## Slide 5: Updated Schedule for GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
6/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT. Incomplete
11/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs. Delayed due to insufficient data…
12/1/2017 – TSPs and REs Provide GIC Model Changes/Updates to ERCOT. Delayed due to insufficient data…
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases. NERC Enforceable from 7/1/2018 (R2)
<number>
9/7/2017 ROS Meeting

## Slide 6: Questions and Answers
<number>