| PGRR Number | 059 | PGRR Title | Related to NPRR837, Regional Planning Group (RPG) Process Reform |
| --- | --- | --- | --- |

| Date | September 8, 2017 |
| --- | --- |

| Submitter’s Information |
| --- |
| Name | Wes Woitt |
| E-mail Address | wesley.woitt@centerpointenergy.com |
| Company | CenterPoint Energy Houston Electric, LLC |
| Phone Number | (713) 207-2760 |
| Cell Number |  |
| Market Segment | Investor Owned Utility |

Comments

CenterPoint Energy Houston Electric, LLC appreciates the opportunity to submit these comments supporting ERCOT’s proposed changes to enhance and clarify the Regional Planning Group (RPG) process and proposes several additional changes and clarifications for consideration by ERCOT and stakeholders.

Revised Cover Page Language

None

Revised Proposed Guide Language

#### 3.1.2.1	All Projects

(1)	The submittal of each transmission project (60 kV and above) for RPG Project Review should include the following elements:

(a)	The proposed project description including expected cost, feasible alternative(s) considered, transmission topology and Transmission Facility modeling parameter data, and all study cases used to generate results supporting the need for the project in electronic format (powerflow data should be in PTI PSS/E RAWD format).  Also, the submission should include accurate maps and one-line diagrams showing locations of the proposed project and feasible alternatives;

(b)	Identification of the SSWG, Dynamics Working Group (DWG), or Regional Transmission Plan powerflow cases used as a basis for the study and any associated changes that describe and allow accurate modeling of the proposed project;

(c)	Description and data for all changes made to the SSWG base cases or Regional Transmission Plan cases used to identify the need for the project, such as Generation Resource unavailability and area peak Load forecast;

(d)	A description of the reliability and/or economic problem that is being solved;

(e)	Desired/needed in-service date for the project, and feasible in-service date, if different;

(f)	The phone number and email address of the single point of contact who can respond to ERCOT and RPG participant questions or requests for additional information necessary for stakeholder review; and

(g)	Analysis of rejected alternatives, including cost estimates, and other factors considered in the comparison of alternatives with the proposed project.

(2)	Both transmission and distribution solutions to performance deficiencies may be considered where applicable.

(3)	If there is any other information, not included above, that the submitting party believes is relevant to consideration of the need for any submitted project, the submitting party should include that information in the project submission.

### 3.1.5	Regional Planning Group Comment Process

(1)	Any stakeholder may initiate an RPG project review in accordance with Protocol Section 3.11.4.1, Project Submission.  All project submissions should be sent electronically to rpg_submittal@ercot.com.  The RPG project review consists of the following steps.

(a)	ERCOT will provide electronic copies of RPG project review submittals by email to the RPG within five Business Days of receipt and solicit comments or questions from the RPG;

(b)	All concerns/questions or objections about the submitted project by any stakeholder or ERCOT should be submitted by email to the RPG within 15 Business Days after ERCOT’s transmittal to the RPG;

(c)	Each Entity providing comments should provide a “single” complete comment about each project by the end of the 15 Business Day comment period rather than sending multiple comments at various times or from various individuals;

(d)	Any questions related to data deficiency should be submitted to ERCOT and the submitting party immediately;

(e)	If concerns or objections about a project are received during the 15 Business Day comment period, the project will be put into “study mode.” During study mode, the submitting party shall respond to any concerns or objections and provide additional information, if necessary, by email to the RPG until all concerns are resolved or until ERCOT assesses that a reasonable effort has been made to resolve all concerns or objections. A submitting party may make modifications to a Tier 3 project to address concerns or objections without having to resubmit the project so long as the modifications do not result in the project being classified as a Tier 1 or 2 project. Study mode shall end no later than 20 Business Days following the end of the comment period, unless ERCOT finds good cause to extend study mode;

(f)	The submitting party should answer all questions and respond to all concerns in a timely manner;

(g)	Comments should be based on Good Utility Practice and sound engineering judgment. Suggestions should be able to be implemented by the TSP constructing and operating the project; and

(h)	ERCOT will post all project submissions, the comments received, and other information and databases associated with submitted transmission projects on the MIS Secure Area.

(i)	Comments received after the 15 Business Day comment period may be considered by ERCOT or the submitting party, but a response is not required.