## Projects
Generator Interconnection Status Report | August 2017
Date: 9/1/2017 3:45:12 PM

## Newly Operational & Cancelled
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | 50 | Pecos | 2017-08-24
16INR0065b | SPTX12B (CED Upton Solar) | 157.5 | Upton | 2017-06-30
New Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
16INR0122 | Blue Summit Battery | 30 | Wilbarger | 2017-08-11
17INR0027 | Dermott Wind 1 | 250 | Scurry | 2017-08-01
16INR0065b | SPTX12B (CED Upton Solar) | 157.5 | Upton | 2017-08-25
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
Projects Cancelled by the Developer*
INR | Project | MW | County | Cancellation Date
20INR0007 | Aubrac Solar | 300 | Reeves | 2017-08-14
20INR0006 | Barzona Solar | 150 | Pecos | 2017-08-14
20INR0004 | Sanco 2 Solar | 150 | Deaf Smith | 2017-08-14
19INR0025 | Duck Creek W | 400 | Dickens | 2017-08-31
19INR0024 | Lacy Creek W | 400 | Glasscock | 2017-08-31
18INR0047 | Comanche South Solar | 25 | Comanche | 2017-08-15
18INR0037 | Burkburnett Solar | 75 | Wichita | 2017-08-25
18INR0036 | Bacon Switch Solar | 150 | Wichita | 2017-08-25
14INR0056 | Payne Mt Wind | 101 | Mills | 2017-09-01
14INR0048_1 | Blue Summit W 2 | 114 | Wilbarger | 2017-09-01
14INR0014 | West Ranch Solar | 100 | Val Verde | 2017-09-01
14INR0011 | Chamisa CAES | 270 | Swisher | 2017-09-01
13INR0056b | Fluvanna Renewable 2 | 152 | Scurry | 2017-09-01
13INR0020b | Rattlesnake W 2 | 158 | Glasscock | 2017-08-31
13INR0006 | Grandview (Last) W | 750 | Gray | 2017-09-01
12INR0018 | Pampa Wind | 500 | Gray | 2017-08-17
12INR0002b | Silver Canyon Wind B | 200 | Briscoe | 2017-08-01
10INR0009 | Caprock Wind | 300 | Castro | 2017-09-01
*Includes only those projects cancelled after developer makes a Full Interconnection Study request.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | FIS Pending or Completed (MW) | IA Executed, FIS Pending or Approved (MW) | IA Executed, FIS Pending (MW) | Grand Total (MW)**
Currently tracking 321 generation interconnection or change requests |  | Gas-AllOther | 300 | 2636 | 5572 |  | 8508
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  | Gas-CombinedCycle | 0 | 1939 | 4615 |  | 6554
August 31, 2017 | Number of Projects | Gas-Compressed Air (CE) | 0 | 0 | 324 |  | 324
Security Screening Studies (SSS) Underway | 21 | Total Gas | 300 | 4575 | 10511 |  | 15386
SSS Completed | 59 | Nuclear | 0 |  | 0 |  | 0
Full Interconnect Study (FIS) Underway | 155 | Coal | 0 | 0 | 0 |  | 0
FIS Completed | 6 | Wind | 3661 | 15794 | 9150 |  | 28605
Interconnection Agreement Executed, FIS Pending or Completed | 40 | Battery | 0 | 0 | 0 |  | 0
Interconnection Agreement Executed | 40 | Solar | 9350 | 11633 | 1868 |  | 22851
Total Interconnection Requests | 321 | Biomass | 0 | 0 | 0 |  | 0
Cancelled Studies (since last month) | 17 | Petroleum Coke | 0 | 0 | 0 |  | 0
| Capacity, MW | Total | 13311 | 32002 | 21529 |  | 66842
Total Capacity Under Study * | 66842 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l). If the capacity for a single project is reported in the column, the value is redacted.
Interconnection Agreements Executed | 21529
Cancelled (since last month) | 3545 | ** Redacted project capacity from column E is excluded from the Grand Totals.
* Redacted project capacity is excluded. |  | Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
FIS Pending or Completed column: Total MW capacity for which an FIS is either pending or completed and reviewed by ERCOT. The column total matches the sum of capacity values reported in the Full Study tab.
IA Executed, FIS Pending or Approved column: Total MW capacity for which a FIS has been requested and approved, and an IA has been executed. The column total matches the sum of capacity values reported in the IA Table tab

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement as of August 31, 2017
GINR Reference Number | Project Name* | Point of Interconnection (POI) | County | Fuel | Capacity to Grid (MW) | Projected Month/Year (as specified by the resource developer) | Status
17INR0065 | Capricorn Ridge III repowering |  | Sterling | WIND | 0 | 10/2017 | Incomplete
17INR0064 | Capricorn Ridge II repowering |  | Sterling | WIND | 0 | 10/2017 | Incomplete
17INR0063 | Capricorn Ridge I repowerng |  | Sterling | WIND | 0 | 10/2017 | Incomplete
17INR0061 | Capricorn Ridge IV repowering |  | Sterling | WIND | 9 | 10/2017 | Incomplete
17INR0060 | Horse Hollow IV repowering |  | Taylor | WIND | 0 | 10/2017 | Incomplete
17INR0058 | Horse Hollow II repowering |  | Taylor | WIND | 0 | 10/2017 | Incomplete
17INR0057 | Red Canyon repowering |  | Borden | WIND | 6 | 10/2017 | Incomplete
17INR0054 | Capricorn I & III repowering | 180757 Capricorn Ridge 3 138kV | Sterling | WIND | 32 | 10/2017 | Incomplete
17INR0056 | Callahan repowering |  | Callahan | WIND | 0 | 10/2017 | Complete
17INR0053 | HHGT increase | 7046 Kendal 345kV | Taylor | WIND | 44 | 4/2018 | Incomplete
17INR0052 | HHGT increase | 6216 Bluff Creek 138kV | Taylor | WIND | 44 | 4/2018 | Incomplete
17INR0045 | Castleman Victoria | 8143 Dupont 138kV | Victoria | GAS | 100 | 4/2018 | Incomplete
18INR0043 | Edmondson Ranch Wind | 59903 Bearkat 345kV | Glasscock | WIND | 292 | 5/2018 | Incomplete
15INR0062b | Hale Community W 2 | 79506 Abernathy 345kV | Hale | WIND | 122 | 5/2018 | Incomplete
15INR0057 | TXP Ricebird |  | Wharton | GAS | 142 | 5/2018 | Incomplete
15INR0055 | TXP Sealy G | 44255 Foster 138kV | Austin | GAS | 142 | 5/2018 | Incomplete
18INR0038 | Jumbo Hill Wind | 1134 Littman bus 138kV | Andrews | WIND | 200 | 6/2018 | Incomplete
18INR0033 | Irion County Wind | 76005 Schneeman Draw 345kV | Irion | WIND | 301 | 6/2018 | Incomplete
17INR0046c | Ivory Solar C | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 50 | 6/2018 | Incomplete
17INR0024 | Pecan Creek 2 Gas | tap one 345kV 11420 Sweetwater - 11406 Central Bluff ckt | Nolan | GAS | 350 | 6/2018 | Incomplete
12INR0055 | Little Mountain Wind | tap 69kV radial LakeKempSw 782 - LakeKemp 783 | Baylor | WIND | 80 | 6/2018 | Incomplete
17INR0048 | Greens Bayou Expansion II |  | Harris | GAS | 149 | 6/2018 | Complete
18INR0064 | Silver Star repowering | 150511 Flat Creek 34.5kV | Eastland | WIND | -7 | 7/2018 | Incomplete
18INR0059 | Raymond Wind | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 201 | 7/2018 | Incomplete
16INR0014 | Cattleman Wind A | 79501 Ogallala 345kV | Castro | WIND | 200 | 7/2018 | Incomplete
14INR0074 | Frame Switch Energy | 3673 Taylor-West 138kV | Williamson | GAS | 92 | 7/2018 | Incomplete
13INR0025 | Buffalo Wind 1 | 79504 AJ Swope 345kV | Randall | WIND | 150 | 7/2018 | Complete
18INR0045 | Misae Solar | 60501 Tesla 345kV | Childress | SOLAR | 241 | 9/2018 | Incomplete
18INR0029 | Armstrong Wind | tap one 345kV 79500 Alibates - 79503 Tule Canyon ckt | Armstrong | WIND | 278 | 9/2018 | Incomplete
18INR0052 | Barclay BrEl PV | tap 69kV 69 Barclay - 65 Silver City | Falls | SOLAR | 25 | 10/2018 | Incomplete
18INR0042 | Kaiser Creek Wind | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WIND | 100 | 10/2018 | Incomplete
18INR0027 | Crane Solar | tap 138kV 76032 NMcCamey - 60361 Santa Rita | Upton | SOLAR | 150 | 10/2018 | Incomplete
18INR0022 | RES Wink Solar | tap 138kV 1009 Yucca - 1146 Notrees | Winkler | SOLAR | 150 | 10/2018 | Incomplete
17INR0025 | Reloj Del Sol Wind | 80220 Cenizo 345kV | Zapata | WIND | 202 | 10/2018 | Incomplete
16INR0093 | Tarbush Solar | 38069 Flat Top 138kV | Reeves | SOLAR | 48 | 10/2018 | Incomplete
16INR0089 | NW Andrews Solar | 1272 Fullerton 138kV | Andrews | SOLAR | 60 | 10/2018 | Incomplete
18INR0067 | Gopher Creek Wind | 11306 Dermott 138kV | Scurry | WIND | 160 | 11/2018 | Incomplete
18INR0050 | Mustang Creek Solar | 138 kV STEC ETP substation (5523) or 69 kV STEC Louise (5528) | Jackson | SOLAR | 120 | 11/2018 | Incomplete
18INR0035 | CityVict | 8172 Victoria 138kV | Victoria | GAS | 100 | 11/2018 | Incomplete
17INR0035 | Las Majadas Wind | 80512 MagVltap 345kV | Willacy | WIND | 227 | 11/2018 | Incomplete
18INR0058 | Texana Solar | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOLAR | 150 | 12/2018 | Incomplete
18INR0055 | Long Draw Solar | 59900 Long Draw 345kV | Borden | SOLAR | 225 | 12/2018 | Incomplete
18INR0051 | Byers Wind | tap one 345kV 6101 Riley - 1730 WKrum ckt | Clay | WIND | 200 | 12/2018 | Incomplete
18INR0049 | Santa Rita Solar | 76005 Schneeman Draw 345kV | Crockett | SOLAR | 400 | 12/2018 | Incomplete
18INR0044 | Bluegrove Wind | Line tap between buses LKAROWHD_8 [1468] and NEWPRT_P8 [1470] | Clay | WIND | 100 | 12/2018 | Incomplete
18INR0039 | Sptx | tap 138kV 6601 Rio Pecos - 76615 Crane | Crane | SOLAR | 300 | 12/2018 | Incomplete
18INR0034 | Blanco Canyon Wind | 59904 Cottonwood 345kV | Crosby | WIND | 251 | 12/2018 | Incomplete
18INR0023 | Lost Mines Wind | 60708 Orsted 345kV | Menard | WIND | 250 | 12/2018 | Incomplete
18INR0014 | Karankawa Wind Alt A | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | WIND | 200 | 12/2018 | Incomplete
17INR0046a | Ivory Solar A | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 50 | 12/2018 | Incomplete
17INR0043 | Vaquero Option 2 W | tap 345kV 8905 N Edinb - 8455 Lon Hill | Brooks | WIND | 400 | 12/2018 | Incomplete
17INR0038 | Vaquero 2 Wind | 80220 Cenizo 345kV | Zapata | WIND | 400 | 12/2018 | Incomplete
17INR0037 | Palmas Altas Wind | 5764 E Rio Hondo 138kV + 8mi radial | Cameron | WIND | 145 | 12/2018 | Incomplete
17INR0033 | Tecovas 2 W | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 12/2018 | Incomplete
17INR0032 | Freer Wind | 8891 Government Well 69kV | Duval | WIND | 53 | 12/2018 | Incomplete
17INR0031 | Espiritu Wind | 5764 E Rio Hondo 138kV | Cameron | WIND | 150 | 12/2018 | Incomplete
17INR0030 | Estacado Solar | 79502 Windmill 345kV | Deaf Smith | SOLAR | 100 | 12/2018 | Incomplete
16INR0119 | Wake Solar | 59904 Cottonwood 345kV | Crosby | SOLAR | 150 | 12/2018 | Incomplete
16INR0117 | Tecovas 1 W | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 12/2018 | Incomplete
16INR0115 | Waymark Solar | 76002 Bakersfield 345kV | Pecos | SOLAR | 182 | 12/2018 | Incomplete
16INR0111 | Las Lomas Wind | 8957 Lopeno 138kV | Starr | WIND | 200 | 12/2018 | Incomplete
16INR0106 | Andrews County Solar | 1281 Amoco Midland tap 69kV | Andrews | SOLAR | 150 | 12/2018 | Incomplete
16INR0105 | Vaquero Wind | 80230 Molina 138kV | Jim Hogg | WIND | 300 | 12/2018 | Incomplete
16INR0104 | Big Sampson Wind | 76005 Schneeman Draw 345kV | Crockett | WIND | 400 | 12/2018 | Incomplete
16INR0100 | Hecate Solar C | tap 138kV 60385 Solstice - 6680 Alamito | Brewster | SOLAR | 150 | 12/2018 | Incomplete
16INR0099 | Hecate Solar B | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | SOLAR | 50 | 12/2018 | Incomplete
16INR0098 | Hecate Solar A | near 6674 Bronco 69kV | Brewster | SOLAR | 50 | 12/2018 | Incomplete
16INR0097 | Morada Del Sol Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | SOLAR | 200 | 12/2018 | Incomplete
16INR0092 | River Rock Solar | near 6674 Bronco 69kV | Brewster | SOLAR | 50 | 12/2018 | Incomplete
16INR0085 | Priddy Wind | tap one 345kV 1444 Brown – 3422 Killeen | Mills | WIND | 300 | 12/2018 | Incomplete
16INR0076 | Brazoria Energy G | New 138kV sub near Amoco (#42090) | Brazoria | GAS | 135 | 12/2018 | Incomplete
16INR0061 | WIT Ranch Wind | tap one 345kV 60500 Edith Clarke- 60501 Tesla | Hardeman | WIND | 200 | 12/2018 | Incomplete
16INR0033 | Hart Wind | 79501 Ogallala 345kV | Castro | WIND | 150 | 12/2018 | Incomplete
16INR0029 | Hubbard Wind | tap 345kV 68090 Sam Sw - 3405 Tradinghouse | Hill | WIND | 200 | 12/2018 | Incomplete
16INR0027 | Bonham Wind | tap 345kV 1685 Farmersville - 1729 ValleySouth | Grayson | WIND | 100 | 12/2018 | Incomplete
16INR0014b | Cattleman Wind B | 79501 Ogallala 345kV | Castro | WIND | 200 | 12/2018 | Incomplete
16INR0012 | Kenedy Project 2 W | 80071 Zorillo 345kV | Kenedy | WIND | 200 | 12/2018 | Incomplete
15INR0081 | Mason Mt Wind | tap 138kV 6364 Yellowjacket - 76390 Ft Mason | Mason | WIND | 62 | 12/2018 | Incomplete
15INR0072 | Barilla Solar 3 | 181652 Hovey 138kV | Pecos | SOLAR | 140 | 12/2018 | Incomplete
15INR0063b | Easter Wind B | tap one 345kV 79501 Ogallala - 79502 Windmill ckt | Castro | WIND | 101 | 12/2018 | Incomplete
15INR0063 | Easter Wind A | 79502 Windmill 345kV | Castro | WIND | 200 | 12/2018 | Incomplete
15INR0062 | Hale Community W 1 | 79506 Abernathy 345kV | Hale | WIND | 200 | 12/2018 | Incomplete
15INR0054 | TXP Reeves G | 6657 Coyanosa 138kV | Reeves | GAS | 123 | 12/2018 | Incomplete
15INR0053 | TXP Winkler G | tap 138kV 1074 Wink - 1009 Yucca Dr near Wink | Winkler | GAS | 123 | 12/2018 | Incomplete
15INR0051 | Tierra Blanca W | 79501 Ogallala 345kV | Castro | WIND | 200 | 12/2018 | Incomplete
15INR0044 | Ocelot Solar | 80219 Lobo 345kV | Webb | SOLAR | 200 | 12/2018 | Incomplete
13INR0006 | Grandview (Last) W | 79000 Gray 345kV | Gray | WIND | 750 | 12/2018 | Incomplete
18INR0016 | Heart of Texas Wind | 76006 Bow Wood 345kV | McCulloch | WIND | 150 | 12/2018 | Complete
16INR0112 | Loma Pinta Wind | 5705 Fowlerton 138kV | La Salle | WIND | 200 | 12/2018 | Complete
19INR0093 | Sole Mio | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | SOLAR | 45 | 1/2019 | Incomplete
19INR0031 | Bestla Solar | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | SOLAR | 150 | 1/2019 | Incomplete
19INR0029 | Phoebe Solar | tap 138kV 1009 Yucca - 1146 Notrees OR tap Vest-Yukon | Winkler | SOLAR | 300 | 1/2019 | Incomplete
19INR0044 | Lily Solar | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | SOLAR | 150 | 3/2019 | Incomplete
19INR0041 | Myrtle Solar | 138kV Angleton 42110 or line tap to Rosharon 44600 | Brazoria | SOLAR | 200 | 3/2019 | Incomplete
19INR0020c | SP-Pecos Bend Solar C | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 3/2019 | Incomplete
19INR0020b | SP-Pecos Bend Solar B | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 3/2019 | Incomplete
19INR0020 | SP-Pecos Bend Solar A | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 3/2019 | Incomplete
18INR0062 | Wagyu Solar | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | SOLAR | 100 | 3/2019 | Incomplete
18INR0061 | Shakes Solar | Line tap between ASHERTON4A [8283] and W_BATESV4A [8236] | Zavala | SOLAR | 42 | 3/2019 | Incomplete
18INR0060 | Brightside Solar | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOLAR | 50 | 3/2019 | Incomplete
18INR0056 | Hallmark Solar | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | SOLAR | 50 | 3/2019 | Incomplete
17INR0046b | Ivory Solar B | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 50 | 3/2019 | Incomplete
14INR0009 | WKN Amadeus Wind | tap 345kV 11305 Dermott - 60704 Kirchhof | Kent | WIND | 248 | 3/2019 | Incomplete
19INR0094 | GSE Three Solar | 6044 Turkey 69kV | Hall | SOLAR | 50 | 4/2019 | Incomplete
19INR0091 | GSE ONE Solar | 1808 Bonham 138kV | Fannin | SOLAR | 100 | 4/2019 | Incomplete
19INR0056 | Chamon Phase 2 | 40260 Chamon 138kV | Harris | GAS | 100 | 4/2019 | Incomplete
18INR0040 | Soda Lake Solar 1 and 2 | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | SOLAR | 400 | 4/2019 | Incomplete
16INR0036 | Pecan Creek 1 Gas | tap one 345kV 11420 Sweetwater - 11406 Central Bluff ckt | Nolan | GAS | 280 | 4/2019 | Incomplete
19INR0092 | Prospero Solar | 79650 Clear Fork 345kV (or 1158 Andrews Co 345kV) | Andrews | SOLAR | 600 | 5/2019 | Incomplete
18INR0030 | Canyon Wind | 11319 ScurryCounty 138kV | Scurry | WIND | 301 | 5/2019 | Incomplete
20INR0011 | Ranchero Wind | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WIND | 250 | 6/2019 | Incomplete
19INR0028 | Normande Solar Farm | 59900 Long Draw 345kV | Borden | SOLAR | 300 | 6/2019 | Incomplete
19INR0019 | Foard City Wind | 60500 Edith Clarke 345kV | Foard | WIND | 350 | 6/2019 | Incomplete
19INR0017 | Crane County Solar | (2) 138kV lines near Permian | Crane | SOLAR | 400 | 6/2019 | Incomplete
19INR0009 | Holstein Solar | 11406 Central Bluff 345kV | Nolan | SOLAR | 200 | 6/2019 | Incomplete
19INR0001 | Texas Solar Nova | tap one 345kV 11305 Dermott - 59904 Cottonwood ckt | Kent | SOLAR | 750 | 6/2019 | Incomplete
16INR0102 | Hecate Sun Valley 130 | 6601 Rio Pecos 138kV | Pecos | SOLAR | 130 | 6/2019 | Incomplete
16INR0101 | Hecate Sun Valley 57 | 6641 Sun Valley 69kV | Pecos | SOLAR | 57 | 6/2019 | Incomplete
19INR0083 | Oberon Solar | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | SOLAR | 180 | 8/2019 | Incomplete
18INR0009 | FGE Eagle Pines I | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | GAS | 1156 | 8/2019 | Incomplete
19INR0098 | Pease River Wind | 60500 Edith Clarke 345kV | Hardeman | WIND | 301 | 9/2019 | Incomplete
19INR0038 | High Lonesome W | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WIND | 500 | 9/2019 | Incomplete
19INR0101 | Tehuacana Wind | 46020 Limestone 345kV + 34mi gentie | Limestone | WIND | 600 | 10/2019 | Incomplete
19INR0100 | Prairie Hill Wind | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | Limestone | WIND | 300 | 10/2019 | Incomplete
19INR0053 | Hidalgo II Wind | 161705 Mirasole 345kV | Hidalgo | WIND | 51 | 10/2019 | Incomplete
19INR0045 | Rayos Del Sol | Two POIs tested in Screening study. POI 1: a tap to the 345kV line between Palmito (5966) and Steward (80137) | Cameron | SOLAR | 150 | 10/2019 | Incomplete
19INR0007 | Charbray Solar | 1032 Morgan Creek 138kV | Mitchell | SOLAR | 200 | 10/2019 | Incomplete
19INR0004 | Sanco Solar | 79502 Windmill 345kV | Deaf Smith | SOLAR | 400 | 10/2019 | Incomplete
19INR0006 | Bluebonnet Solar | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | SOLAR | 61 | 11/2019 | Incomplete
16INR0081 | Rio Bravo II Wind | 80355 Del Sol 345kV | Starr | WIND | 202 | 11/2019 | Incomplete
20INR0008 | Yellow Jacket Wind | tap 345kV 7046 Kendal - 60618 Edison | Menard | WIND | 200 | 12/2019 | Incomplete
19INR0121 | Galloway Solar | tap 345kV 6444 Red Creek - 76006 Bowwood OR 1444 Brown - 76009 TwinButtes | Concho | SOLAR | 360 | 12/2019 | Incomplete
19INR0113 | County Line Solar | 60385 Solstice 138kV | Reeves | SOLAR | 250 | 12/2019 | Incomplete
19INR0088 | Aragorn Solar | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | SOLAR | 150 | 12/2019 | Incomplete
19INR0073 | Shakes Solar II | 8283 Asherton 138kV | Zavala | SOLAR | 158 | 12/2019 | Incomplete
19INR0055 | Monte Cristo II W | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0054 | Monte Cristo 1 W | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0052 | Truscott Gilliland East W | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0051 | Truscott Gilliland West W | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0049 | Willacy Exp West II W | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0048 | Willacy Exp West I W | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0039 | Hubbard West Wind | 3406 Elm Mott 345kV + 13mi gen tie | McLennan | WIND | 201 | 12/2019 | Incomplete
19INR0033 | Murphy Lake Solar | 6904 CombinRC 138kV | Kaufman | SOLAR | 100 | 12/2019 | Incomplete
19INR0026 | Holstein 2 Solar | 11406 Central Bluff 345kV | Nolan | SOLAR | 100 | 12/2019 | Incomplete
19INR0023 | West Willacy 3 W | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0022 | West Willacy 2 W | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0014 | Formosa Increase |  | Calhoun | GAS | 240 | 12/2019 | Incomplete
19INR0002 | King Mountain Solar | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 350 | 12/2019 | Incomplete
18INR0057 | Green Valley Wind | Tap 138kV 8255 Hamilton - 8680 Rough Canyon | Val Verde | WIND | 500 | 12/2019 | Incomplete
18INR0031 | Maryneal Wind | 71050 Bitter Creek 345kV | Nolan | WIND | 180 | 12/2019 | Incomplete
17INR0036 | Grandview 4 Phase A Wind | tap 345kV 79000 Gray - 79006 Allen | Gray | WIND | 200 | 12/2019 | Incomplete
15INR0034 | El Algodon Alto W | tap 345kV 8455 Lon Hill - 5725 Pawnee OR 8455 Lon Hill - 8164 Coleto | San Patricio | WIND | 201 | 12/2019 | Incomplete
18INR0018 | Matagorda Bay Wind | tap 345kV 5915 STP - 42500 Dow | Matagorda | WIND | 150 | 12/2019 | Complete
20INR0026 | Longbow Solar | 42870 Liverpool 138kV | Brazoria | SOLAR | 60 | 3/2020 | Incomplete
20INR0003 | Shorthorn Solar | 60501 Tesla 345kV | Childress | SOLAR | 200 | 3/2020 | Incomplete
20INR0002 | Lake Spring Solar | 79501 Ogallala 345kV | Castro | SOLAR | 360 | 6/2020 | Incomplete
19INR0030 | San Bernard Solar | 43340 Tx Gulf Sulphur 138kV | Wharton | SOLAR | 100 | 6/2020 | Incomplete
20INR0005 | Shorthorn 2 Solar | 60501 Tesla 345kV | Childress | SOLAR | 200 | 10/2020 | Incomplete
18INR0005 | Panda Sherman 2 G | 1758 Payne 138kV | Grayson | GAS | 543 | 12/2020 | Incomplete
21INR0002 | Hariana Solar | 6110 East Munday 138kV | Knox | SOLAR | 200 | 6/2021 | Incomplete
17INR0013 | Site C Brazos G | tap one 345kV Venus - 68090 Sam Switch ckt | Hill | GAS | 800 | 8/2021 | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## IA Table
Generation Interconnection Agreements as of August 31, 2017
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name | Interconnecting Entity | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit(s) | Proof of Adequate Water Supplies | FIS completion
18INR0025 | Tahoka Wind | Lincoln Clean | Lynn | 10/2018 | Wind | 505 | Project Name | No | No | N/A | N/A | Complete
14INR0031 | BTE (Baytown Chiller) | Calpine | Chambers | 8/2017 | Gas | 270 | Project Name | Yes | Yes | Yes | N/A | Complete
17INR0042 | CHAMON (Castleman Chamon) | Castleman Power | Harris | 9/2017 | Gas | 100 | Project Name, Projected Date | Yes | Yes | Yes | Yes | Complete
16INR0055 | SANTACRU (Chapman Ranch Wind I) | Enbridge | Nueces | 9/2017 | Wind | 250 | Project Name | Yes | Yes | N/A | N/A | Complete
16INR0023 | LMESASLR (BNB Lamesa Solar 1) | Res Americas | Dawson | 9/2017 | Solar | 102 | Project Name | Yes | Yes | N/A | N/A | Complete
16INR0009 | CALHOUN (Port Comfort) | Castleman Power | Calhoun | 9/2017 | Gas | 100 | Project Name, Projected Date | Yes | Yes | Yes | Yes | Complete
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | OCI Solar | Pecos | 9/2017 | Solar | 50 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0061 | LASSO (SolaireHolman 1) | Solaire Direct | Brewster | 9/2017 | Solar | 50 | Project Name | Yes | Yes | N/A | N/A | Complete
14INR0038 | BAC (PHR Peakers) | PHR Holdings | Galveston | 9/2017 | Gas | 390 | Project Name, Projected Date | Yes | Yes | Yes | N/A | Complete
13INR0049 | FEGC (Friendswood) | Friendswood Energy Genco | Harris | 9/2017 | Gas | 129 | Project Name | Yes | Yes | Yes | Yes | Complete
12INR0059b | HOVEY (Barilla Solar 1B) | First Solar | Pecos | 9/2017 | Solar | 7 | Project Name | Yes | Yes | N/A | N/A | Complete
11INR0082a | FERMI (Val Verde Wind ) | Akuo Energy | Val Verde | 9/2017 | Wind | 149 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0054 | NA (NASA-JSC CHP) | NASA | Harris | 10/2017 | Gas | 12 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0060b | SALVTION | Lincoln Clean | Haskell | 10/2017 | Wind | 230 | Project Name | Yes | Yes | N/A | N/A | Complete
14INR0057 | BUCKTHRN | NRG | Erath | 10/2017 | Wind | 96 | Project Name | Yes | Yes | N/A | N/A | Complete
13INR0056 | FLUVANNA | Terna Energy | Scurry | 10/2017 | Wind | 155 | Project Name | Yes | Yes | N/A | N/A | Complete
12INR0002a | Silver Canyon Wind A | EDP Renewables | Briscoe | 10/2017 | Wind | 200 |  | No | No | N/A | N/A | Incomplete
16INR0091 | HICKMAN (Santa Rita Wind) | Invenergy | Reagan | 12/2017 | Wind | 300 | Project Name | Yes | Yes | N/A | N/A | Complete
14INR0041a | BBREEZE | Eon | Willacy | 12/2017 | Wind | 228 | Project Name | Yes | Yes | N/A | N/A | Complete
15INR0064 | NBOHR (BearKat Wind A) | TriGlobal | Glasscock | 12/2017 | Wind | 197 | Project Name | Yes | Yes | N/A | N/A | Incomplete
17INR0022 | MIRAGE (NET Power LaPorte) | Net Power | Harris | 2/2018 | Gas | 11 | Project Name | No | Yes | Yes | No | Complete
15INR0045 | RIGGINS | NRG | Pecos | 2/2018 | Solar | 150 | Project Name | Yes | Yes | N/A | N/A | Complete
16INR0087 | RTS Wind | Goldwind | McCulloch | 3/2018 | Wind | 160 |  | Yes | Yes | N/A | N/A | Complete
15INR0082 | FTWIND (Flat Top Wind I) | Alterra Power | Comanche | 3/2018 | Wind | 200 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Incomplete
17INR0017 | Clear Springs G | Navasota | Guadalupe | 6/2018 | Gas | 558 |  | No | No | Yes | No | Complete
17INR0016 | Navasota South Peaker | Navasota | Wilson | 6/2018 | Gas | 582 |  | No | No | Yes | No | Complete
16INR0065 | CASL_GAP (Castle Gap Solar) | Vistra Energy/Luminant | Upton | 6/2018 | Solar | 180 | Project Name | Yes | Yes | N/A | N/A | Complete
18INR0013 | Denton Energy Center | Denton Municipal Electric | Denton | 7/2018 | Gas | 226 |  | Yes | Yes | Yes | N/A | Complete
16INR0086 | Cactus Flats Wind | RES Americas | Concho | 7/2018 | Wind | 150 |  | No | No | N/A | N/A | Incomplete
14INR0044 | West of Pecos Solar | Eon | Reeves | 7/2018 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0062b | Lockett Wind | Lincoln Clean | Wilbarger | 9/2018 | Wind | 184 |  | Yes | Yes | N/A | N/A | Complete
16INR0003 | Freeport LNG | Freeport LNG | Brazoria | 9/2018 | Gas | 11 |  | Yes | Yes | Yes | N/A | Complete
13INR0026 | Canadian Breaks Wind | Macquarie Cap | Oldham | 9/2018 | Wind | 210 | MW For Grid | No | No | N/A | N/A | Complete
13INR0010a | Mariah Del Este | Mariah Acquisition | Parmer | 9/2018 | Wind | 152 |  | Yes | Yes | N/A | N/A | Incomplete
11INR0062 | Patriot Wind | NRG | Nueces | 9/2018 | Wind | 180 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0038 | Swisher Wind | Exelon | Swisher | 10/2018 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
15INR0050 | Unity Wind | Miller Wind | Deaf Smith | 10/2018 | Wind | 203 |  | No | No | N/A | N/A | Incomplete
14INR0033 | Goodnight Wind | FGE Power | Armstrong | 10/2018 | Wind | 500 | Projected Date | No | No | N/A | N/A | Incomplete
16INR0074 | Chocolate Bayou W | Pioneer Green | Brazoria | 11/2018 | Wind | 150 |  | No | No | N/A | N/A | Complete
15INR0090 | Pflugerville Solar | RRE Solar | Travis | 12/2018 | Solar | 120 |  | No | No | N/A | N/A | Complete
12INR0060 | Infinity Live Oak Wind | Infinity Wind | Schleicher | 12/2018 | Wind | 201 |  | Yes | Yes | N/A | N/A | Complete
17INR0020a | RE Maplewood 2a Solar | Recurrent Energy | Pecos | 12/2018 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0005 | Rio Bravo I Wind | Longroad Energy | Starr | 12/2018 | Wind | 238 | NEW | No | No | N/A | N/A | Incomplete
16INR0121 | Salt Fork Wind Expansion | Southern Power Company | Carson | 12/2018 | Wind | 54 |  | No | No | N/A | N/A | Incomplete
16INR0114 | Upton Solar | SunPower | Upton | 12/2018 | Solar | 102 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0037c | Pumpkin Farm Wind | Apex Clean | Floyd | 12/2018 | Wind | 281 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
16INR0019 | Capricorn Ridge Solar | Nextera | Coke | 12/2018 | Solar | 100 |  | No | No | N/A | N/A | Incomplete
14INR0030c | Panhandle Wind 3 | Pattern Energy | Carson | 12/2018 | Wind | 248 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0023b | Longhorn South W | EDF Renewables | Briscoe | 12/2018 | Wind | 160 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
13INR0045 | Changing Winds | TriGlobal | Castro | 12/2018 | Wind | 288 |  | No | No | N/A | N/A | Incomplete
13INR0010c | Mariah Del Sur | Mariah Acquisition | Parmer | 12/2018 | Wind | 218 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0059 | Pecos Solar I | Bobcat Hill Solar | Pecos | 1/2019 | Solar | 108 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0023 | Indeck Wharton | Indeck Energy Services | Wharton | 2/2019 | Gas | 654 |  | No | No | Yes | Yes | Complete
16INR0023b | Lamesa Solar B (Phase II) | BNB Renewables | Dawson | 3/2019 | Solar | 98 | Projected Date | No | No | N/A | N/A | Incomplete
11INR0054 | Midway Wind | Apex Clean | San Patricio | 3/2019 | Wind | 161 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
16INR0008 | Tenaska Roans Prairie | Tenaska | Grimes | 4/2019 | Gas | 663 |  | No | No | Yes | No | Complete
16INR0010 | FGE Texas 1 | FGE Power | Mitchell | 4/2019 | Gas | 745 |  | No | No | Yes | Yes | Incomplete
15INR0064b | BearKat Wind B | TriGlobal | Glasscock | 4/2019 | Wind | 163 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
16INR0044 | Halyard Wharton | Halyard Energy | Wharton | 6/2019 | Gas | 419 |  | No | No | Yes | Yes | Complete
14INR0027 | Guadalupe II | Calpine | Guadalupe | 6/2019 | Gas | 362 |  | No | Yes | Yes | No | Complete
16INR0045 | Halyard Henderson | Halyard Energy | Henderson | 6/2019 | Gas | 450 |  | No | No | Yes | Yes | Incomplete
18INR0001 | Rockwood G | Lincoln Clean | Colorado | 7/2019 | Gas | 1122 |  | No | No | Yes | No | Incomplete
17INR0027b | Coyote Wind | Lincoln Clean | Scurry | 9/2019 | Wind | 250 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
17INR0010 | FGE Texas II | FGE Power | Mitchell | 9/2019 | Gas | 799 |  | No | No | Yes | No | Incomplete
16INR0049 | Nazareth Solar | Lincoln Clean | Castro | 10/2019 | Solar | 201 |  | No | No | N/A | N/A | Complete
15INR0079 | Pullman Road Wind | SunEdison | Randall | 10/2019 | Wind | 300 |  | No | No | N/A | N/A | Complete
18INR0004 | Shawnee G | Lincoln Clean | Hill | 10/2019 | Gas | 928 |  | No | No | Yes | No | Incomplete
17INR0020c | RE Maplewood 2c Solar | Recurrent Energy | Pecos | 12/2019 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020b | RE Maplewood 2b Solar | Recurrent Energy | Pecos | 12/2019 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045b | Torrecillas Wind B | Nextera | Webb | 12/2019 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045a | Torrecillas Wind A | Nextera | Webb | 12/2019 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0005c | Grandview W 3 | Eon | Carson | 12/2019 | Wind | 188 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Avangrid | Swisher | 12/2019 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
16INR0006 | Pinecrest G | Coronado Ventures | Angelina | 4/2020 | Gas | 785 |  | No | No | Yes | Yes | Incomplete
15INR0035 | Stella 1 Wind | Eon | Kenedy | 6/2020 | Wind | 201 | NEW | No | No | N/A | N/A | Incomplete
13INR0010def | Scandia Wind DEF | Scandia Southwest | Parmer | 8/2020 | Wind | 600 | Projected Date | No | No | N/A | N/A | Complete
15INR0013 | Bethel CAES | Apex CAES | Anderson | 11/2020 | Gas/CE | 324 |  | No | No | Yes | Yes | Incomplete
16INR0005 | Brownsville G | Tenaska | Cameron | 12/2020 | Gas | 871 |  | No | No | Yes | No | Complete
17INR0020e | RE Maplewood 2e Solar | Recurrent Energy | Pecos | 12/2020 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020d | RE Maplewood 2d Solar | Recurrent Energy | Pecos | 12/2020 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
11INR0082a | FERMI (Val Verde Wind ) | Val Verde | PLANNED | 2017-09-15 | 2015-08-12 | WIND | WT | 149 | 2017 | TRUE
16INR0055 | SANTACRU (Chapman Ranch Wind I) | Nueces | PLANNED | 2017-09-18 | 2015-07-16 | WIND | WT | 250 | 2017 | TRUE
14INR0060b | SALVTION | Haskell | PLANNED | 2017-10-01 | 2015-05-01 | WIND | WT | 230 | 2017 | TRUE
13INR0056 | FLUVANNA | Scurry | PLANNED | 2017-10-17 | 2015-09-24 | WIND | WT | 155 | 2017 | TRUE
14INR0057 | BUCKTHRN | Erath | PLANNED | 2017-10-27 | 2015-09-10 | WIND | WT | 96 | 2017 | TRUE
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2017-10-31 | 2016-06-22 | WIND | WT | 200 | 2017 | FALSE
14INR0041a | BBREEZE | Willacy | PLANNED | 2017-12-01 | 2015-08-12 | WIND | WT | 228 | 2017 | TRUE
15INR0064 | NBOHR (BearKat Wind A) | Glasscock | PLANNED | 2017-12-29 | 2016-12-20 | WIND | WT | 197 | 2017 | TRUE
16INR0091 | HICKMAN (Santa Rita Wind) | Reagan | PLANNED | 2017-12-31 | 2017-01-03 | WIND | WT | 300 | 2017 | TRUE
16INR0087 | RTS Wind | McCulloch | PLANNED | 2018-03-15 | 2015-10-14 | WIND | WT | 160 | 2018 | TRUE
15INR0082 | FTWIND (Flat Top Wind I) | Comanche | PLANNED | 2018-03-31 | 2016-02-19 | WIND | WT | 200 | 2018 | TRUE
16INR0086 | Cactus Flats Wind | Concho | PLANNED | 2018-07-02 | 2017-03-15 | WIND | WT | 150 | 2018 | TRUE
16INR0062b | Lockett Wind | Wilbarger | PLANNED | 2018-09-01 | 2015-03-31 | WIND | WT | 184 | 2018 | TRUE
11INR0062 | Patriot Wind | Nueces | PLANNED | 2018-09-27 | 2016-10-13 | WIND | WT | 180 | 2018 | TRUE
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2018-09-29 | 2016-05-20 | WIND | WT | 210 | 2018 | FALSE
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-09-30 | 2013-01-31 | WIND | WT | 152 | 2018 | TRUE
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2018-10-01 | 2014-10-03 | WIND | WT | 203 | 2018 | FALSE
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2018-10-15 | 2016-08-09 | WIND | WT | 500 | 2018 | FALSE
13INR0038 | Swisher Wind | Swisher | PLANNED | 2018-10-30 | 2015-09-06 | WIND | WT | 300 | 2018 | TRUE
18INR0025 | Tahoka Wind | Lynn | PLANNED | 2018-10-31 | 2017-07-19 | WIND | WT | 505 | 2018 | FALSE
16INR0074 | Chocolate Bayou W | Brazoria | PLANNED | 2018-11-30 | 2016-08-05 | WIND | WT | 150 | 2018 | FALSE
12INR0060 | Infinity Live Oak Wind | Schleicher | PLANNED | 2018-12-01 | 2016-11-03 | WIND | WT | 201 | 2018 | TRUE
14INR0023b | Longhorn South W | Briscoe | PLANNED | 2018-12-01 | 2012-12-10 | WIND | WT | 160 | 2018 | TRUE
16INR0121 | Salt Fork Wind Expansion | Carson | PLANNED | 2018-12-01 | 2016-06-28 | WIND | WT | 54 | 2018 | FALSE
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2018-12-23 | 2016-02-26 | WIND | WT | 281 | 2018 | TRUE
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2018-12-30 | 2014-08-25 | WIND | WT | 248 | 2018 | TRUE
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 218 | 2018 | TRUE
13INR0045 | Changing Winds | Castro | PLANNED | 2018-12-31 | 2015-02-27 | WIND | WT | 288 | 2018 | FALSE
17INR0005 | Rio Bravo I Wind | Starr | PLANNED | 2018-12-31 | 2017-08-03 | WIND | WT | 238 | 2018 | FALSE
11INR0054 | Midway Wind | San Patricio | PLANNED | 2019-03-01 | 2012-09-24 | WIND | WT | 161 | 2019 | TRUE
15INR0064b | BearKat Wind B | Glasscock | PLANNED | 2019-04-15 | 2016-12-20 | WIND | WT | 163 | 2019 | TRUE
17INR0027b | Coyote Wind | Scurry | PLANNED | 2019-09-30 | 2016-08-09 | WIND | WT | 250 | 2019 | TRUE
15INR0079 | Pullman Road Wind | Randall | PLANNED | 2019-10-31 | 2014-05-29 | WIND | WT | 300 | 2019 | FALSE
13INR0005c | Grandview W 3 | Carson | PLANNED | 2019-12-15 | 2014-04-23 | WIND | WT | 188 | 2019 | TRUE
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2019-12-31 | 2013-07-24 | WIND | WT | 500 | 2019 | FALSE
14INR0045a | Torrecillas Wind A | Webb | PLANNED | 2019-12-31 | 2015-01-30 | WIND | WT | 200 | 2019 | TRUE
14INR0045b | Torrecillas Wind B | Webb | PLANNED | 2019-12-31 | 2015-01-30 | WIND | WT | 200 | 2019 | TRUE
15INR0035 | Stella 1 Wind | Kenedy | PLANNED | 2020-06-01 | 2017-08-02 | WIND | WT | 201 | 2020 | FALSE
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2020-08-15 | 2014-04-25 | WIND | WT | 600 | 2020 | FALSE

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
15INR0061 | LASSO (SolaireHolman 1) | Brewster | PLANNED | 2017-09-01 | 2015-11-10 | SOLAR | PV | 50 | 2017 | TRUE
16INR0023 | LMESASLR (BNB Lamesa Solar 1) | Dawson | PLANNED | 2017-09-01 | 2016-07-28 | SOLAR | PV | 102 | 2017 | TRUE
15INR0070_1b | SIRIUS_UNIT2 (Pearl Solar) | Pecos | PLANNED | 2017-09-15 | 2014-12-17 | SOLAR | PV | 50 | 2017 | TRUE
12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | PLANNED | 2017-09-22 | 2013-12-26 | SOLAR | PV | 7 | 2017 | TRUE
15INR0045 | RIGGINS | Pecos | PLANNED | 2018-02-23 | 2015-01-26 | SOLAR | PV | 150 | 2018 | TRUE
16INR0065 | CASL_GAP (Castle Gap Solar) | Upton | PLANNED | 2018-06-01 | 2015-09-04 | SOLAR | PV | 180 | 2018 | TRUE
14INR0044 | West of Pecos Solar | Reeves | PLANNED | 2018-07-01 | 2017-02-27 | SOLAR | PV | 100 | 2018 | TRUE
16INR0019 | Capricorn Ridge Solar | Coke | PLANNED | 2018-12-01 | 2015-08-19 | SOLAR | PV | 100 | 2018 | FALSE
16INR0114 | Upton Solar | Upton | PLANNED | 2018-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2018 | TRUE
15INR0090 | Pflugerville Solar | Travis | PLANNED | 2018-12-31 | 2017-06-13 | SOLAR | PV | 120 | 2018 | FALSE
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2018-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2018 | TRUE
15INR0059 | Pecos Solar I | Pecos | PLANNED | 2019-01-01 | 2015-06-09 | SOLAR | PV | 108 | 2019 | TRUE
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2019-03-31 | 2015-06-25 | SOLAR | PV | 98 | 2019 | FALSE
16INR0049 | Nazareth Solar | Castro | PLANNED | 2019-10-01 | 2015-05-15 | SOLAR | PV | 201 | 2019 | FALSE
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE
17INR0020e | RE Maplewood 2e Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE