## Sheet1
TX SET Meeting Notes / Action Items
2017-08-16
Agenda Item: | Decision / Resolution | Action Items :
June 2017 Meeting Notes | Minor changes werer made to the notes. | The Texas SET Chair will have the notes posted to the June meeting page key documents.
Retail Market Subcommittee (RMS) Updates
149RMGRR-01 Clarification to Market Processes for ESI IDs Without a REP of Record 062217 & Impact Analysis | RMS approved RMGRR and the related impact analysis.
Flight Update | The ERCOT Flight Administrator provided an update of the upcoming October Flight.
MOU01 Script Updated The Day 6 MVO should be for Day 5 | The Texas SET Chair and the ERCOT Flight Administrator provided a brief explanation of the changes. Texas SET membership was in agreement to those changes.
2018 Market Flight Test Flight Schedule Review (Possible Consensus) | Texas SET reviewed the proposed schedule and made corrections to some of the dates. | The ERCOT Flight Administrator will update the corrections and post a copy to the meeting page. The proposed Flight Schedule will be presented and approval requested at the next RMS meeting.
Change Control Call--10:00 AM | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
ChangeControl2017_807_New--Updates the language in the CW1 Reject Reason code for 814_09 and 814_12 to support NPRR778, Modifications to Date Change and Cancellation Evaluation Window. | ERCOT Staff conducted the Change Control call. Texas SET membership supportedt the changes and will recommend that the Change Control be approved as a Future dated change at the next RMS meeting. | ERCOT will post the updated Change Cointrol to the ERCOT Website and present the Change Control at the next RMS meeting.
Discussion Items
Change Control Process Language Update—Add process for determining versions. | 1. The Texas SET Chair conducted a final review of the updated Texas SET Working Group Procedures and the Texas SET Implementation Guides Change Control Process documents. 2. Minor changes were made. | 1. The Texas SET Chair will send both documents to ERCOT Market Rules for clean up; then ERCOT Market Rules will include the documents in the next RMS meeting voting items. 2. The Texas SET Chair will present the changes and make the recommendation to have RMS approve the changes.
820_02 Bank Remarks section NTE*ZZZ*--Discuss need to update Implementation Guide and Examples.--Research update from NRG and CNP | 1. CNP provided an update stating that another example needs to be added to the current 820_02 examples. 2. Texas SET membership agreed. | CNP will provide the example for Texas SET review at the September meeting.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
Texas SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
RMS assignments:
NPRR839, Clarification of ERCOT Forwarding of Consumption and Other Data--Review with Recommendation to RMS | 1. The Texas SET Chair conducted a review of the language in the NPRR and the associated Impact Analysis. 2. Texas SET membership reached consensus to make a recommendation to RMS to endorse the NPRR and the associated Impact Analysis at the next RMS meeting. | The Texas SET Chair will present the recommendation at the September RMS meeting.
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Review combined documents | Texas SET membership conducted a final review of the changes to the Retail Market Guide and reached consensus to have ERCOT Market Rules clean up the document to send to the PUCT for their review. | 1. ERCOT Market Rules will clean up the document and send to Texas SET and RMS leadership. 2. The RMS Chair will send the document to the PUCT for their review. 3. If the PUCT feedback contains no issues with the language changes, the RMGRR will be submitted to RMS for approval.
Market Testing NPRR778, Modifications to Date Change / Cancellation Evaluation Window--Script Review / Joint TDTMS Logistics Review | 1. The Texas SET Chair conducted a review of the draft test scripts provided at the meeting. 2. Texas SET membership agreed that two basic scripts would be needed to test the change to allow Cancels and Date Changes the day prior to a scheduled request. 3. Two Scripts were created. • DayPrior_001, MVI Cancel, Switch Cancel and MVI Date Change All on the Day prior to the Scheduled Request • DayPrior_002, Move Out - With Date Change and Cancel 1 day prior to Scheduled Date 4. Texas SET membership agreed that regression testing for the "Day of" and a "Date in the Past" scenarios can be conducted outside of the organized effort to test the two scripts created or the “Day Prior” scenarios. 5. The Texas Data Transport and MarkeTrak Systems (TDTMS) Working Group leadership will discuss testing logistics (workshops, conference calls, testing signup, etc.) beginning at their August 17, 2017 meeting. | 1. The Texas SET Chair will send the test scripts to the Texas SET and Texas Data Transport and MarkeTrak Systems (TDTMS) email distribution list. 2. Review of any comments received will be addressed at the September Texas SET meeting.
Discuss CNP’s Process for Charges Applied to Multiple Unmetered Services on the 810_02 TX SET | CNP stated that they are still working to get examples from their system and that they will give an update at the September RMS meeting. | CNP will provide updated examples as those become available to the CRs wishing to test the changes in their systems.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | September 19, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Sam Pak ONCOR | Rebecca Zerwas NRG
Becky Taylor CNP | Kathy Scott CNP
Kaci Jacobs TXU | Carolyn Reed CNP
Lindsay Butterfield ERCOT | Norman Levine DE
Kyle Patrick NRG | Monsherra Blank ONCOR
Samantha Marin Verde Energy | Jim Lee AEP
Attendees Webex
Barbara Goubeaud ECInfoSystems | Teresa Rodriquez Stream Energy
Eric Blakey Just Energy | Crystal Luna Stream Energy
Kathryn Thurman ERCOT | Paula Hines ESG
Deb Belin Aurea | Jasmine Stevenson ECInfoSystems
Kim Wall Hensen Technologies | Laura Aldis APGE
Paul Yockey ERCOT | Mark Ruane ERCOT
pwb