## CON01
Script ID | CON01 |  | Power Point
Script Name | ERCOT and TDSP Test Bed Load
Script Storyline | TDSP sends Test Bed Load to ERCOT. ERCOT successfully receives and sets up.
Success Criteria | Test Bed set up successfully
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
Operating Rule |  |  | TRACK | Connectivity
Simulated Entity
Duns Number
Number of CR's
| ERCOT | TDSP
PreTest Setup
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Pre-Day 1 | ERCOT | TDSP | email | Relationship Matrix | ERCOT sends TDSP the final testing Relationship Matrix.
Pre-Day 1 | TDSP | CR | email | ESI ID Spreadsheet | TDSP emails ESI ID spreadsheet to primary and secondary contacts.
Pre-Day 1 | TDSP | ERCOT | email | ESI ID List | TDSP emails ESI ID spreadsheet to ERCOT flight testing team.
Pre-Day 1 | TDSP | ERCOT | 814_20 | Create ESI ID | TDSP transmits 814_20 Create ESI ID transactions to ERCOT BY THE DATE SPECIFIED IN THE PUBLISHED FLIGHT CALENDAR. No 814_21 or 997 transactions are returned.

## CON05
Script ID | CON05 |  | Power Point
Script Name | NAESB connectivity with ERCOT and CR
Script Storyline | Test NAESB connectivity; successful exchange of standard X12-encrypted handshake files. Note: the 814_01 sent by the CR is sent with an incorrect value in the REF*SU segment of the transaction in order to force it to automatically create an outbound 814_02 in ERCOT's system.
Success Criteria | CR and ERCOT successfully send and receive encrypted files.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
Operating Rule |  |  | TRACK | Connectivity
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | CR
PreTest Setup
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Pre-Day 1 | ERCOT | CR | email | Encryption Keys | ERCOT emails encryption keys along with username and password to CR and schedules connectivity testing
Pre-Day 1 | CR | ERCOT | email | Encryption Keys | CR emails encryption keys along with username and password to ERCOT and schedules connectivity testing
Pre-Day 1 | CR | ERCOT | 814_01 | encrypted file | CR sends an encrypted X12 formatted 814_01 file containing an ESI ID of "CONNECTIVITYTESTESIID" and a "REF*SU*I". CR emails ERCOT results of successful posting from their NAESB log.
Pre-Day 1 | ERCOT | CR | 814_02 | Encrypted file | ERCOT sends an encrypted X12 formatted 814_02 containing an ESI ID of "CONNECTIVITYTESTESIID". ERCOT emails CR successful NAESB response message

## DayPrior_001
Script ID | DayPrior_001 |  | Power Point
Script Name | MVI Cancel, Switch Cancel and MVI Date Change All on the Day prior to the Scheduled Request
Script Storyline | TDSP assigns testing CR ESIID(s) for which they are non REP of Record. On Day 1 • CR submits a Move-In Request for Day 2. ERCOT forwards the request to the TDSP and the TDSP schedules the Move-In Request. • CR submits a Move-In Cancel Request. ERCOT forwards the Cancel Request to the TDSP and the TDSP cancels the move in. • CR submits a Switch Request for Day 2. ERCOT forwards the Switch for Day 2. • CR submits a Switch Cancel Request. ERCOT forwards the Cancel Request to the TDSP and the TDSP cancels the Switch. • CR submits a Move-In Request for Day 3. ERCOT forwards the Move-In Request to the TDSP and the TDSP schedules the Move-In Request for Day 3 On Day 2 CR submits a Move-In Date Change Request to move the Day 3 Move-In Request to Day 4. ERCOT forwards the Date Change Request to the TDSP and the TDSP schedules the move in for Day 4. On Day 4 the Move-In effectuates and the Initial Read is sent to the CR.
Success Criteria | TDSPs with either Standard or Non-standard meter A move in is scheduled and cancelled the day prior; a switch is scheduled and cancelled the day prior; and a move-in is scheduled and the date changed on the day prior.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778RMGRR139
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_16 | RMRD = Day 2 (DTM~375) | MVI requested for Day 2 | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 2 (DTM~375) | MVI requested for Day 2 | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 2 | MVI scheduled for Day 2 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 2 | MVI scheduled for Day 2 | 1 |  |  | CR1
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested
| ERCOT | TDSP | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVI Cancel requested
| TDSP | ERCOT | 814_09 | ASI~WQ~024 | MVI Cancelled
| ERCOT | CR1 | 814_09 | ASI~WQ~024 | MVI Cancelled
| CR1 | ERCOT | 814_01 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~Day 2 | SW | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE~SH~SW DTM~MMR~Day 2 | SW requested for Day 2 | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 2 | SW scheduled for Day 2 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 2 | SW scheduled for Day 2 | 1 |  |  | CR1
| CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested | 1
| ERCOT | TDSP | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | SW Cancel requested | 1
| TDSP | ERCOT | 814_09 | ASI~WQ~024 | SW Cancelled | 1
| ERCOT | CR1 | 814_09 | ASI~WQ~024 | SW Cancelled | 1
| CR1 | ERCOT | 814_16 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 | 1 |  |  | CR1
| ERCOT | TDSP | 814_03 | RMRD = Day 3 (DTM~375) | MVI requested for Day 3 | 1 |  |  | CR1
| TDSP | ERCOT | 814_04 | SMRD = Day 3 | MVI requested for Day 3 | 1 |  |  | CR1
| ERCOT | CR1 | 814_05 | SMRD = Day 3 | MVI requested for Day 3 | 1 |  |  | CR1
Day 02 | CR1 | ERCOT | 814_12 | RMRD = Day 4 (DTM~375) | MVI Date Change requested | 1
| ERCOT | TDSP | 814_12 | RMRD = Day 4 (DTM~375) | MVI Date Change requested | 1
| TDSP | ERCOT | 814_13 | SMRD = Day 4 | MVI Scheduled for Day 4 | 1
| ERCOT | CR1 | 814_13 | SMRD = Day 4 | MVI Scheduled for Day 4 | 1
Day 03
Day 04 |  |  |  |  | Move-In Effectuates | 1 | MVI |  | CR1
Day 05 | TDSP | ERCOT | 867_04 | BPT01 = SU | Initial Read for Customer A | 1 |  |  | CR1
| ERCOT | CR1 | 867_04 | BPT01 = SU | ERCOT forwards 867_04 to CR1 | 1 |  |  | CR1

## DayPrior_002
Script ID | DayPrior_002 |  | Power Point
Script Name | Move Out - With Date Change and Cancel 1 day prior to Scheduled Date
Script Storyline | TDSP assigns testing CR ESIID(s) for which they are the REP of Record. On Day 1 the CR submits a Move-Out Request for Day 3. ERCOT forwards the Move-Out Request to the TDSP and the TDSP schedules the Move-Out Request. On Day 2 the CR submits a Move-Out Date Change Request for the Move Out scheduled for Day 4. ERCOT forwards the Move-Out Date Change Request to the TDSP and the TDSP changes Move-Out Request to Day 4. On Day 3 the CR submits a Move-Out Cancel Request for the scheduled Move-Out. ERCOT forwards the Move-Out Cancel Request to the TDSP and the TDSP cancels the Move-Out Request.
Success Criteria | TDSPs with either Standard or Non-standard meter A move out is scheduled; the date is changed one day prior; then the move out is cancelled one day prior.
Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
| Residential | Standard or Non-Standard | None |  | No
Operating Rule |  |  | TRACK | NPRR778MGRR139
Simulated Entity
Duns Number
Number of CR's | 1
| ERCOT | TDSP | CR1
Pretest Setup | None | None | None
Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01 | CR1 | ERCOT | 814_24 | RMRD - Day 3 (DTM~376) | MVO | 1 |  |  | CR1
| ERCOT | TDSP | 814_24 | RMRD - Day 3 (DTM~376) | MVO | 1 |  |  | CR1
| TDSP | ERCOT | 814_25 | SMRD = Day 3 | MVO | 1 |  |  | CR1
| ERCOT | CR1 | 814_25 | SMRD = Day 3 | MVO | 1 |  |  | CR1
Day 02 | CR1 | ERCOT | 814_12 | RMRD = Day 4 (DTM~376) | MVO Date Change requested | 1
| ERCOT | TDSP | 814_12 | RMRD = Day 4 (DTM~376) | MVO Date Change requested | 1
| TDSP | ERCOT | 814_13 | SMRD = Day 4 | MVO Scheduled for Day 4 | 1
| ERCOT | CR1 | 814_13 | SMRD = Day 4 | MVO Scheduled for Day 4 | 1
Day 03 | CR1 | ERCOT | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 1
| ERCOT | TDSP | 814_08 | REF~1P~B40~CANCELLED BY CUSTOMER REQUEST | MVO Cancel requested for Customer A | 1
| TDSP | ERCOT | 814_09 | ASI~WQ~024 | MVO Cancelled | 1
| ERCOT | CR1 | 814_09 | ASI~WQ~024 | MVO Cancelled | 1