## Slide 1
PR181-01 CRR Framework Upgrade
Project Update for Congestion Management Working Group (CMWG)
October 9, 2017

## Slide 2: Agenda
High Level Timeline
Recent Market Communications
Requalification Status Update
Questions/Open Discussion

## Slide 3: High Level Timeline
DEC 8, 2017 – Market requalification period ends
  Any CRR Account Holders or Counter-Parties that have not completed requalification will need to communicate their intentions to ERCOT
  Cannot guarantee there will be enough time to get them qualified prior to implementing the new MUI
DEC 8, 2017 – Last day to qualify on current MUI
  Any new CRR Account Holders or Counter-Parties will only be qualified on the new MUI after this date and can start participating in auctions held after the MUI implementation
JAN 22, 2018 – MUI implementation go-live
  Any CRR Account Holders or Counter-Parties that have not completed requalification will not be able to participate in any auctions after this date, until a qualification test is passed
NOV/DEC 2017 – Reminder for PCRR-eligible NOIEs
  NPRR808, Three Year CRR Auction, requires off-cycle allocation
  2020 annual allocation will be completed using the current MUI

## Slide 4: Recent Market Communications
SEP 19, 2017 – Reminder Market Notice for the scheduled WebEx sessions (September 20 and 28)
  Another reminder to test MOTE digital certificates
  Attached to MUI Operator Message
SEP 27, 2017 – Reminder Market Notice for the second scheduled WebEx session (September 28)
  Another reminder to test MOTE digital certificates
  Attached to MUI Operator Message
OCT 6, 2017 – Reminder Market Notice for the available online MUI training course
  Attached to MUI Operator Message

## Slide 5: Requalification Status
WebEx sessions
  Session 1 on SEP 20 had ~35 attendees
  Session 2 on SEP 28 had ~75 attendees
As of OCT 6
  59 CRR Account holders have requalified (~230 registered CRR Account Holders); that’s only 26%
MOTE digital certificates
  We still have ~35% of CRR Account Holders and ~40% of Counter-Parties that DO NOT have an active MOTE digital certificate

## Slide 6: Questions/Open Discussion
REMINDER: In order to participate in CRR Auctions after the January 2018 implementation of the upgraded MUI, CRR Account Holders and their Counter-Parties must pass a requalification test.