## Slide 1: Planning Transmission Outages
AEP Presentation to the
Congestion Management Working Group
October 9, 2017

## Slide 2: Nodal Protocols Section 3: Management Activities for the ERCOT System
3.1 Outage Coordination
“Outage Coordination” is the management of Transmission Facilities Outages and Resource Outages in the ERCOT System. Facility owners are solely and directly responsible for the performance of all maintenance, repair, and construction work, whether on energized or de-energized facilities, including all activities related to providing a safe working environment.
3.1.1 Role of ERCOT
ERCOT shall coordinate and use reasonable efforts, consistent with Good Utility Practice, to accept, approve or reject all Outage schedules for maintenance, repair, and construction of both Transmission Facilities and Resources within the ERCOT System. ERCOT may reject an Outage schedule under certain circumstances, as set forth in these Protocols.
3.1.3.1 Transmission Facilities
(1) Each TSP shall provide to ERCOT a Planned Outage or Maintenance Outage plan in an ERCOT-provided format for the next 12 months updated monthly. Planned Outage or Maintenance reviews of the 12-month plan with each TSP at least twice per year.

## Slide 3: TSP Outage Planning
Planning horizon is 6-9 months out
  Weather, materials, etc. can impact
  Impractical to look too far out due to significant uncertainty
Rolling 12-month running outage plan and updates
When ERCOT recognizes a High Impact Outage they contact the TSP
Actions are taken by TSPs and ERCOT to mitigate impact to Market

## Slide 4: TSP Outage Planning
Extended Outage Considerations:
  Resource availability and weather
  Landowner Impacts: harvest, hunting
  Community relations and local government needs
  Regulatory compliance
  Impact to Generators
  Safety and Risk Mitigation
  Financial impacts
  Material and equipment delivery

## Slide 5: ERCOT Outage Planning
What has been received can be seen in OS
What has been received will be considered for scheduling when < 90 days and > 75 days
Outages are not considered for inclusion in CRR models until approved however, OS can help CRR account holders anticipate value of CRR based on OS submissions
ERCOT has no Protocol support to consider economic impact of outages
ERCOT does not have the tool or FTEs to perform economic analysis task

## Slide 6: Other Considerations
NPRR758, Improved Transparency for Outages Potentially having a High Economic Impact (Rescheduled Outages)
  ERCOT completed implementation of changes to the Outage Scheduler for the remaining grey-boxed portions in September.
  NPRR758 supports identification of Outages that have historically resulted in high congestion costs, as adjusted through a stakeholder review process to account for upgrades and other changes that would affect the fidelity of this list as an indicator of Outages that might cause future congestion; and includes identification and posting of High Impact Transmission Elements (HITEs) and High Impact Outages (HIOs) and a Rescheduled Outage type.

## Slide 7: Other Considerations
Inability to predict load 90 days out with great deal of accuracy
Reliability impacts to deferring reliability based outage projects
More qualitative information on outages in rolling 12-month outage plan
Protocol Revisions

## Slide 8: Next Steps…
Continue discussions with Outage Coordination Working Group
  Scope Change for OCWG