## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
November 9, 2017

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
  2017 Release Targets
  2018 Release Targets
  2017 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Appendix
  Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2017 August Release – 9/11/2017-9/13/2017 Complete
  NPRR758 – Improved Transparency for Outages Potentially Having a High Econ Impact
  NPRR775 – Enhanced Implementation of Limits for Fast Responding Regulation Service
2017 October Release – 10/31/2017-11/2/2017 In Flight
  NPRR782 – Settlement of Infeasible A/S Due to Transmission Constraints
  NPRR831(a) – Inclusion of Private Use Networks in Load Zone Price Calculations
    All impacted systems except CRR
2017 December Release – 12/5/2017-12/7/2017 In Flight
  NPRR812 – Alignment of Currently Published Reports
2017 December Retail Release – 12/9/2017-12/10/2017 In Flight
  NPRR778 – Modifications to Date Change and Cancellation Evaluation Window
  RMGRR139 – Alignment with NPRR778, Modifications to Date Change and Cancellation Evaluation Window
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/1 – 5/11 | June 6/27 – 6/29 | August 9/11 – 9/13 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR753 NPRR764 NPRR785 RMGRR134 NPRR790 | SCR790 NPRR746 NPRR786 NPRR792 NOGRR164 PGRR051 RRGRR003 RRGRR006 RRGRR007 RRGRR009 RRGRR010 PGRR046 | NPRR573 NPRR789 NPRR797 NPRR801 NPRR827 NPRR744 | NPRR758 NPRR775 NPRR809(a) PGRR052 PGRR054 | NPRR778 NPRR782 NPRR831(a) NPRR562(a) NPRR808 PGRR056 | NPRR810 NPRR812 NPRR778 RMGRR139
7 | 12 | 6 | 5 | 5 | 3
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NPRR664 | None | SCR781 P | NPRR702 P, NPRR519, NPRR620, NPRR741, NPRR755, SCR789
12/9 – 12/10 (Retail)
5/8 – NMMS Upgrade
6/1
9/1 & 9/14
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
ü
ü
ü
E
E
E
8/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NPRR562(a) – Procedural changes
NPRR809(a) – Procedural changes
NPRR831(a) – All impacted systems except CRR

## Slide 5: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/6 – 2/8 | April 4/3 – 4/5 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/23 – 10/25 | December 12/11 – 12/13
NPRR562(b) NPRR776 NPRR830 NPRR683 NPRR743 NPRR760 NPRR800 NPRR810 NPRR833 SCR777 NPRR831(b) | SCR792 NPRR749 NPRR833 | NPRR749 NPRR809(b) |  |  | PGRR057 SCR789
10 | 3 | 1 | 0 | 0 | 2
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
E
I
Dates TBD
(Retail)
NS
E
P
E
E
E
E
E
E
E
Dates TBD
(Retail)
CMM Release 1a
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
January
(Off-cycle)
P
NPRR562(b) – Reporting/posting system changes
NPRR809(b) – Reporting/posting system changes
NPRR831(b) – CRR system changes
NS
NS
P

## Slide 6: 2017 Project Spending
2017 PPL Budget = $21.5M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2017 and 2018, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2017 | 2018
YTD Actuals | $2.31M | $0.00M
Approved – In-Flight / Complete | $3.02M | $1.48M
Approved – On Hold | $0.00M | $0.00M
Approved – Not Started | $0.02M | $0.09M
Remaining Funding | $0.96M | $2.43M
Total Allocation | $4.00M | $4.00M
As of 9/30/2017

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR843 | Short-Term System Adequacy and AS Offer Disclosure Reports Additions | 2018 | 170 | REGULATORY Creates new reporting requirements to satisfy posting obligations under P.U.C. Subst. R. 25.505 Plan to start project in early 2018
Options for…
PPL Rank Information
Next available Rank in Business Strategy = 2110
Next available Rank in Regulatory = 170

## Slide 9
Appendix
  10/31/2017 Project Gantt
    In-flight items sorted by Project End Date
    “On Hold” projects listed separately
      None at this time
    “Not Started” items sorted by Project Start Date

## Slide 10: Project Portfolio Status – as of 10/31/2017

## Slide 11: Project Portfolio Status – as of 10/31/2017

## Slide 12: Project Portfolio Status – as of 10/31/2017

## Slide 13: Project Portfolio Status – as of 10/31/2017

## Slide 14: Project Portfolio Status – as of 10/31/2017

## Slide 15: Project Portfolio Status – as of 10/31/2017

## Slide 16: Project Portfolio Status – as of 10/31/2017