## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to the ROS
November 2, 2017
Omar Urquidez
PGDTF Chairman
<number>
11/2/2017 ROS Meeting

## Slide 2: Activities of the PGDTF – Sept/Oct
PGDTF Business Meetings on Sept. 28th & Oct. 25th (Open)
  Provided Vulnerability Assessment Scope & Process Recommendation
  Drafting PGRR language for TPL-007-1 Requirement 3-Criteria
  Updated GIC System Model Procedure Manual, bringing to ROS in December
  Next Business Meeting is Nov. 17th
GIC System Model Building Face to Face Meeting – Sept. 29th (TSP Only)
  Completed First ERCOT GIC Model including first look at GIC Flows, cases and GIC values posted on MIS
  SSWG 2021 Summer Peak and 2021 MIN Released July 2017 will be used in GIC System Model building
  Created TSP only Restricted-PGDTF@lists.ercot.com for confidential communication and investigating encrypted transfer for submissions
  Finalized GIC System Model Building Schedule
  Next Model Face to Face Meeting is Nov. 16th
<number>
11/2/2017 ROS Meeting

## Slide 3: Final GIC System Model Timeline
TSP Resubmission Deadline – October 20th
First Pass Release RAW & GIC Files – November 10th
First Pass GIC/VAR Values – November 13th
GIC Model Review Face to Face Meeting – November 16th
First Pass TSP Update Deadline – December 1st
Second Pass Release RAW & GIC Files – December 21st
Second Pass GIC/VAR Values – December 22nd
GIC Model Review Face to Face Meeting – January 12th
Second Pass TSP Update Deadline – January 19th
Third Pass Release RAW & GIC Files – January 28th
Third Pass GIC/VAR Values – January 29th
GIC Model Review Face to Face Meeting – February 16th
Final Pass Release RAW & GIC Files – March 1st
Final Pass GIC/VAR Values – March 1st
<number>
11/2/2017 ROS Meeting

## Slide 4: Questions and Answers
<number>
11/2/2017 ROS Meeting