## Sheet1
ERCOT SPWG Action Item Tracking
Rev: 7/21/2016
Item # | Item Date | Action Item Description | Responsible Party | Status | Target Date | Completion Date
1 | 2015-11-13 | Send out Case Building Guide Version 1.8 for approval | Brian Clowe | Completed | 2015-12-31
2 | 2015-11-13 | Find out what Short Circuit modeling programs ERCOT memebers are using | Jay Teixeira | Completed | 2016-03-17
3 | 2015-11-13 | Draft revision of ERCOT Guide Section 6 to accommodate PRC-002-2 for review at March meeting | Bret Burford | Completed | 2016-03-17
4 | 2016-03-17 | Post Case Building Guide Version 1.8 to ERCOT Website | Bret Burford | Completed | 2016-03-31 | 2016-05-05
8 | 2016-03-18 | Case Building Guide revisions for Version 1.9. Renewable wind resource modeling. | Jon Snellgrove / Samantha Indalecio | In-Progress | 2017-11-01
9 | 2016-03-18 | Ercot Guide Section 2.9 Revisions for PRC-024 for UV ride-through of Generators. Monitor the PDC working group. | Brian Clowe/Bret Burford/David Penney | Open | 2017-11-01
11 | 2016-03-18 | ERCOT Guide Revisions for PRC-019 (coordination of protection with excitation controls). Monitor the PDC working group. | David Penney | Open | 2017-11-01
15 | 2016-07-22 | Voltage controlled Current Source Group. Add representatives from AEP and Oncor. | Lead: Michael Davis, James Wang, , Dung Nguyen, Mike Duff, AEP (Nicholas Ritchie), Oncor (Kayla ?) | In-Progress | Pending
17 | 2016-11-18 | Section 6 consensus to be reached prior to March 2017 meeting. Send to NOGR with SPWG as a sponsor and Bret Burford as primary contact. | Bret Burford | Complete | 2017-03-10 | 2017-03-14
18 | 2016-11-18 | Schedule a combined ERCOT / SPP SPWG meeting | Bret Burford/Mark Henry | Pending
19 | 2016-11-18 | Submit revised SPWG Procedures to ROS for approval; RAS Definition. SPWG members to review revised document for 11/2017 meeting. Need to send out revised document to all. | Bret Burford | Open | 2017-11-01
20 | 2016-11-18 | Submit new Chair/Vice Chair to ROS for approval | Dung Nguyen | On-Going | 2017-11-09
21 | 2017-07-12 | Discrepancies in Short Circuit Case Bus Names vs. SSWG Cases. Submit changes for 2018 base case. | All members |  | 2017-12-01