## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 10/5/2017 and 10/19/2017
Agenda Item: | Decision / Resolution | Action Items :
September 2017 Meeting Notes | No changes were made to the notes. | The Texas SET Chair will have these posted to the September meeting page key documents.
Retail Market Subcommittee (RMS) Updates
o Pending Vote at October 2017 RMS Meeting • Change Control 2017_807,Updates the language in the CW1 Reject Reason code for 814_09 and 814_12 to support NPRR778, Modifications to Date Change and Cancellation Evaluation Window • 2018 Market Flight Test Flight Schedule • Texas SET Working Group Procedures • Texas SET Implementation Guides Change Control Process • NPRR839, Clarification of ERCOT Forwarding of Consumption and Other Data and Impact Analysis | RMS approved or endorsed all items presented.
Flight Update
Flight 1017 update | ERCOT Staff presented the flight update and stated that they will post the 2018 Flight Schedule to the ERCOT website.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Discussion Items | No new items.
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
RMS assignments:
RMGRR132, NOIE Disconnect and Reconnect Process and related Draft NPRR—Language Review and Recommendatino to RMS | 1. Texas SET conducted a discussion related to the proposed changes to the RMGRR132 and related proposed NPRR language and made some minor changes. 2. Texas SET and the submitter (Golden Spread Electric Coop) determined that the language should be further reviewed by the Operations Working Group (OWG). | The Texas SET Chair will send the updated documents to Golden Spread Electric Coop.
NPRR850, Market Suspension and Restart—Language Review and recommendation to RMS | Texas SET conducted a discussion on the language and proposed some minor changes. | The Texas SET Chair will send the updated document to ERCOT Market Rules to create a Texas SET comments document for the recommendation to RMS.
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Update on Draft RMGRR Progress-- 10/5/2017 Review PUCT Staff Feedback 10/19/2017 Review and recommendation to RMS. | 1. October 5, 2017 Conference call: Texas SET discussed the feedback from the PUCT Staff and determined that each Market Participant will review internally to provide feedback on how to proceed at the October 19, 2017 Texas SET meeting. 2. October 19, 2017 Meeting: Texas SET continued the discussion on the feedback received from the PUCT Staff and, based on the feedback from Market Participants, determined that the RMGRR will be put on hold until the PUCT Staff opens the rule for review next year and determines if changes need to be made. Texas SET will revisit the RMGRR language at that time.
Market Testing NPRR778, Modifications to Date Change / Cancellation Evaluation Window-- Joint Texas SET / TDTMS Review of RMS feedback | 1. TDTMS conducted a workshop to discuss testing logistics prior to the Texas SET meeting. 2. Texas SET reviewed the scripts and made updates as suggested in the TDTMS NPRR778 workshop. | The Texas SET Chair will send the updated scripts to the Texas SET email distribution list.
Discuss CNP’s Process for Charges Applied to Multiple Unmetered Services on the 810_02 TX SET--Example update | An update will be given at a future meeting.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | November 14, 2017 RM 168
Attendees F-T-F-NPRR778 WS and Texas SET Meeting
Diana Rehfeldt TNMP | Monica Jones NRG
Lindsay Butterfield ERCOT | Sam Pak ONCOR
Debbie McKeever ONCOR | Taylor Woodruff ONCOR
Kathy Scott CNP | Tom Burke GSEC
John Schatz TXU
Jim Lee AEP
Kyle Patrick NRG
Rebecca Zerwas NRG
Carolyn Reed CNP
Martin Allen ONCOR
Attendees Webex--NPRR778 WS and Texas SET Meeting
Aaron Tobias | Noah Weidman Direct Energy | Brittney Taylor
Alberto Herrera | Cindy Duong Just Energy | Candice Keller
Becky Taylor CNP | Crystal Luna Stream | Carolyn Barger NEC
Deb Belin MarketWise | Dave Michelsen ERCOT | Cory Phillips (ERCOT)
Gustavo Rodriquez Champion | Douglas Fohn | Doug Summerville Zoom Energy
Kathryn Thurman ERCOT | Eileen Weaver ERCOT | Eric Blakey - Just Energy
Kelly Tidwell | Jasmine Acosta CES | Janie Escalante Summer Energy
Kelly Yen | John Petkansus ECInforsystems | Judy Baily Big Data Energy
Kim Wall Hansen Technologies | Paul Williams EPSolutions | Juliana Morehead ERCOT
Laura Aldis | Stephen Wilson Sharyland Utilities | Liz Kayser PUCT
Matt Hansen | Tabitha Lochard Stream | Paula Shadle NEC COOP
Michael Glass (Sharyland Utilities) | Teresa Rodriquez Stream