|  |  |  |  | System Planning |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Monthly Status Report November 2017 |  |  |
|  |  | Report Highlights |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $542.5 Million. - Transmission Projects endorsed in 2017 total $643.3 Million. - All projects (in engineering, routing, licensing and construction) total approximately $7.07 Billion as of October 15, 2017. - Transmission Projects energized in 2017 total about $805.4 Million as of October 15, 2017. |  |  |  |  |  |

Regional Planning Group Project Reviews

- Sharyland Utilities has submitted the South Plains Transmission project. This is a Tier 1 project that is estimated to cost $251 million. ERCOT has issued an interim report on the independent review and determined that the project does not meet the ERCOT economic planning criteria based on the assumptions used in the study.  ERCOT will reevaluate the assumptions in 2018 and may perform a reassessment of the need for the project.

- Garland Power & Light and Oncor have jointly submitted the North Garland Reliability Infrastructure Project (N-GRIP). This is a Tier 1 project that is estimated to cost $78 million. The ERCOT independent review for this project is currently placed on hold per the request of GPL.

- CenterPoint Energy has submitted the Freeport Master Plan project. This is a Tier 1 project that is estimated to cost $246.7 million. ERCOT has completed the independent review, and the project will be presented to the Board of Director’s for endorsement in December.

- Brazos Electric Cooperative (BEC) & Rayburn Country Electric Cooperative (RCEC) have jointly submitted the Northeast Denton County & Celina/Prosper Transmission Improvement project. This is a Tier 1 project that is estimated to cost $72.9 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) has submitted the Kalgary Area Improvement project. This is a Tier 2 project that is estimated to cost $33 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) has submitted the South Denton County project. This is a Tier 2 project that is estimated to cost $42 million. This project is currently under ERCOT independent review.

- WETT has submitted the Bearkat Area Transmission Improvements project. This is a Tier 1 project that is estimated to cost $69.9 million. The ERCOT independent review for this project is currently placed on hold per the request of WETT.

- LCRA has submitted the Wirtz-Johnson City-Mountain Top 69 kV transmission line Overhaul project. This project was initially classified as a Tier 3 project that is estimated to cost $25.2 million. This project has completed the RPG review and has beeen re-classified as a Tier 4 Neutral project.

- TNMP has submitted the IH20 SVC project. This is a Tier 3 project that is estimated to cost $20 million. This project has completed the RPG review, and ERCOT will prepare the RPG acceptance letter.

# Planning Model Activities

The short term calendar of major planning model events is as follows:

- December 20, 2017	NMMS snapshot for 17SSWG Update 2

- March 1,  2018		Post 17SSWG Update 2 Base Cases

- March 31, 2017	P	Post Contingency definitions and Planning Data Dictionary

The following table shows interconnection projects that met Planning Guide section 6.9(1) and 6.9(2) and were modeled in the SSWG cases as either complete or as a simple model in accordance with Planning Guide section 6.9.  The 6.9(2) Deadline shown in red have received a notification that the 60 day deadline has past and the set of planning data has not been received.

# Permian Basin Oil Rig Count

# Other Notable Activities

- ERCOT has completed reliability and economic analysis for the 2017 Regional Transmission Plan (RTP).  and is currently working on finalizing the RTP report draft. ERCOT also shared the draft of scope and assumptions document for the 2018 RTP at the November RPG. Stakeholders are encouraged to provide feedback for the 2018 RTP study.

- ERCOT and over thirty members in attendance at the June RPG meeting participated in a scenario development workshop for the 2018 LTSA. This session was a follow-up of the LTSA scenario development workshop conducted at the May RPG meeting. In addition to the Current Trends scenario, three new scenarios were identified as a result of the workshop. ERCOT staff compiled the results of these workshops and presented the findings on scenario descriptions and assumptions that will be studied in the 2018 LTSA at the August RPG meeting.

- The SPWG has completed work on the 2017 FY base cases.  ERCOT sent the final pass out to the group on 06/30/2017.

+/- symbol indicates the increase or decrease from the previous month in oil rigs present in each county. There is a total increase of twelve oil rigs in the Permian Basin from October-November 2017.