## NOTE
THIS GIS REPORT MOCK-UP IS INTENDED FOR DISCUSSION ONLY. IT CONTAINS A MIXTURE OF ACTUAL GIS REPORT DATA AND SAMPLE DATA USED FOR ILLUSTRATIVE PURPOSES.

## Disclaimer
Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes and has been developed from data provided by Interconnecting Entities or their reporting representatives. The data may contain errors or be obsolete if Interconnecting Entities fail to provide updates to ERCOT on a timely basis. ERCOT MAKES NO WARRANTY, EXPRESS OR IMPLIED, INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE, AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS. The specific suitability for any use of the Working Paper and its accuracy should be confirmed by each entity that contributed data for this Working Paper.

## References and Acronyms
Reference Documents
Below are links to ERCOT Webpages and documents that provide information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf
Acronyms
SSS | Security Screening Study
IA | Standard Generator Interconnection Agreement
NtP | Notice to Proceed

## Summary
Summary - December 2017
GINR Milestone Status by Fuel Type
|  |  | Fuel Type | Screening Study Underway or Completed (MW) | FIS Underway / IA Not Executed (MW) | IA Executed / FIS Underway (MW) | IA Executed / FIS Completed (MW) | Grand Total (MW)**
|  |  | Gas-Other | 0 | 1942 | 5149 | 2849 | 7091
|  |  | Gas-Combined Cycle | 0 | 1939 | 4615 | 2100 | 8654
|  |  | Gas-Compressed Air (CE) | 0 | 0 | 324 | 0 | 324
|  |  | Gas | 0 | 3881 | 10088 | 4949 | 16069
|  |  | Nuclear | 0 | 0 | 0 |  | 0
|  |  | Coal | 0 | 0 | 0 |  | 0
|  |  | Wind | 5664 | 15814 | 8720 | 1450 | 31648
|  |  | Battery | 0 | 30 | 0 | 0 | 30
|  |  | Solar | 9272 | 12899 | 1952 | 350 | 24473
|  |  | Biomass | 0 | 0 | 0 |  | 0
|  |  | Petroleum Coke | 0 | 0 | 0 |  | 0
|  |  | Total | 14936 | 32624 | 20760 | 6749 | 72220
Generation Interconnection Request Summary
Currently tracking 337 generation interconnection or change requests
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY | [8 empty] | Queue Status | Base | Final | Change | Number of Projects | % of Total
December 31, 2017 | Number of Projects | % of Total | [6 empty] | Total Interconnection Requests | 337 |  |  | 337 | 1
Security Screening Studies (SSS) Underway | 14 | 4.154% | [6 empty] | Security Screening Studies (SSS) Underway | 323 | 14 | -14 | 14 | 0.041543
SSS Completed | 64 | 18.99% | [6 empty] | SSS Completed | 259 | 64 | -64 | 64 | 0.18991
FIS Underway | 163 | 48.37% | [6 empty] | Full Interconnect Study (FIS) Underway | 96 | 163 | -163 | 163 | 0.48368
FIS Completed | 19 | 5.638% | [6 empty] | FIS Completed | 77 | 19 | -19 | 19 | 0.05638
Interconnection Agreement Executed, FIS Completed | 45 | 13.35% | [6 empty] | Interconnection Agreement Executed, FIS Pending or Completed | 32 | 45 | -45 | 45 | 0.13353
Interconnection Agreement Executed, FIS Incomplete | 32 | 9.496% | [6 empty] | Interconnection Agreement Executed | 0 | 32 | -32 | 32 | 0.094955
Total Interconnection Requests | 337
Cancelled Studies (since last month) | 8
Capacity, MW
Total Capacity Under Study * | 72220
Interconnection Agreements Executed | 20760
Cancelled (since last month) | 908
* Redacted project capacity is excluded.

## Project Status Changes
Project Commissioning Status Changes and Cancellations - December 2017
Category | INR | Project | County | Date | MW
New Resources Approved for Commercial Operation * | 14INR0041a | BBREEZE | Willacy | 2017-12-21 | 228
| 14INR0057 | BUCKTHORN WIND | Erath | 2017-12-12 | 100
| 14INR0060b | SALVTION | Haskell | 2017-12-29 | 250
New Resources Approved for Synchronization | 15INR0064 | NBOHR (BearKat Wind A) | Glasscock | 2017-12-15 | 197
| 16INR0091 | HICKMAN | Reagan | 2017-12-19 | 300
| 17INR0068 | Sweetwater 2 repowering | Nolan | 2017-12-20 | 7
New Resources Approved for Energization | 14INR0038 | BAC | Galveston | 2016-06-14 | 390
| 16INR0023 | LMESASLR (BNB Lamesa Solar 1) | Dawson | 2017-01-13 | 102
| 15INR0082 | Flat Top Wind I | Comanche | 2017-12-20 | 200
| 17INR0022 | MIRAGE | Harris | 2017-02-06 | 11
Projects Cancelled by the Developer** | 16INR0089 | NW Andrews Solar | Andrews | 2017-12-04 | 60
| 16INR0092 | River Rock Solar | Brewster | 2017-12-13 | 50
| 16INR0093 | Tarbush Solar | Reeves | 2017-12-13 | 48
| 16INR0098 | Hecate Solar A | Brewster | 2017-12-08 | 50
| 16INR0100 | Hecate Solar C | Brewster | 2017-12-08 | 150
| 18INR0027 | Crane Solar | Upton | 2017-12-04 | 150
| 18INR0049 | Santa Rita Solar | Crockett | 2017-12-13 | 400
Date listed is the ERCOT Resource Commissioning Date, defined in Section 2 of the ERCOT Nodal Protocols: "The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations."
** Includes only those projects cancelled after developer makes a Full Interconnection Study request.
Changes Since Previous Monthly Report
Project Count
GINR Queue Activity | Dec 31st, 2017 | Nov 30th, 2017 | Difference
Security Screening Studies (SSS) Underway | 14 | 14 | 0
SSS Completed | 64 | 64 | 0
Full Interconnect Study (FIS) Underway | 163 | 172 | -9
FIS Completed | 19 | 15 | 4
Interconnection Agreement Executed, FIS Pending or Completed | 45 | 42 | 3
Interconnection Agreement Executed | 32 | 33 | -1
Total Interconnection Requests | 337 | 340 | -3
Total MW Capacity
| Dec 31st, 2017 | Nov 30th, 2017 | Difference
Screening Study (MW)* | 14936 | 13767 | 1169
FIS Pending or Completed (MW) | 32624 | 33548 | -924
IA Executed, FIS Pending or Approved (MW) | 20760 | 20600 | 160
Total | 68320 | 67915 | 405

## GINR Project Milestones
GINR Project Milestones - December 2017
Projects only shown for which a Full Interconnection Study has been requested
Project Attributes | [7 empty] | Changes from Last Report | GINR Project Milestones
INR | ProjectName | Interconnecting Entity | POI Location | County | Projected COD | Fuel | MW for Grid, Summer |  | SSS Complete | FIS Approved | IA Signed | Financial Commitment / NtP | Air Permit | Water Supply Declaration | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Part 1 (Approved for Energization) | Part 2 (Approved for Synchronization)
15INR0061 | LASSO | Solaire Direct | 6674 Bronco 69kV | Brewster | 2018-01-01 | Solar | 50 |  | 2014-02-17 | 2016-11-13 | 2015-11-10 | Yes | n/a | n/a | Yes | 2017-03-17 | 2017-03-30
15INR0064 | Niels Bohr (BearKat Wind A) | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2018-01-12 | Wind | 197 | Projected Date | 2014-01-27 | 2017-09-27 | 2016-12-20 | Yes | n/a | n/a | Yes | 2017-12-08 | 2017-12-15
14INR0031 | BTE (Baytown Chiller) | Calpine | 110731-110734 | Chambers | 2018-01-15 | Gas | 270 |  | 2012-08-14 | 2013-05-03 | 2013-12-11 | Yes | Yes | n/a | Yes
16INR0023 | LMESASLR (BNB Lamesa Solar 1) | RES Americas | 1163 Lamesa 138kV | Dawson | 2018-01-15 | Solar | 101.6 | Projected Date | 2014-09-10 | 2016-12-08 | 2016-07-28 | Yes | n/a | n/a | Yes | 2017-01-13 | 2017-02-14
16INR0054 | NA | NASA | 42970 Nasa 138kV | Harris | 2018-02-01 | Gas | 12 |  | 2015-04-01 | 2016-01-26 | 2016-10-27 | Yes | n/a | n/a | Yes
17INR0022 | MIRAGE | Net Power | 111161 Mirage 13.8kV | Harris | 2018-02-01 | Gas | 11 |  | 2015-05-01 | 2016-09-13 | 2016-08-31 | Yes | Yes | Yes | Yes | 2017-02-06
17INR0054 | Capricorn I & III repowering | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | 2018-02-01 | Wind | 432.5 |  | 2017-04-24 |  |  | No | n/a | n/a | No
17INR0057 | Red Canyon repowering | Nextera |  | Borden | 2018-02-01 | Wind | 89.6 |  | 2017-09-15 | 2017-10-13 |  | No | n/a | n/a | No
15INR0045 | RIGGINS | NRG | 6630 Fort Stockton 138kV | Pecos | 2018-02-12 | Solar | 150 |  | 2015-11-12 | 2017-07-24 | 2015-01-26 | Yes | n/a | n/a | Yes
13INR0049 | FEGC | Friendswood Energy Genco | 47150 HOC 138kV | Harris | 2018-02-13 | Gas | 115 | Projected Date | 2012-03-13 | 2015-06-17 | 2015-09-23 | Yes | Yes | Yes | Yes
17INR0052 | HH1 (HHGT increase) | Nextera | 6216 Bluff Creek 138kV | Taylor | 2018-03-01 | Wind | 44 |  | 2016-10-17 |  |  | No | n/a | n/a | No
17INR0053 | HH3 (HHGT increase) | Nextera | 7046 Kendal 345kV | Taylor | 2018-03-01 | Wind | 44 |  | 2016-10-17 | 2017-07-06 |  | No | n/a | n/a | No
17INR0056 | Callahan repowering | Nextera |  | Taylor | 2018-03-01 | Wind | 114 |  | 2017-09-15 | 2017-08-14 |  | No | n/a | n/a | No
17INR0058 | Horse Hollow II repowering | Nextera |  | Taylor | 2018-03-01 | Wind | 184 |  | 2017-09-15 | 2017-12-12 |  | No | n/a | n/a | No
17INR0060 | Horse Hollow IV repowering | Nextera |  | Taylor | 2018-03-01 | Wind | 115 |  | 2017-09-15 | 2017-12-12 |  | No | n/a | n/a | No
17INR0061 | Capricorn Ridge IV repowering | Nextera |  | Sterling | 2018-03-01 | Wind | 121.5 |  | 2017-09-15 |  |  | No | n/a | n/a | No
17INR0063 | Capricorn Ridge I repowerng | Nextera |  | Sterling | 2018-03-01 | Wind | 214.5 |  | 2017-09-15 | 2017-11-08 |  | No | n/a | n/a | No
17INR0064 | Capricorn Ridge II repowering | Nextera |  | Sterling | 2018-03-01 | Wind | 149.5 |  | 2017-09-15 | 2017-12-12 |  | No | n/a | n/a | No
17INR0065 | Capricorn Ridge III repowering | Nextera |  | Sterling | 2018-03-01 | Wind | 186 |  | 2017-09-15 | 2017-11-08 |  | No | n/a | n/a | No
16INR0087 | RTS Wind Project | Goldwind | 76006 Bow Wood 345kV | McCulloch | 2018-03-15 | Wind | 160 | Project Name | 2015-04-06 | 2016-03-29 | 2015-10-14 | Yes | n/a | n/a | Yes
15INR0082 | Flat Top Wind I | Alterra Power | 11441 Flat Top 345kV | Comanche | 2018-03-31 | Wind | 200 |  | 2014-05-16 | 2017-09-08 | 2016-02-19 | Yes | n/a | n/a | Yes | 2017-12-20
16INR0091 | HICKMAN | Invenergy | 76005 Schneeman Draw 345kV | Reagan | 2018-04-12 | Wind | 300 | Projected Date | 2015-05-01 | 2015-11-16 | 2017-01-03 | Yes | n/a | n/a | Yes | 2017-12-08 | 2017-12-19
16INR0065 | CASL_GAP (Castle Gap Solar) | Vistra Energy/Luminant | 132781 Castle Gap 34.5kV | Upton | 2018-06-01 | Solar | 180 |  | 2014-10-28 | 2017-07-31 | 2015-09-04 | Yes | n/a | n/a | Yes
16INR0086 | Cactus Flats Wind | Southern Power (RES Americas) | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | 2018-06-15 | Wind | 148.4 | MW For Grid | 2015-03-27 | 2017-10-20 | 2017-03-15 | Yes | n/a | n/a | Yes
18INR0013 | Denton Energy Center | Denton Municipal Electric | 916 Jim Christal 138kV | Denton | 2018-07-01 | Gas | 225.8 |  | 2015-10-15 | 2017-05-09 | 2017-03-03 | Yes | Yes | n/a | Yes
13INR0010a | Mariah Del Este | Mariah Acquisition | 141765 Mariah 345kV | Parmer | 2018-09-30 | Wind | 152.5 |  | 2009-09-25 |  | 2013-01-31 | Yes | n/a | n/a | Yes
18INR0035 | CityVict | Castleman Power | 8172 Victoria 138kV | Victoria | 2018-10-01 | Gas | 100 |  | 2016-09-27 |  |  | No | No | No | No
18INR0071 | Midway Wind II | Apex Clean | 161503 Midwind 138kV | San Patricio | 2018-10-01 | Wind | 52 |  | 2017-12-13 |  |  | No | n/a | n/a | No
18INR0025 | Tahoka Wind | Lincoln Clean | 59900 Long Draw 345kV + radial | Lynn | 2018-10-01 | Wind | 505 | SFS | 2016-03-23 | 2017-01-26 | 2017-07-19 | Yes | n/a | n/a | Yes
16INR0076 | Brazoria Energy G | Ineos | New 138kV sub near Amoco (#42090) | Brazoria | 2018-10-04 | Gas | 96 | NEW | 2015-03-19 | 2017-08-24 | 2017-12-05 | Yes | Yes | No | Yes
18INR0067 | Gopher Creek Wind | Terna Energy | 11306 Dermott 138kV | Scurry | 2018-11-19 | Wind | 158 |  | 2017-08-28 |  |  | No | n/a | n/a | No
14INR0023b | LHORN (Longhorn South W) | EDF Renewables | 140853 Tule Canyon 345kV | Briscoe | 2018-12-01 | Wind | 160 |  | 2012-05-07 |  | 2012-12-10 | Yes | n/a | n/a | Yes
16INR0019 | Capricorn Ridge Solar | Nextera | 76090 Divide 345kV | Coke | 2018-12-01 | Solar | 100 |  | 2013-12-30 |  | 2015-08-19 | No | n/a | n/a | No
16INR0114 | Upton Solar | SunPower | 132581 Upton 34.5kV | Upton | 2018-12-01 | Solar | 102 |  | 2015-07-02 |  | 2015-12-04 | Yes | n/a | n/a | Yes
16INR0121 | Salt Fork Wind Expansion | Southern Power Company | 79000 Gray 345kV | Carson | 2018-12-01 | Wind | 54 |  | 2015-12-11 |  | 2016-06-28 | No | n/a | n/a | No
18INR0070 | Blue Summit II | Nextera | 61001 Jim Treece 345kV | Wilbarger | 2018-12-03 | Wind | 102 |  | 2017-12-21 |  |  | No | n/a | n/a | No
15INR0064b | BearKat Wind B | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2018-12-03 | Wind | 162.1 | Projected Date | 2014-01-27 | 2017-09-27 | 2016-12-20 | Yes | n/a | n/a | Yes
15INR0035 | Stella 1 Wind | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | 2018-12-15 | Wind | 201 |  | 2013-03-15 |  | 2017-08-02 | No | n/a | n/a | No
16INR0115 | Waymark Solar | 174 Power Global | 76002 Bakersfield 345kV | Pecos | 2018-12-15 | Solar | 182 |  | 2015-06-12 |  | 2016-09-23 | Yes | n/a | n/a | Yes
16INR0037c | Pumpkin Farm Wind | Apex Clean | 79505 White River 345kV | Floyd | 2018-12-23 | Wind | 280.9 |  | 2014-04-08 |  | 2017-03-24 | Yes | n/a | n/a | Yes
13INR0010c | Mariah Del Sur | Mariah Acquisition | 141765 Mariah 345kV | Parmer | 2018-12-31 | Wind | 217.5 |  | 2009-09-25 |  | 2013-01-31 | Yes | n/a | n/a | Yes
14INR0033 | Goodnight Wind | FGE Power | tap 345kV 79500 Alibates - 70501 Tule Canyon | Armstrong | 2018-12-31 | Wind | 496.8 |  | 2012-09-19 | 2017-09-25 | 2016-08-09 | No | n/a | n/a | No
14INR0045a | Torrecillas Wind A | Nextera | 161252, 161301 Torrecillas 34.5kV | Webb | 2018-12-31 | Wind | 200 |  | 2013-03-14 |  | 2015-01-30 | Yes | n/a | n/a | Yes
14INR0045b | Torrecillas Wind B | Nextera | 161352, 161401 Torrecillas 34.5kV | Webb | 2018-12-31 | Wind | 200 |  | 2013-07-20 |  | 2015-01-30 | Yes | n/a | n/a | Yes
17INR0020a | RE Maplewood 2a Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2018-12-31 | Solar | 100 |  | 2014-12-01 |  | 2016-02-03 | Yes | n/a | n/a | Yes
18INR0016 | Heart of Texas Wind | RES Americas | 76006 Bow Wood 345kV | McCulloch | 2018-12-31 | Wind | 150 |  | 2015-12-07 | 2017-03-24 | 2017-11-21 | No | n/a | n/a | No
18INR0072 | Blue Summit Repowering | Nextera | 140382 Blue Summit 1.6 34.5kV | Wilbarger | 2018-12-31 | Wind | 145.3 |  |  |  |  | No | n/a | n/a | No
16INR0112 | Loma Pinta Wind | Enerverse | 5705 Fowlerton 138kV | La Salle | 2018-12-31 | Wind | 200 | NEW | 2015-07-02 | 2017-03-24 | 2017-12-13 | Yes | n/a | n/a | Yes
17INR0005 | Cabezon Wind | Longroad Energy | 80355 Del Sol 345kV | Starr | 2018-12-31 | Wind | 237.6 | Project Name, SFS | 2013-10-25 | 2017-12-22 | 2017-08-03 | Yes | n/a | n/a | Yes
14INR0038 | BAC | PHR Holdings | 111132-7 BAC 13.8kV | Galveston | 2018-12-31 | Gas | 388 | Projected Date | 2012-12-11 | 2013-10-28 | 2014-01-21 | Yes | Yes | n/a | Yes | 2016-06-14 | 2017-03-22
16INR0023b | Lamesa Solar B (Phase II) | BNB Renewables (RES) | 1163 Lamesa 138kV | Dawson | 2018-12-31 | Solar | 50 | Projected Date, SFS | 2014-09-10 |  | 2016-07-28 | Yes | n/a | n/a | Yes
19INR0137 | Live Oak Solar | Infinity Wind | 76003 Big Hill 345kV | Schleicher | 2019-01-01 | Solar | 50 |  | 2017-11-14 |  |  | No | n/a | n/a | No
15INR0059 | Emerald Grove Solar | Cypress Creek Renewables | 6601 Rio Pecos 138kV | Pecos | 2019-01-01 | Solar | 108 | Project Name | 2013-12-23 |  | 2015-06-09 | Yes | n/a | n/a | Yes
19INR0029 | Phoebe Solar | Longroad Energy | tap 138kV 1009 Yucca - 1146 Notrees OR tap Vest-Yukon | Winkler | 2019-01-25 | Solar | 300 |  | 2017-02-15 |  |  | No | n/a | n/a | No
19INR0031 | Bestla Solar | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | 2019-01-25 | Solar | 150 |  | 2017-03-06 |  |  | No | n/a | n/a | No
15INR0023 | Indeck Wharton | Indeck Energy Services | tap 345kV 44200 Hillje - 44000 WA Parrish | Wharton | 2019-02-01 | Gas | 654 |  | 2012-12-04 | 2016-12-06 | 2014-09-15 | No | Yes | Yes | No
11INR0054 | Midway Wind | Apex Clean | 8961 Whitepoint 138kV | San Patricio | 2019-03-01 | Wind | 162.9 |  | 2009-05-28 |  | 2012-09-24 | Yes | n/a | n/a | Yes
16INR0074 | Chocolate Bayou W | Map Royalty | tap 138kV 42090 Amoco - 42940 Monsanto | Brazoria | 2019-03-01 | Wind | 150 |  | 2015-03-02 |  |  | No | n/a | n/a | No
19INR0020 | SP-Pecos Bend Solar A | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | 2019-03-01 | Solar | 180 |  | 2016-12-07 |  |  | No | n/a | n/a | No
19INR0020b | SP-Pecos Bend Solar B | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | 2019-03-01 | Solar | 180 |  | 2016-12-07 |  |  | No | n/a | n/a | No
19INR0020c | SP-Pecos Bend Solar C | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | 2019-03-01 | Solar | 180 |  | 2016-12-07 |  |  | No | n/a | n/a | No
12INR0055 | Little Mountain Wind | Infinity Wind | tap 69kV radial LakeKempSw 782 - LakeKemp 783 | Baylor | 2019-03-01 | Wind | 80 | NEW | 2010-12-20 |  | 2017-12-04 | No | n/a | n/a | No
19INR0041 | Myrtle Solar | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | 2019-03-17 | Solar | 200 |  | 2017-04-28 |  |  | No | n/a | n/a | No
19INR0042 | Long Point Solar | Sunchase Power | tap 138kV 44010 WAP - 42981 Nash98 | Fort Bend | 2019-03-17 | Solar | 100 |  | 2017-04-20 |  |  | No | n/a | n/a | No
19INR0044 | Lily Solar | Sunchase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | 2019-03-27 | Solar | 150 |  | 2017-04-28 |  |  | No | n/a | n/a | No
18INR0039 | Fowler Ranch | Solar Prime | tap 138kV 60014 Spudder - 76615 Crane | Crane | 2019-03-30 | Solar | 150 |  | 2016-11-08 |  |  | No | n/a | n/a | No
18INR0055 | Long Draw Solar | BNB Renewables | 59900 Long Draw 345kV | Borden | 2019-03-31 | Solar | 225 |  | 2017-02-02 |  |  | No | n/a | n/a | No
18INR0060 | Brightside Solar | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | 2019-03-31 | Solar | 50 |  | 2017-03-20 |  |  | No | n/a | n/a | No
18INR0061 | Shakes Solar | Cypress Creek Renewables | tap 138kV 8283 Asherton - 8236 W_Batesvl | Zavala | 2019-03-31 | Solar | 42 |  | 2017-03-22 |  |  | No | n/a | n/a | No
16INR0008 | Tenaska Roans Prairie | Tenaska | tap 345kV 44645 Singleton - 46500 Tomball | Grimes | 2019-04-01 | Gas | 663 |  | 2013-02-04 | 2016-09-12 | 2014-11-17 | No | Yes | No | No
16INR0036 | Pecan Creek 1 Gas | NTE Energy | tap 345kV 11420 Sweetwater - 11406 Central Bluff | Nolan | 2019-04-01 | Gas | 280 |  | 2014-03-26 |  |  | No | Yes | No | No
17INR0045 | Castleman Victoria | Castleman Power | 8143 Dupont 138kV | Victoria | 2019-04-01 | Gas | 100 |  | 2016-06-10 |  |  | No | No | No | No
18INR0040 | Soda Lake Solar 1 and 2 | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | 2019-04-01 | Solar | 400 |  | 2016-11-08 |  |  | No | n/a | n/a | No
19INR0056 | Chamon Phase 2 | Castleman Power | 40260 Chamon 138kV | Harris | 2019-04-01 | Gas | 100 |  | 2017-06-09 |  |  | No | No | No | No
19INR0057 | Victoria Port Phase 2 | Castleman Power | 8143 Dupont 138kV | Victoria | 2019-04-01 | Gas | 100 |  | 2017-05-22 |  |  | No | No | No | No
19INR0091 | GSE ONE Solar | Alpin Sun | 1808 Bonham 138kV | Fannin | 2019-04-01 | Solar | 82.5 |  | 2017-08-23 |  |  | No | n/a | n/a | No
19INR0093 | Sole Mio | Alpin Sun | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | 2019-04-01 | Solar | 45 |  | 2017-08-23 |  |  | No | n/a | n/a | No
19INR0094 | GSE Three Solar | Alpin Sun | 6044 Turkey 69kV | Hall | 2019-04-01 | Solar | 50 |  | 2017-08-23 |  |  | No | n/a | n/a | No
19INR0123 | GSE Eleven | Alpin Sun | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | 2019-04-01 | Solar | 150 |  | 2017-11-13 |  |  | No | n/a | n/a | No
19INR0124 | Sole Mio One | Alpin Sun | tap 138kV 1698 Sulphur Springs Switch - 1814 Sulphur Springs | Hopkins | 2019-04-01 | Solar | 50 |  | 2017-11-13 |  |  | No | n/a | n/a | No
16INR0010 | FGE Texas 1 | FGE Power | Tap 345kV 1030 Morgan - 1025 Falcon | Mitchell | 2019-04-05 | Gas | 720 |  | 2013-05-29 |  | 2016-08-31 | No | Yes | Yes | No
13INR0026 | Canadian Breaks Wind | Macquarie Cap | Tap 345kV 79502 Windmill - 79504 AJ Swope | Oldham | 2019-04-15 | Wind | 210 |  | 2010-10-04 | 2017-03-16 | 2016-05-20 | No | n/a | n/a | No
18INR0045 | Misae Solar | Childress Solar LLC | 60501 Tesla 345kV | Childress | 2019-04-15 | Solar | 240.8 |  | 2017-01-06 |  |  | No | n/a | n/a | No
18INR0050 | Mustang Creek Solar | Sunchase Power | 5523 ETP 138kV | Jackson | 2019-04-30 | Solar | 150 |  | 2016-12-20 |  |  | No | n/a | n/a | No
18INR0058 | Texana Solar | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | 2019-04-30 | Solar | 150 |  | 2017-02-14 |  |  | No | n/a | n/a | No
19INR0119 | Patriot Wind II | NRG | 85000 Nelson Sharpe 345kV | Nueces | 2019-04-30 | Wind | 57.6 |  | 2017-10-25 |  |  | No | n/a | n/a | No
11INR0062 | Patriot Wind | NRG | 85000 Nelson Sharpe 345kV | Nueces | 2019-04-30 | Wind | 180 | Projected Date | 2009-06-16 |  | 2016-10-13 | Yes | n/a | n/a | Yes
13INR0010def | Scandia Wind DEF | Scandia Southwest | 141765 Mariah 345kV | Parmer | 2019-05-01 | Wind | 600.3 |  | 2009-09-25 | 2017-08-03 | 2014-04-25 | No | n/a | n/a | No
17INR0027b | Coyote Wind | Lincoln Clean | 11305 Dermott 345kV | Scurry | 2019-05-01 | Wind | 242.5 |  | 2015-05-22 |  | 2016-08-09 | Yes | n/a | n/a | Yes
19INR0082 | Diebel | Castleman Power | 8140 Joslin 138kV | Calhoun | 2019-05-01 | Gas | 100 |  | 2017-08-09 |  |  | No | No | No | No
19INR0092 | Prospero Solar | Longroad Energy | 79650 Clear Fork 345kV (or 1158 Andrews Co 345kV) | Andrews | 2019-05-01 | Solar | 300 |  | 2017-08-07 |  |  | No | n/a | n/a | No
16INR0111 | Las Lomas Wind | Enerverse | 8957 Lopeno 138kV | Starr | 2019-05-31 | Wind | 200 |  | 2015-06-25 |  |  | No | n/a | n/a | No
18INR0030 | Canyon Wind | TriGlobal | 11319 ScurryCounty 138kV | Scurry | 2019-05-31 | Wind | 300.9 |  | 2016-07-22 |  |  | No | n/a | n/a | No
18INR0053 | Fort Bend Solar | Lendlease Energy | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | 2019-05-31 | Solar | 240 |  | 2017-02-15 |  |  | No | n/a | n/a | No
16INR0003 | LEVEE (Freeport LNG) | Freeport LNG | Oyster Creek (tap 138kV 43360 Vlasco - 42190 Biport) | Brazoria | 2019-06-01 | Gas | 11 |  | 2012-02-15 |  | 2014-01-13 | Yes | Yes | n/a | Yes
16INR0044 | Halyard Wharton | Halyard Energy | tap 345kV 9073 Holman - 44200 Hillje | Wharton | 2019-06-01 | Gas | 419 |  | 2014-04-28 | 2015-08-25 | 2016-01-26 | No | Yes | Yes | No
16INR0045 | Halyard Henderson | Halyard Energy | tap 345kV 3109 Stryker - 3123 Trinidad | Henderson | 2019-06-01 | Gas | 450 |  | 2014-04-15 |  | 2016-04-01 | No | Yes | Yes | No
16INR0062b | Lockett Wind | Lincoln Clean | 141355-6 Electra 34.5kV | Wilbarger | 2019-06-01 | Wind | 184 |  | 2014-12-10 |  | 2015-03-31 | Yes | n/a | n/a | Yes
17INR0016 | Union Valley G | Quantum | tap one 345kV 5133 Elm Creek - 5915 STP | Wilson | 2019-06-01 | Gas | 591.6 |  | 2014-07-11 |  | 2016-01-22 | No | Yes | No | No
17INR0017 | Clear Springs G | Quantum | 7050 Clear Springs 345kV | Guadalupe | 2019-06-01 | Gas | 591.6 |  | 2014-07-02 |  | 2016-05-11 | No | Yes | No | No
16INR0102 | Hecate Sun Valley 130 | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | 2019-06-01 | Solar | 130 |  | 2015-05-14 |  |  | No | n/a | n/a | No
18INR0023 | Lost Mines Wind | RES Americas | 60708 Orsted 345kV | Menard | 2019-06-01 | Wind | 250 |  | 2016-09-04 |  |  | No | n/a | n/a | No
19INR0001 | Texas Solar Nova | SunPower | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | 2019-06-01 | Solar | 750 |  | 2015-12-30 |  |  | No | n/a | n/a | No
19INR0009 | Holstein Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | 2019-06-01 | Solar | 200 |  | 2016-09-13 |  |  | No | n/a | n/a | No
19INR0028 | Normande Solar Farm | 8minutenergy | 59900 Long Draw 345kV | Borden | 2019-06-01 | Solar | 300 |  | 2017-02-22 |  |  | No | n/a | n/a | No
19INR0131 | Cutlass Solar | Lendlease Energy | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | 2019-06-01 | Solar | 300 |  | 2017-11-20 |  |  | No | n/a | n/a | No
20INR0011 | Ranchero Wind | Scout Clean Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | 2019-06-04 | Wind | 250 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0095 | Borden Wind | Longroad Energy | 59905 Faraday 345kV OR 1301 Willow Valley 138kV | Borden | 2019-06-06 | Wind | 250 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0036 | Oxbow Solar | BNB Renewables | 59905 Faraday 345kV | Borden | 2019-06-15 | Solar | 250 |  | 2017-04-13 |  |  | No | n/a | n/a | No
18INR0033 | Irion County Wind | Invenergy | 76005 Schneeman Draw 345kV | Irion | 2019-06-30 | Wind | 300 |  | 2016-09-07 |  |  | No | n/a | n/a | No
19INR0017 | Tri-County Solar | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | 2019-06-30 | Solar | 207 |  | 2016-11-29 |  |  | No | n/a | n/a | No
19INR0019 | Foard City Wind | Alterra Power | 60500 Edith Clarke 345kV | Foard | 2019-06-30 | Wind | 350 |  | 2016-11-28 |  |  | No | n/a | n/a | No
19INR0080 | Mesquite Star Wind | Hill Country Wind | 68001 Clayton 345kV | Fisher | 2019-06-30 | Wind | 400 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0122 | Lone Star 1 | Solar Gen Resources | 39950 TNP One 345kV OR 34 Calvert 138kV | Robertson | 2019-06-30 | Solar | 150 |  | 2017-10-27 |  |  | No | n/a | n/a | No
18INR0001 | Rockwood G | Lincoln Clean | tap 345kV 44200 Hillje - 9073 Holman | Colorado | 2019-07-01 | Gas | 1122 |  | 2014-06-13 |  | 2015-11-30 | No | Yes | No | No
13INR0025 | Buffalo Wind 1 | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | 2019-07-01 | Wind | 150 |  | 2010-09-02 | 2017-08-30 |  | No | n/a | n/a | No
18INR0064 | Silver Star repowering | BP | 150511 Flat Creek 34.5kV | Eastland | 2019-07-01 | Wind | 52.8 |  | 2017-05-08 |  |  | No | n/a | n/a | No
18INR0065 | Goodranch Solar | EDF Renewables | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | 2019-07-01 | Solar | 200 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0130 | Buckthorn Solar 2 | NRG | tap 69kV 6643 PecosV - 38470 Gomez or other | Pecos | 2019-07-01 | Solar | 75 |  | 2017-11-13 |  |  | No | n/a | n/a | No
18INR0009 | FGE Eagle Pines I | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | 2019-08-01 | Gas | 1156 |  | 2015-06-23 |  |  | No | Yes | No | No
19INR0083 | Oberon Solar | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | 2019-08-01 | Solar | 180 |  | 2017-07-13 |  |  | No | n/a | n/a | No
18INR0062 | Wagyu Solar | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | 2019-08-15 | Solar | 120 |  | 2017-04-03 |  |  | No | n/a | n/a | No
18INR0029 | Armstrong Wind | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | 2019-09-01 | Wind | 253 |  | 2016-05-24 |  |  | No | n/a | n/a | No
19INR0038 | High Lonesome W | Swift Current Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | 2019-09-01 | Wind | 500 |  | 2017-04-17 |  |  | No | n/a | n/a | No
19INR0098 | Pease River Wind | Eon | 60500 Edith Clarke 345kV | Hardeman | 2019-09-01 | Wind | 301.4 |  | 2017-08-28 |  |  | No | n/a | n/a | No
19INR0099a | Kontiki Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2019-09-01 | Wind | 255.3 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0107 | Las Palmas Wind II | Eon | tap 345kV 8383 NEdinb - 8318 Rio Hondo, ~10.5 mi from RH new sub Bonilla + 18 mi gentie | Willacy | 2019-09-01 | Wind | 102 |  | 2017-09-13 |  |  | No | n/a | n/a | No
19INR0116 | KMF Wind | Eon | tap 138kV 8899 Armstrong - 5648 Loyola | Kenedy | 2019-09-01 | Wind | 150 |  | 2017-10-25 |  |  | No | n/a | n/a | No
19INR0154 | Yturria Ranch Wind | Apex Clean | 80513 MGValleytap 345kV OR tap 138kV 5742 Yturria - 8302 Raymondvl | Willacy | 2019-09-01 | Wind | 169.2 |  |  |  |  | No | n/a | n/a | No
18INR0043 | Edmondson Ranch Wind | Wind Tex | 59903 Bearkat 345kV | Glasscock | 2019-09-01 | Wind | 292.5 | SFS | 2016-12-22 |  | 2017-10-04 | Yes | n/a | n/a | Yes
17INR0010 | FGE Texas II | FGE Power | Tap 345kV 1030 Morgan – 1058 Longshore | Mitchell | 2019-09-15 | Gas | 703 |  | 2014-03-26 |  | 2015-06-02 | No | Yes | No | No
19INR0138 | Buffalo Gap 4 | AES | 66216 Bluff Creek 138kV | Nolan | 2019-09-15 | Wind | 175 |  | 2017-11-20 |  |  | No | n/a | n/a | No
16INR0097 | Morada Del Sol Solar | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | 2019-09-30 | Solar | 200 |  | 2015-06-23 |  |  | No | n/a | n/a | No
19INR0102 | Queen Solar | Cielo Wind | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | 2019-09-30 | Solar | 400 |  | 2017-08-28 |  |  | No | n/a | n/a | No
19INR0125 | Wolfcamp 1 | Energie Kontor | 60397 Gaspad 138kV | Pecos | 2019-09-30 | Solar | 100 |  | 2017-11-01 |  |  | No | n/a | n/a | No
19INR0126 | Wolfcamp 2 | Energie Kontor | 6673 Musquiz 138kV | Pecos | 2019-09-30 | Solar | 100 |  | 2017-11-01 |  |  | No | n/a | n/a | No
15INR0050 | Unity Wind | Miller Wind | 79502 Windmill 345kV | Deaf Smith | 2019-10-01 | Wind | 203 |  | 2013-11-04 |  | 2014-10-03 | No | n/a | n/a | No
16INR0049 | Nazareth Solar | Lincoln Clean | 79501 Ogallala 345kV | Castro | 2019-10-01 | Solar | 201 |  | 2014-07-25 | 2016-07-18 | 2015-05-15 | No | n/a | n/a | No
18INR0004 | Shawnee G | Lincoln Clean | 68090 Sam Switch 345kV | Hill | 2019-10-01 | Gas | 928 |  | 2014-08-07 |  | 2016-04-19 | No | Yes | No | No
18INR0027 | Ponwar Solar Farm | 8minutenergy | tap 138kV 76032 NMcCamey - 60361 Santa Rita | Upton | 2019-10-01 | Solar | 180 |  | 2016-05-27 |  |  | No | n/a | n/a | No
18INR0042 | Kaiser Creek Wind | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | 2019-10-01 | Wind | 100 |  | 2016-12-01 |  |  | No | n/a | n/a | No
19INR0004 | Sanco Solar | 8minutenergy | 79502 Windmill 345kV | Deaf Smith | 2019-10-01 | Solar | 400 |  | 2016-11-01 | 2017-11-10 |  | No | n/a | n/a | No
19INR0007 | Charbray Solar | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | 2019-10-01 | Solar | 180 |  | 2016-10-07 |  |  | No | n/a | n/a | No
19INR0120 | Sherbino II Wind repowering | BP | 131454 Keo_3 138kV | Pecos | 2019-10-01 | Wind | 132 |  | 2017-09-28 |  |  | No | n/a | n/a | No
19INR0134 | Cottonwood Bayou | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | 2019-10-01 | Solar | 150 |  | 2017-11-17 |  |  | No | n/a | n/a | No
19INR0135 | Hill Solar | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasco OR 3523 Hillsboro 69kV | Hill | 2019-10-01 | Solar | 80 |  | 2017-11-17 |  |  | No | n/a | n/a | No
19INR0136 | Able Solar | Sunchase Power | 12469 Able Spring 138kV | Kaufman | 2019-10-01 | Solar | 50 |  | 2017-11-17 |  |  | No | n/a | n/a | No
19INR0142 | Bacon Switch Solar | Sunchase Power | tap 345kV 6101 Riley - 1425 Fisher OR 138kV 1450 Pleasva – 1485 Ceramic | Wichita | 2019-10-01 | Solar | 150 |  | 2017-11-08 |  |  | No | n/a | n/a | No
19INR0144 | Bird Dog Wind | Americlean | 1301 Willow Valley 138kV | Borden | 2019-10-01 | Wind | 300 |  | 2017-12-14 |  |  | No | n/a | n/a | No
18INR0068 | Loraine Windpark Phase III | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | 2019-10-15 | Wind | 100 |  | 2017-10-05 |  |  | No | n/a | n/a | No
19INR0100 | Prairie Hill Wind | Map Royalty | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | Limestone | 2019-10-15 | Wind | 300 |  | 2017-08-11 |  |  | No | n/a | n/a | No
13INR0038 | Wildrose Wind | S Power | 79501 Ogallala 345kV | Swisher | 2019-10-30 | Wind | 211.9 |  | 2011-05-26 | 2016-02-12 | 2015-09-06 | Yes | n/a | n/a | Yes
12INR0002a | Silver Canyon Wind A | EDP Renewables | 79503 Tule Canyon 345kV | Briscoe | 2019-10-31 | Wind | 200 |  | 2007-01-26 |  | 2016-06-22 | No | n/a | n/a | No
15INR0079 | Pullman Road Wind | SunEdison | 79500 Alibates 345kV | Randall | 2019-10-31 | Wind | 300 |  | 2014-04-11 | 2016-03-14 | 2014-05-29 | No | n/a | n/a | No
15INR0063 | Easter Wind A | TriGlobal | 79502 Windmill 345kV | Castro | 2019-10-31 | Wind | 155 |  | 2014-02-27 | 2017-12-06 |  | No | n/a | n/a | No
17INR0025 | Reloj Del Sol Wind | EDP Renewables | 80220 Cenizo 345kV | Zapata | 2019-10-31 | Wind | 202 |  | 2015-05-05 |  |  | No | n/a | n/a | No
18INR0056 | Hallmark Solar | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | 2019-10-31 | Solar | 50 |  | 2017-02-16 |  |  | No | n/a | n/a | No
19INR0045 | Rayos Del Sol | Tradewind Energy | Two POIs tested in Screening study. POI 1: a tap to the 345kV line between Palmito (5966) and Steward (80137) 2. tap to the 138kV line between Wesmer and Rangerville | Cameron | 2019-10-31 | Solar | 150 |  | 2017-05-22 |  |  | No | n/a | n/a | No
19INR0053 | Hidalgo II Wind | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | 2019-10-31 | Wind | 51 |  | 2017-05-19 |  |  | No | n/a | n/a | No
19INR0109 | Crockett Solar | EDP Renewables | tap 138kV 6564 Illinois - 76579 Ft Lancaster | Crockett | 2019-10-31 | Solar | 150 |  | 2017-09-13 |  |  | No | n/a | n/a | No
19INR0110 | Angelina Solar | EDP Renewables | 3349 TMPLinla 138kV | Angelina | 2019-10-31 | Solar | 150 |  | 2017-09-15 |  |  | No | n/a | n/a | No
19INR0111 | Tom Green Solar | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | 2019-10-31 | Solar | 150 |  | 2017-09-13 |  |  | No | n/a | n/a | No
19INR0006 | Bluebonnet Solar | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | 2019-11-01 | Solar | 60.7 |  | 2016-10-07 |  |  | No | n/a | n/a | No
19INR0104 | Alpine Solar | ReneSola | 6666 Alpine 69kV | Brewster | 2019-11-01 | Solar | 50 |  | 2017-11-14 |  |  | No | n/a | n/a | No
19INR0150 | Millhouse Solar | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | 2019-11-15 | Solar | 113 |  |  |  |  | No | n/a | n/a | No
16INR0081 | Mesteno Wind | Duke Energy | 80355 Del Sol 345kV | Starr | 2019-11-30 | Wind | 201.6 |  | 2015-03-09 |  |  | No | n/a | n/a | No
17INR0035 | Las Majadas Wind | EDF Renewables | 80512 MagicValleytap 345kV | Willacy | 2019-11-30 | Wind | 227 |  | 2015-12-14 |  |  | No | n/a | n/a | No
19INR0149 | Lapetus Solar | 7x Energy | 1284 Shafter Lake 138kV | Andrews | 2019-11-30 | Solar | 50 |  |  |  |  | No | n/a | n/a | No
19INR0155 | Morrow Lake Solar | Sunchase Power | tap 138kV Pearsall 5895 - Miracle 5700 | Frio | 2019-11-30 | Solar | 150 |  |  |  |  | No | n/a | n/a | No
12INR0060 | Infinity Live Oak Wind | Infinity Wind | 76003 Big Hill 345kV | Schleicher | 2019-12-01 | Wind | 199.5 |  | 2014-03-21 |  | 2016-11-03 | Yes | n/a | n/a | Yes
15INR0090 | Pflugerville Solar | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | 2019-12-01 | Solar | 120 |  | 2015-07-01 | 2017-03-09 | 2017-06-13 | No | n/a | n/a | No
16INR0104 | Big Sampson Wind Project | Infinity Wind | 76005 Schneeman Draw 345kV | Crockett | 2019-12-01 | Wind | 400 |  | 2015-06-17 |  |  | No | n/a | n/a | No
16INR0105 | Zapata I W | Nextera | 80230 Molina 138kV | Jim Hogg | 2019-12-01 | Wind | 300 |  | 2015-05-26 |  |  | No | n/a | n/a | No
17INR0033 | Tecovas 2 W | Infinity Wind | 79503 Tule Canyon 345kV | Briscoe | 2019-12-01 | Wind | 200.1 |  | 2015-07-06 |  |  | No | n/a | n/a | No
17INR0036 | Grandview 4 Phase A Wind | Eon | tap 345kV 79000 Gray - 79006 Allen | Gray | 2019-12-01 | Wind | 200.5 |  | 2016-01-11 |  |  | No | n/a | n/a | No
18INR0018 | Peyton Creek Wind | Eon | tap 345kV 5915 STP - 42500 Dow | Matagorda | 2019-12-01 | Wind | 150 |  | 2015-12-22 | 2017-07-24 |  | No | n/a | n/a | No
18INR0031 | Maryneal Wind | Duke Energy | 71050 Bitter Creek 345kV | Nolan | 2019-12-01 | Wind | 180 |  | 2016-07-21 |  |  | No | n/a | n/a | No
18INR0038 | Jumbo Hill Wind | Infinity Wind | 1134 Littman bus 138kV | Andrews | 2019-12-01 | Wind | 200 |  | 2016-12-12 |  |  | No | n/a | n/a | No
19INR0002 | King Mountain Solar | Nextera | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | 2019-12-01 | Solar | 350 |  | 2016-06-06 |  |  | No | n/a | n/a | No
19INR0026 | Holstein 2 Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | 2019-12-01 | Solar | 100 |  | 2017-02-02 |  |  | No | n/a | n/a | No
19INR0033 | Murphy Lake Solar | S Power | 6904 CombinRC 138kV | Kaufman | 2019-12-01 | Solar | 100 |  | 2017-03-03 |  |  | No | n/a | n/a | No
19INR0035 | Norton Solar | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | 2019-12-01 | Solar | 125 |  | 2017-04-20 |  |  | No | n/a | n/a | No
19INR0061 | Gold Creek Solar | S Power | 1163 Lamesa 138kV | Dawson | 2019-12-01 | Solar | 200 |  | 2017-07-24 |  |  | No | n/a | n/a | No
19INR0070 | Trevino Solar | S Power | 78015 Rosita 138kV | Maverick | 2019-12-01 | Solar | 180 |  | 2017-06-02 |  |  | No | n/a | n/a | No
19INR0075 | Horseshoe Bend Solar | Clenera | 1444 Brown 345kV | Coleman | 2019-12-01 | Solar | 250 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0076 | Duffau Solar | Clenera | Tap 138kV 3522 Hillsboro - 3515 Hubbard | Erath | 2019-12-01 | Solar | 100 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0077 | Harton Solar | 8minutenergy | 1665 Brownwood Switching Station 138kV | Brown | 2019-12-01 | Solar | 250 |  | 2017-07-31 |  |  | No | n/a | n/a | No
19INR0078 | Salorn Solar | 8minutenergy | 4 Iola 138kV | Grimes | 2019-12-01 | Solar | 200 |  | 2017-07-18 |  |  | No | n/a | n/a | No
19INR0079 | White Park Solar | 8minutenergy | 3412 Temple Pecan 345kV | Bell | 2019-12-01 | Solar | 600 |  | 2017-07-18 |  |  | No | n/a | n/a | No
19INR0089 | Castle Rock Solar | Clenera | 11305 Dermott 345kV | Scurry | 2019-12-01 | Solar | 250 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0113 | County Line Solar | S Power | 60385 Solstice 138kV, Tap between Pigcreek (60393) and TNFLATTOP (38069) | Pecos | 2019-12-01 | Solar | 250 |  | 2017-11-01 |  |  | No | n/a | n/a | No
19INR0121 | Galloway Solar | 8minutenergy | tap 345kV 6444 Red Creek - 76006 Bowwood OR 1444 Brown - 76009 TwinButtes | Concho | 2019-12-01 | Solar | 360 |  | 2017-10-02 |  |  | No | n/a | n/a | No
19INR0129 | Flatland Solar | TriGlobal | 1309 Bluftap 138kV or tap 138kV 1032 Morgan - 1064 Sun | Scurry | 2019-12-01 | Solar | 150 |  | 2017-12-13 |  |  | No | n/a | n/a | No
19INR0139 | Craver Ranch | sPower | tap 138kV 562 Aubrey - 672 Rector | Denton | 2019-12-01 | Solar | 100 |  | 2017-12-07 |  |  | No | n/a | n/a | No
19INR0148 | Simmental Solar | 8minutenergy | 5390 Somerset 138kV OR 5290 Lytle 138kV | Bexar | 2019-12-01 | Solar | 200 |  | 2018-01-11 |  |  | No | n/a | n/a | No
19INR0160 | Great Dane Wind | Seventus Gen | 138kV Danevang substation | Wharton | 2019-12-01 | Wind | 302.5 |  |  |  |  | No | n/a | n/a | No
19INR0161 | Pierce Wind | Seventus | 345kV ROW between Hillje & WAP | Wharton | 2019-12-01 | Wind | 300 |  |  |  |  | No | n/a | n/a | No
13INR0005c | Grandview W 3 | Eon | 140653 Alibates 345kV | Carson | 2019-12-15 | Wind | 187.5 |  | 2009-06-08 |  | 2014-04-23 | Yes | n/a | n/a | Yes
15INR0051 | Tierra Blanca W | Eon | 79501 Ogallala 345kV | Randall | 2019-12-15 | Wind | 200 |  | 2013-10-18 |  |  | No | n/a | n/a | No
16INR0012 | Stella 2 Wind | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | 2019-12-15 | Wind | 201 |  | 2013-03-15 |  |  | No | n/a | n/a | No
16INR0014 | Cattleman Wind A | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | 2019-12-15 | Wind | 201.6 |  | 2013-11-18 |  |  | No | n/a | n/a | No
16INR0014b | Cattleman Wind B | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | 2019-12-15 | Wind | 201.6 |  | 2013-11-18 |  |  | No | n/a | n/a | No
18INR0057 | Green Valley Wind | Eon | Tap 138kV 8255 Hamilton - 8680 Rough Canyon | Val Verde | 2019-12-15 | Wind | 500 |  | 2017-03-13 |  |  | No | n/a | n/a | No
18INR0059 | Raymond Wind | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | 2019-12-15 | Wind | 201.6 |  | 2017-03-09 |  |  | No | n/a | n/a | No
19INR0051 | Truscott Gilliland West W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | 2019-12-15 | Wind | 277.5 |  | 2017-05-18 |  |  | No | n/a | n/a | No
19INR0052 | Truscott Gilliland East W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | 2019-12-15 | Wind | 277.5 |  | 2017-05-18 |  |  | No | n/a | n/a | No
19INR0073 | Shakes Solar II | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | 2019-12-15 | Solar | 158 |  | 2017-06-15 |  |  | No | n/a | n/a | No
19INR0084 | Brazos Solar | Open Road Renewables | tap 138kV 8162 Coleto - 8186 Kenedy | Karnes | 2019-12-15 | Solar | 110 |  | 2017-07-14 |  |  | No | n/a | n/a | No
19INR0085 | Iola Solar | Open Road Renewables | 4 Iola 138kV | Grimes | 2019-12-15 | Solar | 210 |  | 2017-08-11 |  |  | No | n/a | n/a | No
19INR0086 | Tejas Solar | Open Road Renewables | 5688 GeorgeWest 138kV | Live Oak | 2019-12-15 | Solar | 150 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0087 | Lavista Solar | Open Road Renewables | 65 Silver 69kV | Milam | 2019-12-15 | Solar | 60 |  | 2017-07-14 |  |  | No | n/a | n/a | No
19INR0101 | Tehuacana Wind | Pioneer Green | 46020 Limestone 345kV + 34mi gentie | Limestone | 2019-12-15 | Wind | 600 |  | 2017-08-11 |  |  | No | n/a | n/a | No
14INR0044 | West of Pecos Solar | Eon | 1094 Mason 138kV | Reeves | 2019-12-15 | Solar | 100 | Projected Date | 2013-02-19 | 2017-09-28 | 2017-02-27 | Yes | n/a | n/a | Yes
20INR0008 | Yellow Jacket Wind | RES Americas | tap 345kV 7046 Kendal - 60618 Edison | Menard | 2019-12-19 | Wind | 200.1 |  | 2017-03-09 |  |  | No | n/a | n/a | No
19INR0151 | GSE Twelve | Alpin Sun | tap 345kV 1695 Moses - 1692 Paris | Lamar | 2019-12-20 | Solar | 200 |  |  |  |  | No | n/a | n/a | No
19INR0152 | GSE Thirteen | Alpin Sun | tap 345kV 3380 Big Brown - 68091 Navarro | Freestone | 2019-12-20 | Solar | 135 |  | 2018-01-11 |  |  | No | n/a | n/a | No
19INR0128 | White Mesa Wind | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | 2019-12-23 | Wind | 500 |  | 2017-11-20 |  |  | No | n/a | n/a | No
19INR0156 | Grape Creek Wind | Apex Clean | tap 345kV 76009 TwinB - 76090 Divide | Coke | 2019-12-23 | Wind | 524.4 |  |  |  |  | No | n/a | n/a | No
19INR0114 | Rambler Solar | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | 2019-12-30 | Solar | 150 |  | 2017-10-10 |  |  | No | n/a | n/a | No
12INR0029 | Comanche Run Wind | Avangrid | 79501 Ogallala 345kV | Swisher | 2019-12-31 | Wind | 500 |  | 2009-05-28 |  | 2013-07-24 | No | n/a | n/a | No
17INR0020b | RE Maplewood 2b Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2019-12-31 | Solar | 100 |  | 2014-12-01 |  | 2016-02-03 | Yes | n/a | n/a | Yes
17INR0020c | RE Maplewood 2c Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2019-12-31 | Solar | 100 |  | 2014-12-01 |  | 2016-02-03 | Yes | n/a | n/a | Yes
14INR0009 | WKN Amadeus Wind | WKN | tap 345kV 11305 Dermott - 60704 Kirchhof | Kent | 2019-12-31 | Wind | 245.86 |  | 2011-03-18 |  |  | No | n/a | n/a | No
15INR0034 | El Algodon Alto W | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | 2019-12-31 | Wind | 201 |  | 2013-03-25 |  |  | No | n/a | n/a | No
15INR0044 | Corazon Solar | Enerverse | 80219 Lobo 345kV | Webb | 2019-12-31 | Solar | 200 |  | 2013-09-16 |  |  | No | n/a | n/a | No
16INR0061 | WIT Ranch Wind | Eon | tap 345kV 60500 Edith Clarke- 60501 Tesla | Hardeman | 2019-12-31 | Wind | 200 |  | 2014-11-14 |  |  | No | n/a | n/a | No
16INR0119 | Wake Solar | Invenergy | 59904 Cottonwood 345kV | Crosby | 2019-12-31 | Solar | 150 |  | 2015-07-27 |  |  | No | n/a | n/a | No
17INR0030 | Estacado Solar | Avangrid | 79502 Windmill 345kV | Deaf Smith | 2019-12-31 | Solar | 100 |  | 2015-06-01 |  |  | No | n/a | n/a | No
17INR0031 | Espiritu Wind | Apex Clean | 5764 E Rio Hondo 138kV | Cameron | 2019-12-31 | Wind | 148.5 |  | 2015-06-22 |  |  | No | n/a | n/a | No
17INR0038 | Zapata II W | Nextera | 80220 Cenizo 345kV | Zapata | 2019-12-31 | Wind | 400 |  | 2016-02-15 |  |  | No | n/a | n/a | No
18INR0022 | RES Wink Solar | RES Americas | tap 138kV 1009 Yucca - 1146 Notrees | Winkler | 2019-12-31 | Solar | 150 |  | 2016-03-01 | 2017-07-31 |  | No | n/a | n/a | No
18INR0034 | Blanco Canyon Wind | Invenergy | 59904 Cottonwood 345kV | Crosby | 2019-12-31 | Wind | 250.7 |  | 2016-09-14 |  |  | No | n/a | n/a | No
18INR0044 | Bluegrove Wind | Alterra Power | tap 138kV 1468 LKAROWHD - 1470 NEWPRT_P | Clay | 2019-12-31 | Wind | 100 |  | 2016-12-06 |  |  | No | n/a | n/a | No
18INR0049 | Santa Rita Solar | Invenergy | 76005 Schneeman Draw 345kV | Crockett | 2019-12-31 | Solar | 400 |  | 2016-12-19 |  |  | No | n/a | n/a | No
18INR0051 | Byers Wind | Alterra Power | tap 345kV 6101 Riley - 1730 W Krum | Clay | 2019-12-31 | Wind | 200 |  | 2016-12-15 |  |  | No | n/a | n/a | No
18INR0066 | Winkler Solar | RES Americas | tap 138kV 1009 Yucca - 1146 Notrees | Winkler | 2019-12-31 | Solar | 40 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0014 | Formosa Increase | Formosa Plastics |  | Calhoun | 2019-12-31 | Gas | 240 |  | 2016-11-14 |  |  | No | No | No | No
19INR0022 | West Willacy 2 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | 2019-12-31 | Wind | 200 |  | 2017-01-10 |  |  | No | n/a | n/a | No
19INR0023 | West Willacy 3 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | 2019-12-31 | Wind | 200 |  | 2017-01-10 |  |  | No | n/a | n/a | No
19INR0048 | Willacy Exp West I W | Terra-Gen | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-05-03 |  |  | No | n/a | n/a | No
19INR0049 | Willacy Exp West II W | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-05-03 |  |  | No | n/a | n/a | No
19INR0054 | Monte Cristo 1 W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-05-03 |  |  | No | n/a | n/a | No
19INR0055 | Monte Cristo II W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-05-03 |  |  | No | n/a | n/a | No
19INR0074 | Karankawa 2 Wind Farm | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | 2019-12-31 | Wind | 200 |  | 2017-06-23 |  |  | No | n/a | n/a | No
19INR0081 | Anson Solar | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | 2019-12-31 | Solar | 500 |  | 2017-08-07 |  |  | No | n/a | n/a | No
19INR0088 | Aragorn Solar | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | 2019-12-31 | Solar | 186.3 |  | 2017-07-21 |  |  | No | n/a | n/a | No
19INR0090 | SF Bug Ranch S | Chermac | 79500 Alibates 345kV | Carson | 2019-12-31 | Solar | 200 |  | 2017-07-17 |  |  | No | n/a | n/a | No
19INR0103 | Rodeo Solar | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | 2019-12-31 | Solar | 200 |  | 2017-08-04 |  |  | No | n/a | n/a | No
19INR0105 | Concho Valley Solar | Merit SI | tap 138kV 6480 SAPS - 6490 Santiago | Tom Green | 2019-12-31 | Solar | 150 |  | 2017-08-17 |  |  | No | n/a | n/a | No
19INR0106 | Las Palmas Wind | Eon | tap 345kV 8383 NEdinb - 8318 Rio Hondo, ~10.5 mi from RH new sub Bonilla + 18 mi gentie | Willacy | 2019-12-31 | Wind | 201 |  | 2017-09-13 |  |  | No | n/a | n/a | No
19INR0108 | Hardeman Wind | Eon | 6050 Lake Pauline 138kV | Hardeman | 2019-12-31 | Wind | 200.2 |  | 2017-10-10 |  |  | No |  |  | No
19INR0112 | Cranel Wind | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | 2019-12-31 | Wind | 201 |  | 2017-11-01 |  |  | No | n/a | n/a | No
19INR0115 | Blackwater Draw Solar | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | 2019-12-31 | Solar | 150 |  | 2017-10-09 |  |  | No | n/a | n/a | No
19INR0127 | EK Ilanga | Energie Kontor | 38430 Whitebaker 138kV | Pecos | 2019-12-31 | Solar | 100 |  | 2017-12-11 |  |  | No | n/a | n/a | No
19INR0132 | Los Porciones I | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-11-13 |  |  | No | n/a | n/a | No
19INR0133 | Los Porciones II | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | 2019-12-31 | Wind | 200 |  | 2017-11-13 |  |  | No | n/a | n/a | No
19INR0147 | Bald Eagle Creek Solar | Eon | tap 345kV 76009 TwinB - 1444 Brown | Tom Green | 2019-12-31 | Solar | 200 |  | 2018-01-08 |  |  | No | n/a | n/a | No
17INR0037 | Palmas Altas Wind | Acciona | 5764 E Rio Hondo 138kV + 8mi radial | Cameron | 2019-12-31 | Wind | 144.9 | NEW | 2016-05-06 |  | 2017-11-30 | No | n/a | n/a | No
18INR0014 | Karankawa Wind Alt A | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | 2019-12-31 | Wind | 200 | NEW | 2015-11-11 |  | 2017-11-30 | No | n/a | n/a | No
16INR0117 | Tecovas 1 W | Infinity Wind | 79503 Tule Canyon 345kV | Briscoe | 2020-01-01 | Wind | 200.1 |  | 2015-07-06 |  |  | No | n/a | n/a | No
20INR0044 | French Goldston Solar | Belltown Power | tap 138kV 1431 Graham - 1477 Rice OR 1596 Graham 138kV | Young | 2020-02-01 | Solar | 120 |  |  |  |  | No | n/a | n/a | No
20INR0003 | Shorthorn Solar | 8minutenergy | 60501 Tesla 345kV | Childress | 2020-03-01 | Solar | 200 |  | 2016-08-04 |  |  | No | n/a | n/a | No
20INR0026 | Longbow Solar | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | 2020-03-01 | Solar | 105 |  | 2017-10-13 |  |  | No | n/a | n/a | No
20INR0027 | Lavaca Wind | Acciona | 8126 Formosa 138kV OR 8140 Joslin 138kV | Calhoun | 2020-03-01 | Wind | 151.2 |  | 2017-10-25 |  |  | No | n/a | n/a | No
20INR0031 | Rippey Solar | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | 2020-03-01 | Solar | 50 |  | 2017-11-13 |  |  | No | n/a | n/a | No
20INR0037 | Coniglio Solar | Belltown Power | 1809 Boistret 138kV | Fannin | 2020-03-01 | Solar | 135 |  |  |  |  | No | n/a | n/a | No
16INR0006 | Pinecrest G | Coronado Ventures | 3117 Lufkin 345kV | Angelina | 2020-04-12 | Gas | 785 |  | 2012-12-06 |  | 2015-02-09 | No | Yes | Yes | No
19INR0034 | Greasewood Solar | OnPeak Power | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | 2020-04-30 | Solar | 200 |  | 2017-04-17 |  |  | No | n/a | n/a | No
20INR0043 | Gulf Wind 2 |  |  | Kenedy | 2020-05-01 | Wind | 180 |  |  |  |  | No | n/a | n/a | No
20INR0020 | Pumpkin Farm Solar | Apex Clean | 79505 White River 345kV | Floyd | 2020-05-30 | Solar | 400 |  | 2017-10-05 |  |  | No | n/a | n/a | No
19INR0030 | San Bernard Solar | Sunchase Power | 43340 Tx Gulf Sulphur 138kV | Wharton | 2020-06-01 | Solar | 100 |  | 2017-04-12 |  |  | No | n/a | n/a | No
20INR0002 | Lake Spring Solar | 8minutenergy | 79501 Ogallala 345kV | Castro | 2020-06-01 | Solar | 400 |  | 2016-08-04 |  |  | No | n/a | n/a | No
20INR0030 | Rustler Solar | Cypress Creek Renewables | tap 138kV 5827 Moore - 5895 Pearsall | Frio | 2020-06-30 | Solar | 113 |  | 2017-11-13 |  |  | No | n/a | n/a | No
20INR0019 | Trinity Hills Wind repowering | BP | 150751 & 150752 Trinity Hills 34.5kV | Young | 2020-07-01 | Wind | 198 |  | 2017-09-08 |  |  | No | n/a | n/a | No
20INR0021 | IS 341 | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | 2020-07-01 | Solar | 20 |  | 2017-10-10 |  |  | No | n/a | n/a | No
20INR0024 | IS 177 | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | 2020-07-01 | Solar | 25 |  | 2017-10-22 |  |  | No | n/a | n/a | No
20INR0042 | Palmas Altas Wind 2 | Cielo | 5764 E Rio Hondo 138kV | Cameron | 2020-07-01 | Wind | 144.9 |  |  |  |  | No | n/a | n/a | No
20INR0012 | Lueders Solar | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | 2020-08-01 | Solar | 40 |  | 2017-08-28 |  |  | No | n/a | n/a | No
20INR0013 | Basalt Solar | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | 2020-08-01 | Solar | 20 |  | 2017-09-01 |  |  | No | n/a | n/a | No
20INR0014 | Obsidian Solar | Innovative Solar | 6131 Padr 69kV | Cottle | 2020-08-01 | Solar | 60 |  | 2017-08-28 |  |  | No | n/a | n/a | No
20INR0015 | Citrine Solar | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | 2020-08-01 | Solar | 45 |  | 2017-08-28 |  |  | No | n/a | n/a | No
20INR0016 | Opal Solar | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | 2020-08-01 | Solar | 45 |  | 2017-08-28 |  |  | No | n/a | n/a | No
20INR0022 | Sandine Solar | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | 2020-08-01 | Solar | 30 |  | 2017-10-22 |  |  | No | n/a | n/a | No
20INR0023 | Agate Solar | Innovative Solar | 1906 Venus S 345kV | Ellis | 2020-08-01 | Solar | 60 |  | 2017-10-18 |  |  | No | n/a | n/a | No
20INR0025 | Spinel Solar | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | 2020-08-01 | Solar | 30 |  | 2017-10-09 |  |  | No | n/a | n/a | No
20INR0035 | Angus Solar | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | 2020-08-31 | Solar | 188 |  | 2018-01-02 |  |  | No | n/a | n/a | No
20INR0036 | Stillwater Solar | Cypress Creek Renewables | tap 345kV 8455 LONHILL - 8955 NEDIN | Nueces | 2020-08-31 | Solar | 216 |  |  |  |  | No | n/a | n/a | No
19INR0099b | Kontiki Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2020-09-01 | Wind | 255.3 |  | 2017-08-04 |  |  | No | n/a | n/a | No
20INR0005 | Shorthorn 2 Solar | 8minutenergy | 60501 Tesla 345kV | Childress | 2020-10-01 | Solar | 200 |  | 2016-11-14 |  |  | No | n/a | n/a | No
20INR0045 | Maverick Creek I |  |  | Concho | 2020-10-01 | Wind | 252 |  |  |  |  | No | n/a | n/a | No
20INR0046 | Maverick Creek II |  |  | Concho | 2020-10-01 | Wind | 252 |  |  |  |  | No | n/a | n/a | No
15INR0063b | Easter Wind B | TriGlobal | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | 2020-10-31 | Wind | 152.5 |  | 2014-02-27 | 2017-12-06 |  | No | n/a | n/a | No
20INR0017 | Cooke Wind | EDP Renewables | 685 Leo 138kV | Cooke | 2020-10-31 | Wind | 152 |  | 2017-09-01 |  |  | No | n/a | n/a | No
20INR0018 | Hamilton Wind | EDP Renewables | 258 Hamilton 69kV | Hamilton | 2020-10-31 | Wind | 101 |  | 2017-09-01 |  |  | No | n/a | n/a | No
20INR0033 | Cooke Wind Farm II | EDP Renewables | tap 345kV 1730 KrumW - 2373 Anna | Cooke | 2020-10-31 | Wind | 152 |  | 2017-12-11 |  |  | No | n/a | n/a | No
20INR0034 | Cargil Solar | Cypress Creek Renewables | tap 69kV 8231 Uvalde - 8672 LaPryor | Zavala | 2020-10-31 | Solar | 65 |  | 2017-12-28 |  |  | No | n/a | n/a | No
20INR0034_ES | Cargil Solar batt | Cypress Creek Renewables | tap 69kV 8231 Uvalde - 8672 LaPryor | Zavala | 2020-10-31 | Storage | 30 |  | 2017-12-28 |  |  | No |  |  | No
15INR0013 | Bethel CAES | Apex CAES | tap 345kV 3380 Big Brown - 3133 Richland Chambers | Anderson | 2020-11-27 | Gas | 324 | Fuel | 2011-12-15 |  | 2015-06-25 | No | Yes | Yes | No
14INR0030c | Panhandle Wind 3 | Pattern Energy | 79005 Railhead 345kV | Carson | 2020-12-01 | Wind | 248 |  | 2012-08-17 |  | 2014-08-25 | Yes | n/a | n/a | Yes
18INR0005 | Panda Sherman 2 G | Panda Funds | 1758 Payne 138kV | Grayson | 2020-12-01 | Gas | 496 |  | 2015-04-01 |  |  | No | No | Yes | No
20INR0028 | Fossil Ridge | Clenera | 1730 W Krum 345kV | Denton | 2020-12-01 | Solar | 300 |  | 2017-10-27 |  |  | No | n/a | n/a | No
20INR0029 | JA Ranch | EDF Renewables | tap 345kV 6101 Riley - 1730 W Krum | Clay | 2020-12-01 | Wind | 202 |  | 2017-11-07 |  |  | No | n/a | n/a | No
19INR0096 | Shamrock Wind | Eon | 76005 Schneeman Draw 345kV | Crockett | 2020-12-15 | Wind | 201.6 |  | 2017-09-13 |  |  | No | n/a | n/a | No
19INR0097 | Shamrock Wind II | Eon | 76005 Schneeman Draw 345kV | Crockett | 2020-12-15 | Wind | 201.6 |  | 2017-09-13 |  |  | No | n/a | n/a | No
16INR0005 | Brownsville G | Tenaska | Tap 345kV 5966 Palmito - 80137 Stewart | Cameron | 2020-12-31 | Gas | 871 |  | 2012-08-08 |  | 2015-06-15 | No | Yes | No | No
17INR0020d | RE Maplewood 2d Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2020-12-31 | Solar | 100 |  | 2014-12-01 |  | 2016-02-03 | Yes | n/a | n/a | Yes
17INR0020e | RE Maplewood 2e Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2020-12-31 | Solar | 100 |  | 2014-12-01 |  | 2016-02-03 | Yes | n/a | n/a | Yes
15INR0062 | Hale Community W 1 | Nextera | 79506 Abernathy 345kV | Hale | 2020-12-31 | Wind | 301 |  | 2014-01-27 |  |  | No | n/a | n/a | No
15INR0062b | Hale Community W 2 | Nextera | 79506 Abernathy 345kV | Hale | 2020-12-31 | Wind | 122 |  | 2014-01-27 |  |  | No | n/a | n/a | No
16INR0033 | Hart Wind | Orion | 79501 Ogallala 345kV | Castro | 2020-12-31 | Wind | 150 |  | 2014-03-20 |  |  | No | n/a | n/a | No
16INR0085 | Priddy Wind | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | 2020-12-31 | Wind | 300 |  | 2015-02-10 |  |  | No | n/a | n/a | No
16INR0099 | Hecate Solar | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | 2020-12-31 | Solar | 50 |  | 2015-05-14 |  |  | No | n/a | n/a | No
16INR0101 | Hecate Sun Valley 57 | Hecate Energy | 6641 Sun Valley 69kV | Pecos | 2020-12-31 | Solar | 57 |  | 2015-05-14 |  |  | No | n/a | n/a | No
16INR0106 | Andrews County Solar | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | 2020-12-31 | Solar | 150 |  | 2015-05-26 |  |  | No | n/a | n/a | No
17INR0043 | Vaquero Option 2 W | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Brooks | 2020-12-31 | Wind | 400 |  | 2016-05-10 |  |  | No | n/a | n/a | No
19INR0117 | Road Runner Crossing Wind 1 | Eon | tap 345kV 68005 WShack - 68050 Romney OR 345kV 68006 WShack - 68010 Romney | Eastland | 2020-12-31 | Wind | 201 |  | 2017-11-07 |  |  | No | n/a | n/a | No
20INR0032 | IP Titan | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | 2020-12-31 | Solar | 226.8 |  | 2017-12-08 |  |  | No | n/a | n/a | No
20INR0038 | Red Mud Creek | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | 2020-12-31 | Wind | 201 |  |  |  |  | No | n/a | n/a | No
20INR0039 | Red Mud Creek II | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | 2020-12-31 | Wind | 102 |  |  |  |  | No | n/a | n/a | No
20INR0040 | Montgomery Ranch Wind | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | 2020-12-31 | Wind | 200.2 |  |  |  |  | No | n/a | n/a | No
20INR0041 | Watusi Solar | Cypress Creek Renewables | tap 69kV 6363 Yellowjacket - 60386 Heartland | Menard | 2020-12-31 | Solar | 195 |  |  |  |  | No | n/a | n/a | No
21INR0004 | Hutt Wind I | Pioneer Natural Resources | tap 138kV 71210 LSkywest - 1210 Midkiff OR 138kV 1226 Aruba - 1329 Sprayberry | Midland | 2021-01-01 | Wind | 204 |  | 2017-11-10 |  |  | No | n/a | n/a | No
21INR0005 | Hutt Wind II | Pioneer Natural Resources | tap 345kV 11028 Odessa - 59901 Grelton OR 345kV 11016 Quail - 19000 Longshorefly | Midland | 2021-01-01 | Wind | 306 |  | 2017-11-10 |  |  | No | n/a | n/a | No
21INR0006 | Giddings Wind | Pioneer Natural Resources | 71212 Upton 138kV | Upton | 2021-01-01 | Wind | 204 |  | 2017-11-10 |  |  | No | n/a | n/a | No
08INR0019b | Grandview 5 W | Eon | 79005 Railhead 345kV | Gray | 2021-03-01 | Wind | 250 |  | 2006-10-02 |  |  | No | n/a | n/a | No
21INR0007 | Deepwater | AES | 40450 Deepwater 345kV | Harris | 2021-04-30 | Gas | 462.2 |  |  |  |  | No | No | No | No
21INR0002 | Hariana Solar | 8minutenergy | 6110 East Munday 138kV | Knox | 2021-06-01 | Solar | 200 |  | 2017-02-06 |  |  | No | n/a | n/a | No
17INR0013 | Site C Brazos G | Brazos Elec Coop | tap one 345kV Venus - 68090 Sam Switch ckt | Hill | 2021-08-01 | Gas | 800 |  | 2014-06-30 |  |  | No | Yes | No | No
19INR0118 | Road Runner Crossing Wind 2 | Eon | tap 345kV 68005 WShack - 68050 Romney OR 345kV 86005 WShack - 68010 Romney | Eastland | 2021-12-31 | Wind | 102 |  | 2017-11-07 |  |  | No | n/a | n/a | No
20INR0009 | Mariah Del Sur 2 | Mariah Acquisition | 141765 Mariah 345kV | Parmer | 2023-12-31 | Wind | 350 |  | 2017-11-07 |  |  | No | n/a | n/a | No

## GINR Trends
GINR Trends, 36 Months: December 2014 through December 2017
|  |  |  | Project Count | [13 empty] | Capacity (GW)
|  |  |  | GINR milestones | [6 empty] | Fuel Type | [6 empty] | GINR Project milestones | [6 empty] | Fuel Type
| Year | Month | Project Total Count | SSS Underway | SSS Completed | FIS Underway | FIS Completed | Signed IA | Part 1 | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Other | SSS Underway | SSS Completed | FIS Underway | FIS Completed | Signed IA | Part 1 | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Other
| 2014 | Dec | 250 | 2 | 20 | 150 | 10 | 70 | 5 | 5 | 120 | 35 | 150 | 0 | 0 | 0 | 0 | 0.38168 | 3.8168 | 28.626 | 1.9084 | 13.3588 | 0.9542 | 0.9542 | 19.6721 | 5.7377 | 24.5902 | 0 | 0 | 0 | 0
| 2015 | Jan | 253 | 2.2353 | 21.6 | 143 | 10.1429 | 71.5714 | 6 | 7 | 121.1429 | 38 | 147.1429 | 0 | 0 | 0 | 0 | 0.43184 | 4.173 | 27.6265 | 1.9595 | 13.8271 | 1.1592 | 1.3523 | 19.9855 | 6.269 | 24.2749 | 0 | 0 | 0 | 0
| 2015 | Feb | 256 | 2.4706 | 23.2 | 147 | 10.2857 | 73.1429 | 3 | 5 | 122.2857 | 41 | 144.2857 | 0 | 0 | 0 | 0 | 0.47764 | 4.4853 | 28.4198 | 1.9886 | 14.1409 | 0.58 | 0.96666 | 20.3002 | 6.8063 | 23.9524 | 0 | 0 | 0 | 0
| 2015 | Mar | 252 | 2.7059 | 24.8 | 158 | 10.4286 | 74.7143 | 7 | 4 | 123.4286 | 44 | 141.4286 | 0 | 0 | 0 | 0 | 0.49562 | 4.5425 | 28.9401 | 1.9102 | 13.6851 | 1.2822 | 0.73266 | 20.6162 | 7.3493 | 23.6227 | 0 | 0 | 0 | 0
| 2015 | Apr | 269 | 2.9412 | 26.4 | 145 | 10.5714 | 76.2857 | 3 | 3 | 124.5714 | 47 | 138.5714 | 0 | 0 | 0 | 0 | 0.57368 | 5.1494 | 28.2826 | 2.062 | 14.8797 | 0.58516 | 0.58516 | 20.9335 | 7.8981 | 23.2861 | 0 | 0 | 0 | 0
| 2015 | May | 269 | 3.1765 | 28 | 140 | 10.7143 | 77.8571 | 7 | 4 | 125.7143 | 50 | 135.7143 | 0 | 0 | 0 | 0 | 0.61767 | 5.4446 | 27.2231 | 2.0834 | 15.1394 | 1.3612 | 0.7778 | 21.252 | 8.4525 | 22.9425 | 0 | 0 | 0 | 0
| 2015 | Jun | 252 | 3.4118 | 29.6 | 148 | 10.8571 | 79.4286 | 6 | 4 | 126.8571 | 53 | 132.8571 | 0 | 0 | 0 | 0 | 0.64496 | 5.5956 | 27.9779 | 2.0524 | 15.0152 | 1.1342 | 0.75616 | 21.5718 | 9.0125 | 22.5921 | 0 | 0 | 0 | 0
| 2015 | Jul | 255 | 3.6471 | 31.2 | 145 | 11 | 81 | 3 | 3 | 128 | 56 | 130 | 0 | 0 | 0 | 0 | 0.70495 | 6.0307 | 28.0275 | 2.1262 | 15.6567 | 0.57988 | 0.57988 | 21.8928 | 9.5781 | 22.2349 | 0 | 0 | 0 | 0
| 2015 | Aug | 266 | 3.8824 | 32.8 | 149 | 11.1429 | 82.5714 | 6 | 6 | 129.1429 | 59 | 127.1429 | 0 | 0 | 0 | 0 | 0.72259 | 6.1048 | 27.7322 | 2.0739 | 15.3684 | 1.1167 | 1.1167 | 22.2151 | 10.1492 | 21.8711 | 0 | 0 | 0 | 0
| 2015 | Sep | 256 | 4.1176 | 34.4 | 160 | 11.2857 | 84.1429 | 5 | 8 | 130.2857 | 62 | 124.2857 | 0 | 0 | 0 | 0 | 0.73466 | 6.1376 | 28.5469 | 2.0136 | 15.0126 | 0.89209 | 1.4273 | 22.5385 | 10.7256 | 21.5006 | 0 | 0 | 0 | 0
| 2015 | Oct | 258 | 4.3529 | 36 | 147 | 11.4286 | 85.7143 | 7 | 3 | 131.4286 | 65 | 121.4286 | 0 | 0 | 0 | 0 | 0.8173 | 6.7593 | 27.6005 | 2.1458 | 16.0936 | 1.3143 | 0.56328 | 22.8632 | 11.3073 | 21.1236 | 0 | 0 | 0 | 0
| 2015 | Nov | 268 | 4.5882 | 37.6 | 159 | 11.5714 | 87.2857 | 6 | 3 | 132.5714 | 68 | 118.5714 | 0 | 0 | 0 | 0 | 0.82878 | 6.7918 | 28.7205 | 2.0902 | 15.7666 | 1.0838 | 0.5419 | 23.189 | 11.8944 | 20.7402 | 0 | 0 | 0 | 0
| 2015 | Dec | 257 | 4.8235 | 39.2 | 156 | 11.7143 | 88.8571 | 5 | 3 | 133.7143 | 71 | 115.7143 | 0 | 0 | 0 | 0 | 0.88083 | 7.1584 | 28.4874 | 2.1392 | 16.2263 | 0.91306 | 0.54783 | 23.516 | 12.4866 | 20.3504 | 0 | 0 | 0 | 0
| 2016 | Jan | 259 | 5.0588 | 40.8 | 148 | 11.8571 | 90.4286 | 6 | 7 | 134.8571 | 74 | 112.8571 | 0 | 0 | 0 | 0 | 0.93082 | 7.5072 | 27.2319 | 2.1817 | 16.6388 | 1.104 | 1.288 | 23.8441 | 13.084 | 19.9543 | 0 | 0 | 0 | 0
| 2016 | Feb | 267 | 5.2941 | 42.4 | 151 | 12 | 92 | 3 | 3 | 136 | 77 | 110 | 0 | 0 | 0 | 0 | 0.98461 | 7.8857 | 28.0834 | 2.2318 | 17.1104 | 0.55795 | 0.55795 | 24.1734 | 13.6864 | 19.552 | 0 | 0 | 0 | 0
| 2016 | Mar | 253 | 5.5294 | 44 | 153 | 12.1429 | 93.5714 | 7 | 7 | 137.1429 | 80 | 107.1429 | 0 | 0 | 0 | 0 | 0.99422 | 7.9114 | 27.5102 | 2.1834 | 16.8247 | 1.2586 | 1.2586 | 24.5038 | 14.2939 | 19.1436 | 0 | 0 | 0 | 0
| 2016 | Apr | 257 | 5.7647 | 45.6 | 153 | 12.2857 | 95.1429 | 5 | 6 | 138.2857 | 83 | 104.2857 | 0 | 0 | 0 | 0 | 1.0442 | 8.26 | 27.7143 | 2.2254 | 17.2341 | 0.9057 | 1.0868 | 24.8352 | 14.9063 | 18.7291 | 0 | 0 | 0 | 0
| 2016 | May | 254 | 6 | 47.2 | 145 | 12.4286 | 96.7143 | 3 | 4 | 139.4286 | 86 | 101.4286 | 0 | 0 | 0 | 0 | 1.1262 | 8.8591 | 27.2155 | 2.3328 | 18.1526 | 0.56308 | 0.75077 | 25.1678 | 15.5236 | 18.3086 | 0 | 0 | 0 | 0
| 2016 | Jun | 270 | 6.2353 | 48.8 | 147 | 12.5714 | 98.2857 | 6 | 8 | 140.5714 | 89 | 98.5714 | 0 | 0 | 0 | 0 | 1.1355 | 8.8868 | 26.7697 | 2.2893 | 17.8985 | 1.0926 | 1.4569 | 25.5015 | 16.1458 | 17.8821 | 0 | 0 | 0 | 0
| 2016 | Jul | 259 | 6.4706 | 50.4 | 159 | 12.7143 | 99.8571 | 5 | 5 | 141.7143 | 92 | 95.7143 | 0 | 0 | 0 | 0 | 1.1482 | 8.9438 | 28.2156 | 2.2562 | 17.7203 | 0.88728 | 0.88728 | 25.8362 | 16.7727 | 17.4499 | 0 | 0 | 0 | 0
| 2016 | Aug | 263 | 6.7059 | 52 | 144 | 12.8571 | 101.4286 | 7 | 5 | 142.8571 | 95 | 92.8571 | 0 | 0 | 0 | 0 | 1.235 | 9.5765 | 26.5195 | 2.3678 | 18.6794 | 1.2891 | 0.92082 | 26.172 | 17.4044 | 17.0118 | 0 | 0 | 0 | 0
| 2016 | Sep | 253 | 6.9412 | 53.6 | 158 | 13 | 103 | 4 | 7 | 144 | 98 | 90 | 0 | 0 | 0 | 0 | 1.2277 | 9.4805 | 27.9463 | 2.2994 | 18.2181 | 0.7075 | 1.2381 | 26.5089 | 18.0408 | 16.568 | 0 | 0 | 0 | 0
| 2016 | Oct | 268 | 7.1765 | 55.2 | 143 | 13.1429 | 104.5714 | 7 | 4 | 145.1429 | 101 | 87.1429 | 0 | 0 | 0 | 0 | 1.3242 | 10.1856 | 26.3866 | 2.4251 | 19.2957 | 1.2917 | 0.73809 | 26.8467 | 18.6817 | 16.1186 | 0 | 0 | 0 | 0
| 2016 | Nov | 250 | 7.4118 | 56.8 | 142 | 13.2857 | 106.1429 | 4 | 7 | 146.2857 | 104 | 84.2857 | 0 | 0 | 0 | 0 | 1.3689 | 10.4908 | 26.227 | 2.4538 | 19.6043 | 0.73879 | 1.2929 | 27.1856 | 19.3273 | 15.6636 | 0 | 0 | 0 | 0
| 2016 | Dec | 285 | 7.6471 | 58.4 | 155 | 13.4286 | 107.7143 | 5 | 4 | 147.4286 | 107 | 81.4286 | 0 | 0 | 0 | 0 | 1.3654 | 10.4275 | 27.6757 | 2.3977 | 19.2327 | 0.89276 | 0.71421 | 27.5255 | 19.9773 | 15.203 | 0 | 0 | 0 | 0
| 2017 | Jan | 269 | 7.8824 | 60 | 152 | 13.5714 | 109.2857 | 4 | 4 | 148.5714 | 110 | 78.5714 | 0 | 0 | 0 | 0 | 1.4211 | 10.8175 | 27.4043 | 2.4468 | 19.7033 | 0.72117 | 0.72117 | 27.8664 | 20.6319 | 14.737 | 0 | 0 | 0 | 0
| 2017 | Feb | 312 | 8.1176 | 61.6 | 156 | 13.7143 | 110.8571 | 6 | 3 | 149.7143 | 113 | 75.7143 | 0 | 0 | 0 | 0 | 1.4407 | 10.9324 | 27.686 | 2.4339 | 19.6743 | 1.0648 | 0.53242 | 28.2083 | 21.2908 | 14.2656 | 0 | 0 | 0 | 0
| 2017 | Mar | 312 | 8.3529 | 63.2 | 151 | 13.8571 | 112.4286 | 4 | 5 | 150.8571 | 116 | 72.8571 | 0 | 0 | 0 | 0 | 1.5008 | 11.3554 | 27.1307 | 2.4898 | 20.2004 | 0.71869 | 0.89837 | 28.5511 | 21.9541 | 13.7889 | 0 | 0 | 0 | 0
| 2017 | Apr | 320 | 8.5882 | 64.8 | 158 | 14 | 114 | 7 | 8 | 152 | 119 | 70 | 0 | 0 | 0 | 0 | 1.487 | 11.2198 | 27.3569 | 2.424 | 19.7386 | 1.212 | 1.3852 | 28.8949 | 22.6217 | 13.3069 | 0 | 0 | 0 | 0
| 2017 | May | 330 | 8.8235 | 66.4 | 159 | 14.1429 | 115.5714 | 3 | 7 | 153.1429 | 122 | 67.1429 | 0 | 0 | 0 | 0 | 1.5421 | 11.6047 | 27.7884 | 2.4717 | 20.1984 | 0.52431 | 1.2234 | 29.2397 | 23.2936 | 12.8197 | 0 | 0 | 0 | 0
| 2017 | Jun | 315 | 9.0588 | 68 | 140 | 14.2857 | 117.1429 | 7 | 7 | 154.2857 | 125 | 64.2857 | 0 | 0 | 0 | 0 | 1.6464 | 12.3591 | 25.4451 | 2.5964 | 21.2908 | 1.2723 | 1.2723 | 29.5854 | 23.9697 | 12.3273 | 0 | 0 | 0 | 0
| 2017 | Jul | 339 | 9.2941 | 69.6 | 142 | 14.4286 | 118.7143 | 6 | 4 | 155.4286 | 128 | 61.4286 | 0 | 0 | 0 | 0 | 1.6955 | 12.6972 | 25.9053 | 2.6322 | 21.6572 | 1.0946 | 0.72973 | 29.9321 | 24.6499 | 11.8298 | 0 | 0 | 0 | 0
| 2017 | Aug | 295 | 9.5294 | 71.2 | 159 | 14.5714 | 120.2857 | 4 | 8 | 156.5714 | 131 | 58.5714 | 0 | 0 | 0 | 0 | 1.6501 | 12.329 | 27.5324 | 2.5232 | 20.8286 | 0.69264 | 1.3853 | 30.2796 | 25.3343 | 11.3272 | 0 | 0 | 0 | 0
| 2017 | Sep | 294 | 9.7647 | 72.8 | 146 | 14.7143 | 121.8571 | 5 | 7 | 157.7143 | 134 | 55.7143 | 0 | 0 | 0 | 0 | 1.7469 | 13.0241 | 26.1198 | 2.6324 | 21.8005 | 0.89451 | 1.2523 | 30.6281 | 26.0228 | 10.8197 | 0 | 0 | 0 | 0
| 2017 | Oct | 330 | 10 | 74.4 | 143 | 14.8571 | 123.4286 | 6 | 4 | 158.8571 | 137 | 52.8571 | 0 | 0 | 0 | 0 | 1.81 | 13.4666 | 25.8833 | 2.6892 | 22.3409 | 1.086 | 0.72401 | 30.9775 | 26.7153 | 10.3073 | 0 | 0 | 0 | 0
| 2017 | Nov | 336 | 10.2353 | 76 | 149 | 15 | 125 | 7 | 3 | 160 | 140 | 50 | 0 | 0 | 0 | 0 | 1.8208 | 13.5196 | 26.5056 | 2.6683 | 22.2362 | 1.2452 | 0.53367 | 31.3277 | 27.4118 | 9.7899 | 0 | 0 | 0 | 0
| 2017 | Dec | 350 | 10 | 60 | 150 | 15 | 125 | 5 | 5 | 160 | 140 | 50 | 0 | 0 | 0 | 0 | 1.8378 | 11.027 | 27.5676 | 2.7568 | 22.973 | 0.91892 | 0.91892 | 31.0857 | 27.2 | 9.7143 | 0 | 0 | 0 | 0
Fuel
| CDR Zone | Year | Wind | Solar | Gas | Storage | Grand Total
| Coastal | 2018 | 253 | 0 | 96 | 0 | 349
|  | 2019 | 3700.7 | 620 | 447 | 0 | 4767.7
|  | 2020 | 4176.8 | 941 | 1318 | 0 | 6435.8
| Houston | 2018 | 0 | 0 | 796 | 0 | 796
|  | 2019 | 0 | 640 | 896 | 0 | 1536
|  | 2021 | 0 | 640 | 1358.2 | 0 | 1998.2
| West | 2017 | 1015.4 | 7.4 | 0 | 0 | 1022.8
|  | 2018 | 4427.8 | 1023 | 0 | 0 | 5450.8
|  | 2019 | 13396.46 | 11870 | 1703 | 0 | 26969.46
|  | 2020 | 15462.16 | 13288.8 | 1703 | 0 | 30453.96
|  | 2021 | 16176.16 | 13488.8 | 1703 | 0 | 31367.96
| North | 2018 | 200 | 0 | 225.8 | 0 | 425.8
|  | 2019 | 1152.8 | 2852.5 | 3422.8 | 0 | 7428.1
|  | 2020 | 2058.8 | 3585.5 | 5027.8 | 0 | 10672.1
|  | 2021 | 2160.8 | 3585.5 | 5827.8 | 0 | 11574.1
| Panhandle | 2018 | 1361.7 | 0 | 0 | 0 | 1361.7
|  | 2019 | 5586.9 | 1341.8 | 0 | 0 | 6928.7
|  | 2020 | 6760.5 | 2541.8 | 0 | 0 | 9302.3
|  | 2021 | 7010.5 | 2541.8 | 0 | 0 | 9552.3
|  | 2023 | 7360.5 | 2541.8 | 0 | 0 | 9902.3
| South | 2018 | 1147.6 | 0 | 100 | 0 | 1247.6
|  | 2019 | 4304.7 | 1833 | 3678.2 | 0 | 9815.9
|  | 2020 | 4704.7 | 2206 | 3678.2 | 30 | 10618.9