## Slide 1
Impact Analysis Template Revision
and
Impact Analysis Statistics
March 8, 2018

## Slide 2
Impact Analysis (IA) Recommendations
  IA Template Revisions
    ERCOT and Vendor Labor Cost Percentages
    Percentage of Cost by Impacted System
    Combining Sections
      “Alternatives for a More Efficient Implementation”
      “Evaluation of Interim Solutions”
    Removal of “Feasibility of Implementation”
Impact Analysis Statistics
  Cost Estimate Accuracy
  Duration Estimate Accuracy
  Estimated Time to Complete an Impact Analysis
Agenda

## Slide 3: Section 21 Impact Analysis Requirements – 21.4.6

## Slide 4: Impact Analysis Template Recommendations
l
l
l

## Slide 5: Impact Analysis Template Recommendations
l
l
l
Summary of Recommended IA Template Revisions
  Add ERCOT and vendor labor cost percentages
  Add percentage of cost by impacted system
  Combine “Evaluation of Interim Solutions” and “Alternatives for More Effective Implementation”
  Remove “Feasibility of Implementation”
    “Comments” field or separate Comments filing is used to communicate issues in this area

## Slide 6: IA Statistics – Cost Estimate Accuracy
Chart: 
| -$44,756 | -$15,669 | $0 | -$9,429 | -$22,356 | -$4,033 | -$90,557 | $0 | -$35,983 | $233,095 | $130,550 | -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | $15,244 | $24,331 | $25,807 | $40,571 | $57,644 | $60,967 | $119,443 | $153,152 | $189,017 | $533,095 | $840,550 | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | No | No | No | No | No | No | Yes | No | No | Yes, 2 change controls. Added scope | Yes, one change control. Two NPRRs removed from scope | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 5 - $500k to $1M | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | $15,000 | $20,000 | $10,000 | $25,000 | $10,000 | $30,000 | $90,000 | $60,000 | $50,000 | $50,000 | $230,000 | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $75,000 | $60,000 | $30,000 | $75,000 | $90,000 | $95,000 | $300,000 | $180,000 | $275,000 | $300,000 | $710,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $67,500 | $50,000 | $25,000 | $62,500 | $85,000 | $80,000 | $255,000 | $150,000 | $250,000 | $275,000 | $595,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $60,000 | $40,000 | $20,000 | $50,000 | $80,000 | $65,000 | $210,000 | $120,000 | $225,000 | $250,000 | $480,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | Market | Market | ERCOT | Market | Market | Market | Both | Both | ERCOT | Market | Both | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | NPRR500 | NPRR543 | NPRR680 | SCR775 | SCR772 | NPRR556 | NPRR698, NPRR595, NPRR706, NPRR710 | NPRR559, NPRR597, NPRR601, NPRR639, SCR778 | SCR779 | SCR756 | NPRR665, NPRR626, OBD, NPRR645 | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | Posting of Generation that is Off but Available | Message for Confirmed E-Tags | Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation | Posting Results of Real-Time Data in a Display Format | New Extract for Five Minute Interval Settlement Data | Resource Adequacy During Transmission Equipment Outage | Clarifications to NPRR595, RRS Load Resource Treatment In ORDC | 2014 CMM NPRRs and SCRs | Increase to the CRR Auction Transaction Limit | MarkeTrak Enhancements - Remaining SCR756 Items | Market System Enhancements 2015 | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | 151-01 | 152-01 | 178-01 | 160-01 | 126-01 | 176-01 | 149-02 | 154-01 | 138-01 | 010-03 | 149-01 | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017
Actual Variance from IA Estimate Range | -44756.07 | -15668.75 | 0 | -9429.49 | -22356.25 | -4033 | -90556.94 | 0 | -35982.81 | 233094.58 | 130549.98 | -11823.53 | -3391.34 | 49954.86 | -12318 | 0 | 0 | -70696.8 | 43734.23 | 72990.8 | 102533.38 | 104867.87 | -35000 | -36213 | -21105 | -11000.8 | 1119.97 | -5333 | 6568.52 | -5911.38 | -3242 | 11991.1 | 0 | 0 | -61130.26 | 59424.36 | 24677.15 | 0 | 108135



10
Exceeds IA Range
13 Projects
Below IA Range
19 Projects
Within IA Range
7 Projects
If actual spend falls within the IA range the variance is 0
Actual $ Variance from IA Range
2015
11 Projects
21 Revision Requests
2016
11 Projects
18 Revision Requests
2017
17 Projects
22 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
2
3
4
5
6
7
8
9
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
35
36
37
38
39

## Slide 7: IA Statistics – Duration Estimate Accuracy
Chart: 
| 1 | 2 | 3 | 4 | 5 | 7 | 10 | 12 | 15 | 20 | 25 | 29 | 30 | 33 | 34 | 36 | 38 | 39 | 40 | 43 | 45 | 51 | 52 | 53 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 66 | 67 | 75 | 76 | 78 | 87 | -$44,756 | -$15,669 | $0 | -$9,429 | -$22,356 | -$4,033 | -$90,557 | $0 | -$35,983 | $233,095 | $130,550 | -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | $15,244 | $24,331 | $25,807 | $40,571 | $57,644 | $60,967 | $119,443 | $153,152 | $189,017 | $533,095 | $840,550 | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | No | No | No | No | No | No | Yes | No | No | Yes, 2 change controls. Added scope | Yes, one change control. Two NPRRs removed from scope | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 5 - $500k to $1M | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | $15,000 | $20,000 | $10,000 | $25,000 | $10,000 | $30,000 | $90,000 | $60,000 | $50,000 | $50,000 | $230,000 | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $75,000 | $60,000 | $30,000 | $75,000 | $90,000 | $95,000 | $300,000 | $180,000 | $275,000 | $300,000 | $710,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $67,500 | $50,000 | $25,000 | $62,500 | $85,000 | $80,000 | $255,000 | $150,000 | $250,000 | $275,000 | $595,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $60,000 | $40,000 | $20,000 | $50,000 | $80,000 | $65,000 | $210,000 | $120,000 | $225,000 | $250,000 | $480,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | Market | Market | ERCOT | Market | Market | Market | Both | Both | ERCOT | Market | Both | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | NPRR500 | NPRR543 | NPRR680 | SCR775 | SCR772 | NPRR556 | NPRR698, NPRR595, NPRR706, NPRR710 | NPRR559, NPRR597, NPRR601, NPRR639, SCR778 | SCR779 | SCR756 | NPRR665, NPRR626, OBD, NPRR645 | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | Posting of Generation that is Off but Available | Message for Confirmed E-Tags | Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation | Posting Results of Real-Time Data in a Display Format | New Extract for Five Minute Interval Settlement Data | Resource Adequacy During Transmission Equipment Outage | Clarifications to NPRR595, RRS Load Resource Treatment In ORDC | 2014 CMM NPRRs and SCRs | Increase to the CRR Auction Transaction Limit | MarkeTrak Enhancements - Remaining SCR756 Items | Market System Enhancements 2015 | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | 151-01 | 152-01 | 178-01 | 160-01 | 126-01 | 176-01 | 149-02 | 154-01 | 138-01 | 010-03 | 149-01 | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017
Actual Variance from IA Duration Range | 0.83333 | 2.6667 | 0 | 4.3667 | 0 | 0 | 0 | 0 | 3.3667 | 2.8 | 0 | 0 | 0 | 0.33333 | 2.7667 | 0 | 0 | 0 | 0 | 3.6333 | 4.6 | 0 | 0 | 1.4333 | 0 | 0 | 2.4333 | 0 | 0 | 0.8 | 3.3667 | 0.46667 | 0 | 0 | 0.2 | 4.8 | 5 | 0 | 0
34
12
Exceeds IA Range
18 Projects
Below IA Range
0 Projects
Within IA Range
21 Projects
2015
11 Projects
21 Revision Requests
2016
11 Projects
18 Revision Requests
2017
17 Projects
22 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
Number of Months from IA Range
1
2
3
4
5
6
8
9
10
11
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
35
36
37
38
7
39

## Slide 8: Revision Request Project Legend
(E) ERCOT Sponsored
(M) Market Sponsored
(V) Various
NPRR500, Posting of Generation that is Off but Available, (M)
NPRR543, Message for Confirmed E-Tags, (M)
NPRR680, Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation, (E)
SCR775, Posting Results of Real-Time Data in a Display Format, (M)
SCR772, New Extract for Five Minute Interval Settlement Data, (M)
NPRR556, Resource Adequacy During Transmission Equipment Outage, (M)
NPRR698, NPRR595, NPRR706, NPRR710, Clarifications to NPRR595, RRS Load Resource Treatment In ORDC, (V)
NPRR559, NPRR597, NPRR601, NPRR639, SCR778, 2014 CMM NPRRs and SCRs, (V)
SCR779, Increase to the CRR Auction Transaction Limit, (E)
SCR756, MarkeTrak Enhancements - Remaining SCR756 Items, (M)
NPRR665, NPRR626, OBD, NPRR645, Market System Enhancements 2015, (V)
SCR788 Addition of Integral ACE Feedback to GTBD Calculation, (M)
NPRR754, Revise Load Distribution Factors Report Posting Frequency, (E)
NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge, (E)
SCR786, Retail Market Test Environment, (M)
NOGRR147, SCR787, NOGRR147 and SCR787 NDCRC Enhancement, (M)
NPRR662 Proxy Energy Offer Curves, (M)
NPRR770, NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor, (V)
NPRR617 and NPRR700 Implementation, (M)
NPRR515 Day-Ahead Market Self-Commitment of Generation Resources, (E)
NPRR588, NPRR615, NPRRs 588 and 615, (M)
NPRR219, SCR783, NOGRR050, 2015 Outage Scheduler Enhancements, (V)
NPRR785, Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts, (E)
NPRR808, Three Year CRR Auction, (M)
NPRR797 & NPRR789 Load Forecast Enhancements, (M)
NPRR649, Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides, (E)
SCR790, Wind Resource Power Production and Forecast Transparency, (M)
NPRR778, Modifications to Date Change and Cancellation Evaluation Window, (M)
RMGRR134, Allow AMS Data Submittal Process for TDSP – Read Non-Modeled Generators, (E)
NPRR764, QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80), (E)
NPRR782, Settlement of Infeasible Ancillary Services Due to Transmission Constraints, (E)
NPRR746, Adjustments Due to Negative Load, (E)
NPRR573, NPRR801, Implementation of NPRR573 & NPRR801, (E)
NPRR821, Inclusion of Private Use Networks in Load Zone Price Calculations, (E)
RRGRR003, RRGRR006, RRGRR007, RRGRR009, 2016 RARF Enhancements, (V)
RMGRR140, Mass Transition/Acquisition Enhancements (MTAQ), (M)
NPRR272, Definition and Participation of Quick Start Generation Resources, (E)
NPRR744, RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement, (E)
NPRR758, Improved Transparency for Outages Potentially having a High Economic Impact, (E)

## Slide 9: IA Statistics – Estimated Time To Complete an IA
At the November IA process overview, a question was asked about the time it takes ERCOT to develop an IA
We estimated the labor of internal ERCOT staff to develop several recent IAs
Results
Project Cost Estimate | Hours | Labor Cost
Small (<$100k) | 40 – 60 | $3k – $5k
Medium ($100k-$250k) | 60 – 120 | $5k – $10k
Large (>$250k) | >120 | >$10k
IA Preparation Effort

## Slide 10: Closing
Questions?
Comments?