## Slide 1: PLANNED TRANSMISSION OUTAGE PLANNING

## Slide 2
MOST MAJOR PLANNED TRANSMISSION OUTAGES ARE KNOWN MANY YEARS IN ADVANCE
  CONSTRUCTION OUTAGES
    WELL KNOWN AHEAD OF TIME
    MITIGATION COST COULD BE INCLUDED IN CCN
  ROUTINE MAINTENANCE
    MAINTENANCE MANAGEMENT SYSTEMS PROVIDE DATA NEEDED TO ANTICIPATE ROUTINE MAINTENANCE REQUIREMENTS FOR A DECADE OR MORE
    ROUTINE MAINTENANCE TYPICALLY HAS SIGNIFICANT SCHEDULE FLEXIBILITY
  MAINTENANCE DUE TO INSPECTION RESULTS
    COULD BE AN EMERGENCY
      STILL TAKES TIME TO EVALUATE OPTIONS AND ASSEMBLE RESOURCES
      QUICKLY MOVE FROM PLANNING TO SCHEDULING
    IF NOT AN EMERGENCY
      TYPICALLY MORE TIME IS TAKEN TO EVALUATE DATA AND REPAIR OPTIONS AND THEN FOLLOWED WITH EQUIPMENT SPECIFICATIONS/PURCHASING AND RESOURCE PLANNING
      THERE IS LIKELY SOME SCHEDULING FLEXIBILITY
  FORCED OUTAGE – IMMEDIATE ACTION – POSSIBLE PLANNING FOR LONG RANGE REPAIR

## Slide 3
INCLUDE AN ESTIMATE OF COST TO THE MARKET EARLY IN THE PLANNED OUTAGE PROCESS
  THIS IS A PLANNING PROCESS – NOT A SCHEDULING PROCESS
  A ROUGH ESTIMATE (FIGURE OF MERIT) IS ALL THAT IS NEEDED
    USE STANDARD LOAD FLOW CASES WITH NO ADDITIONAL OUTAGES
    ADJUST GENERATION PATTERNS IF NEEDED TO EVALUATE POSSIBILITIES
    TSP COMMUNICATES ONLY WITH ERCOT – NO STAKEHOLDER INVOLVEMENT
  THE TSP WILL HAVE A BETTER IDEA OF THE POTENTIAL VALUE OF MITIGATING MEASURES
    WORKING CIRCUITS HOT
    ADDITIONAL CREWS
    TEMPORARY STRUCTURES
    SCHEDULING CREZ AREA WORK DURING LOW WIND SEASONS
    DESIGN SPECIALTY TOOLS/JIGS AND SYSTEMS FOR SPEED AND SAFETY
  DEVELOP MARKET IMPACT ESTIMATES EARLY IN THE PROCESS TO INCREASE THE TIME TO EVALUATE AND IMPLEMENT OPTIONS

## Slide 4
DEVELOPING A ROUGH ESTIMATE OF MARKET IMPACT DUE TO TRANSMISSION OUTAGES
  USE SSWG CASES “AS IS” FOR THE YEAR STUDIED
  USE STANDARD PRODUCTION COST DATA
  DO NOT MODEL ADDITIONAL TRANSMISSION OUTAGES
  MAY NEED TO MODIFY GENERATION PATTERNS
  THE OBJECTIVE IS TO START ESTIMATING EFFECTS
INITIALLY LIMIT TSPs TO ONLY A FEW STUDIES PER YEAR
DEVELOP A CRITERIA FOR SELECTING OUTAGES TO STUDY
FOCUS IS ON MITIGATING STRATEGIES NOT SCHEDULING
NEXT STEPS
  ESTIMATED STAFF IMPACT ON ERCOT
  INITIAL CRITERIA FOR SELECTING OUTAGES TO EVALUATE IMPACTS