## Projects
Generator Interconnection Status Report | March 2018
Date: 3/31/2018 5:05:09 PM

## Newly Operational & Cancelled
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
16INR0087 | RTS Wind Project | 160 | McCulloch | 2018-03-08
16INR0065 | CASL_GAP (Castle Gap Solar) | 180 | Upton | 2018-03-16
Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
Projects Cancelled by the Developer*
INR | Project | MW | County | Cancellation Date*
20INR0018 | Hamilton Wind | 101 | Hamilton | 2018-03-14
20INR0017 | Cooke Wind | 152 | Cooke | 2018-03-14
19INR0137 | Live Oak Solar | 50 | Schleicher | 2018-03-19
19INR0107 | Las Palmas Wind II | 102 | Willacy | 2018-03-14
19INR0106 | Las Palmas Wind | 201 | Willacy | 2018-03-14
19INR0082 | Diebel | 100 | Calhoun | 2018-03-14
19INR0079 | White Park Solar | 600 | Bell | 2018-03-12
16INR0008 | Tenaska Roans Prairie | 663 | Grimes | 2018-03-12
*Includes only those projects cancelled after developer makes a Full Interconnection Study request.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | FIS Pending or Completed (MW) | IA Executed, FIS Pending or Approved (MW) | Grand Total (MW)**
Currently tracking 340 generation interconnection or change requests |  | Gas-AllOther | 0 | 1742 | 3485 | 5227
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  | Gas-CombinedCycle | 0 | 1957 | 4557 | 6514
March 31, 2018 | Number of Projects | Gas-Compressed Air (CE) | 0 | 0 | 324 | 324
Security Screening Studies (SSS) Underway | 14 | Total Gas | 0 | 3699 | 8366 | 12065
SSS Completed | 41 | Nuclear | 0 |  | 0 | 0
Full Interconnect Study (FIS) Underway | 179 | Coal | 0 | 0 | 0 | 0
FIS Completed | 27 | Wind | 4517 | 19055 | 9325 | 32897
Interconnection Agreement Executed, FIS Pending | 45 | Battery | 0 | 0 | 0 | 0
Interconnection Agreement Executed | 34 | Solar | 4785 | 16706 | 2024 | 23515
Total Interconnection Requests | 340 | Biomass | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 8 | Petroleum Coke | 0 | 0 | 0 | 0
| Capacity, MW | Total | 9302 | 39460 | 19715 | 68477
Total Capacity Under Study * | 68477 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l). If the capacity for a single project is reported in the column, the value is redacted.
Interconnection Agreements Executed | 19715
Cancelled (since last month) | 1969 | ** Redacted project capacity from column E is excluded from the Grand Totals.
* Redacted project capacity is excluded. |  | Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
FIS Pending or Completed column: Total MW capacity for which an FIS is either pending or completed and reviewed by ERCOT. The column total matches the sum of capacity values reported in the Full Study tab.
IA Executed, FIS Pending or Approved column: Total MW capacity for which a FIS has been requested and approved, and an IA has been executed. The column total matches the sum of capacity values reported in the IA Table tab

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement as of March 31, 2018
GINR Reference Number | Project Name* | Interconnecting Entity | Point of Interconnection (POI) | County | Fuel | Capacity to Grid (MW) | Projected COD Month/Year (as specified by the resource developer) | FIS Report Status
17INR0065 | Capricorn III repower | Nextera |  | Sterling | WIND | 0 | 4/2018 | Complete
17INR0064 | Capricorn II repower | Nextera |  | Sterling | WIND | 0 | 4/2018 | Complete
17INR0057 | Red Canyon repower | Nextera |  | Borden | WIND | 0 | 4/2018 | Complete
17INR0070 | Desert Sky repower | Invenergy |  | Pecos | WIND | 7 | 6/2018 | Complete
17INR0069 | Trent repower | Invenergy |  | Nolan | WIND | 6 | 6/2018 | Complete
17INR0067 | Sweetwater 1 repower | Leeward Energy | 180151 Sweetwater1 34.5kV | Nolan | WIND | 0 | 6/2018 | Complete
17INR0060 | Horse Hollow IV repower | Nextera |  | Taylor | WIND | 0 | 6/2018 | Complete
17INR0058 | Horse Hollow II repower | Nextera |  | Taylor | WIND | 0 | 6/2018 | Complete
17INR0052 | HH1 (HHGT increase) | Nextera | 6216 Bluff Creek 138kV | Taylor | WIND | 44 | 7/2018 | Incomplete
17INR0104 | Capricorn 4 repower | Nextera |  | Coke | WIND | 0 | 7/2018 | Complete
17INR0103 | Horse 3 repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0101 | Horse 1 repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0063 | Capricorn I repower | Nextera |  | Sterling | WIND | 0 | 7/2018 | Complete
17INR0061 | Capricorn IV repower | Nextera |  | Sterling | WIND | 9 | 7/2018 | Complete
17INR0056 | Callahan repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0054 | Capricorn I & III repower | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WIND | 32 | 7/2018 | Complete
17INR0053 | HH3 (HHGT increase) | Nextera | 7046 Kendal 345kV | Taylor | WIND | 44 | 7/2018 | Complete
18INR0075 | Gulf Wind 1 Repower | Pattern Energy |  | Kenedy | WIND | 0 | 8/2018 | Incomplete
18INR0072 | Blue Summit Repower | Nextera | 140382 Blue Summit 1.6 34.5kV | Wilbarger | WIND | 10 | 12/2018 | Incomplete
18INR0070 | Blue Summit II | Nextera | 61001 Jim Treece 345kV | Wilbarger | WIND | 102 | 12/2018 | Incomplete
18INR0068 | Loraine Windpark Phase III | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WIND | 100 | 12/2018 | Incomplete
12INR0060 | Infinity Live Oak Wind | Infinity Renewables | 76003 Big Hill 345kV | Schleicher | WIND | 200 | 12/2018 | Incomplete
19INR0031 | Bestla Solar | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | SOLAR | 150 | 1/2019 | Incomplete
18INR0061 | Shakes Solar | Cypress Creek Renewables | tap 138kV 8283 Asherton - 8236 W_Batesvl | Zavala | SOLAR | 42 | 3/2019 | Incomplete
18INR0060 | Brightside Solar | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOLAR | 50 | 3/2019 | Incomplete
18INR0055 | Long Draw Solar | BNB Renewables | 59900 Long Draw 345kV | Borden | SOLAR | 225 | 3/2019 | Incomplete
18INR0023 | Lost Mines Wind | RES Americas | 60708 Orsted 345kV - Big Hill | Schleicher | WIND | 201 | 3/2019 | Incomplete
19INR0124 | Solemio Springs | Alpin Sun | tap 138kV 1698 Sulphur Springs Switch - 1814 Sulphur Springs | Hopkins | SOLAR | 50 | 4/2019 | Incomplete
19INR0119 | Patriot Wind II | Nrg | 85000 Nelson Sharpe 345kV | Nueces | WIND | 58 | 4/2019 | Incomplete
19INR0094 | GSE Three Solar | Alpin Sun | 6044 Turkey 69kV | Hall | SOLAR | 50 | 4/2019 | Incomplete
19INR0093 | Sole Mio | Alpin Sun | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | SOLAR | 45 | 4/2019 | Incomplete
19INR0091 | GSE ONE Solar | Alpin Sun | 1808 Bonham 138kV | Fannin | SOLAR | 82 | 4/2019 | Incomplete
19INR0057 | Old Bloomington Road | Castleman Power | 8143 Dupont 138kV | Victoria | GAS | 100 | 4/2019 | Incomplete
19INR0056 | Chamon Phase 2 | Castleman Power | 40260 Chamon 138kV | Harris | GAS | 100 | 4/2019 | Incomplete
18INR0045 | Misae Solar | Childress Solar LLC | 60501 Tesla 345kV | Childress | SOLAR | 241 | 4/2019 | Incomplete
16INR0036 | Pecan Creek 1 Gas | NTE Energy | tap 345kV 11420 Sweetwater - 11406 Central Bluff | Nolan | GAS | 280 | 4/2019 | Incomplete
19INR0092 | Prospero Solar | Longroad Energy | 79650 Clear Fork 345kV (or 1158 Andrews Co 345kV) | Andrews | SOLAR | 300 | 5/2019 | Incomplete
18INR0053 | Fort Bend Solar | Lendlease Energy | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | SOLAR | 240 | 5/2019 | Incomplete
16INR0111 | Las Lomas Wind | Enerverse | 8957 Lopeno 138kV | Starr | WIND | 200 | 5/2019 | Incomplete
20INR0011 | Ranchero Wind | Scout Clean Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WIND | 250 | 6/2019 | Incomplete
19INR0036 | Oxbow Solar | BNB Renewables | 59905 Faraday 345kV | Borden | SOLAR | 250 | 6/2019 | Incomplete
19INR0028 | Normande Solar Farm | 8minutenergy | 59900 Long Draw 345kV | Borden | SOLAR | 300 | 6/2019 | Incomplete
19INR0017 | Tri-County Solar | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | SOLAR | 207 | 6/2019 | Incomplete
19INR0001 | Texas Solar Nova | SunPower | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | SOLAR | 750 | 6/2019 | Incomplete
18INR0033 | Irion County Wind | Invenergy | 76005 Schneeman Draw 345kV | Irion | WIND | 300 | 6/2019 | Incomplete
18INR0040 | Soda Lake Solar 1 and 2 | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | SOLAR | 400 | 6/2019 | Complete
18INR0039 | Fowler Ranch | Solar Prime | tap 138kV 60014 Spudder - 76615 Crane | Crane | SOLAR | 150 | 6/2019 | Complete
19INR0044 | Lily Solar | SunChase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | SOLAR | 150 | 7/2019 | Incomplete
19INR0041 | Myrtle Solar | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | SOLAR | 240 | 7/2019 | Incomplete
18INR0064 | Silver Star repower | Bp | 150511 Flat Creek 34.5kV | Eastland | WIND | -7 | 7/2019 | Incomplete
13INR0025 | Buffalo Wind 1 | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | WIND | 150 | 7/2019 | Complete
19INR0083 | Oberon Solar | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | SOLAR | 180 | 8/2019 | Incomplete
18INR0062 | Wagyu Solar | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | SOLAR | 120 | 8/2019 | Incomplete
18INR0058 | Texana Solar | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOLAR | 150 | 8/2019 | Incomplete
18INR0050 | Mustang Creek Solar | Sunchase Power | 5523 ETP 138kV | Jackson | SOLAR | 150 | 8/2019 | Incomplete
19INR0138 | Buffalo Gap 4 | Aes | 66216 Bluff Creek 138kV | Nolan | WIND | 175 | 9/2019 | Incomplete
19INR0102 | Queen Solar | Cielo | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 400 | 9/2019 | Incomplete
19INR0099a | Kontiki Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | WIND | 255 | 9/2019 | Incomplete
19INR0038 | High Lonesome W | Swift Current Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WIND | 500 | 9/2019 | Incomplete
16INR0097 | Morada Del Sol Solar | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | SOLAR | 200 | 9/2019 | Incomplete
18INR0030 | Canyon Wind | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WIND | 360 | 9/2019 | Complete
18INR0029 | Armstrong Wind | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | WIND | 253 | 9/2019 | Complete
19INR0166 | Loma Pinta II | Enerverse | 5705 Fowlerton 138kV | La Salle | WIND | 202 | 10/2019 | Incomplete
19INR0142 | Bacon Switch Solar | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher OR 138kV 1450 Pleasva – 1485 Ceramic | Wichita | SOLAR | 150 | 10/2019 | Incomplete
19INR0120 | Sherbino II Wind repower | Bp | 131454 Keo_3 138kV | Pecos | WIND | -13 | 10/2019 | Incomplete
19INR0111 | Tom Green Solar | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | SOLAR | 150 | 10/2019 | Incomplete
19INR0110 | Angelina Solar | EDP Renewables | 3349 TMPLinla 138kV | Angelina | SOLAR | 150 | 10/2019 | Incomplete
19INR0109 | Crockett Solar | EDP Renewables | tap 138kV 6564 Illinois - 76579 Ft Lancaster | Crockett | SOLAR | 150 | 10/2019 | Incomplete
19INR0080 | Whitehorse Wind | Hill Country Wind | 68001 Clayton 345kV | Fisher | WIND | 400 | 10/2019 | Incomplete
19INR0053 | Hidalgo II Wind | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | WIND | 51 | 10/2019 | Incomplete
19INR0045 | Rayos Del Sol | Tradewind Energy | Two POIs tested in Screening study. POI 1: a tap to the 345kV line between Palmito (5966) and Steward (80137) 2. tap to the 138kV line between Wesmer and Rangerville | Cameron | SOLAR | 150 | 10/2019 | Incomplete
19INR0029 | Phoebe Solar | Longroad Energy | tap 138kV 1009 Yucca - 1146 Notrees OR tap Vest-Yukon | Winkler | SOLAR | 253 | 10/2019 | Incomplete
19INR0007 | Charbray Solar | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | SOLAR | 200 | 10/2019 | Incomplete
18INR0056 | Hallmark Solar | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | SOLAR | 50 | 10/2019 | Incomplete
18INR0042 | Kaiser Creek Wind | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WIND | 100 | 10/2019 | Incomplete
18INR0027 | Ponwar Solar Farm | 8minutenergy | tap 138kV 76032 NMcCamey - 60361 Santa Rita | Upton | SOLAR | 180 | 10/2019 | Incomplete
17INR0025 | Reloj Del Sol Wind | EDP Renewables | 80220 Cenizo 345kV | Zapata | WIND | 202 | 10/2019 | Incomplete
19INR0004 | Sanco Solar | 8minutenergy | 79502 Windmill 345kV | Deaf Smith | SOLAR | 400 | 10/2019 | Complete
15INR0063 | Easter Wind A | TriGlobal | 79502 Windmill 345kV | Castro | WIND | 155 | 10/2019 | Complete
19INR0155 | Morrow Lake Solar | Sunchase Power | tap 138kV Pearsall 5895 - Miracle 5700 | Frio | SOLAR | 150 | 11/2019 | Incomplete
19INR0150 | Millhouse Solar | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOLAR | 113 | 11/2019 | Incomplete
19INR0006 | Bluebonnet Solar | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | SOLAR | 61 | 11/2019 | Incomplete
18INR0031 | Maryneal Wind | Duke Energy | 71050 Bitter Creek 345kV | Nolan | WIND | 180 | 11/2019 | Incomplete
17INR0035 | Las Majadas Wind | EDF Renewables | 80512 MagicValleytap 345kV | Willacy | WIND | 227 | 11/2019 | Incomplete
16INR0081 | Mesteno Wind | Duke Energy | 80355 Del Sol 345kV | Starr | WIND | 202 | 11/2019 | Complete
20INR0008 | Yellow Jacket Wind | RES Americas | tap 345kV 7046 Kendal - 60618 Edison | Menard | WIND | 200 | 12/2019 | Incomplete
19INR0171 | Concho Valley Solar | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0165 | Barranca Wind | Enerverse | 80380 Cabezon 345kV | Zapata | WIND | 202 | 12/2019 | Incomplete
19INR0161 | Pierce Wind | Seventus | 345kV ROW between Hillje & WAP | Wharton | WIND | 300 | 12/2019 | Incomplete
19INR0160 | Great Dane Wind | Seventus | 5546 Danevang 138kV | Wharton | WIND | 302 | 12/2019 | Incomplete
19INR0156 | Grape Creek Wind | Apex Clean | tap 345kV 76009 TwinB - 76090 Divide | Coke | WIND | 524 | 12/2019 | Incomplete
19INR0149 | Lapetus Solar | 7x Energy | 1284 Shafter Lake 138kV | Andrews | SOLAR | 115 | 12/2019 | Incomplete
19INR0147 | Big Dog Solar | Eon | tap 345kV 76009 TwinB - 1444 Brown | Tom Green | SOLAR | 200 | 12/2019 | Incomplete
19INR0133 | Los Porciones II | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0132 | Los Porciones I | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0128 | White Mesa Wind | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WIND | 500 | 12/2019 | Incomplete
19INR0114 | Rambler Solar | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0113 | County Line Solar | S Power | 60385 Solstice 138kV, Tap between Pigcreek (60393) and TNFLATTOP (38069) | Pecos | SOLAR | 250 | 12/2019 | Incomplete
19INR0112 | Cranel Wind | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | WIND | 220 | 12/2019 | Incomplete
19INR0108 | Hardeman Wind | Eon | 6050 Lake Pauline 138kV | Hardeman | WIND | 200 | 12/2019 | Incomplete
19INR0103 | Rodeo Solar | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | SOLAR | 200 | 12/2019 | Incomplete
19INR0101 | Tehuacana Wind | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | WIND | 600 | 12/2019 | Incomplete
19INR0100 | Prairie Hill Wind | Infinity Renewables | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | Limestone | WIND | 300 | 12/2019 | Incomplete
19INR0098 | Pease River Wind | Eon | 60500 Edith Clarke 345kV | Hardeman | WIND | 301 | 12/2019 | Incomplete
19INR0088 | Aragorn Solar | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | SOLAR | 186 | 12/2019 | Incomplete
19INR0085 | Iola Solar | Open Road Renewables | 4 Iola 138kV | Grimes | SOLAR | 210 | 12/2019 | Incomplete
19INR0073 | Shakes Solar II | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOLAR | 158 | 12/2019 | Incomplete
19INR0070 | Trevino Solar | S Power | 78015 Rosita 138kV | Maverick | SOLAR | 180 | 12/2019 | Incomplete
19INR0055 | Monte Cristo II W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0054 | Monte Cristo 1 W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0052 | Truscott Gilliland East W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0051 | Truscott Gilliland West W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0049 | Buenos Aires 2 W | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0048 | Buenos Aires 1 W | Terra-Gen | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0035 | Norton Solar | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | SOLAR | 125 | 12/2019 | Incomplete
19INR0033 | Murphy Lake Solar | S Power | 6904 CombinRC 138kV | Kaufman | SOLAR | 100 | 12/2019 | Incomplete
19INR0023 | West Willacy 3 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0022 | West Willacy 2 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0014 | Formosa Increase | Formosa Plastics |  | Calhoun | GAS | 240 | 12/2019 | Incomplete
19INR0002 | King Mountain Solar | Nextera | tap 345kV 11028 Odessa - 76000 NMcCamey | Upton | SOLAR | 350 | 12/2019 | Incomplete
18INR0059 | Raymond Wind | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 202 | 12/2019 | Incomplete
18INR0057 | Green Valley Wind | Eon | Tap 138kV 8255 Hamilton - 8680 Rough Canyon | Val Verde | WIND | 500 | 12/2019 | Incomplete
18INR0051 | Byers Wind | Alterra Power | tap 345kV 6101 Riley - 1730 W Krum | Clay | WIND | 200 | 12/2019 | Incomplete
18INR0049 | Santa Rita Solar | Invenergy | 76005 Schneeman Draw 345kV | Crockett | SOLAR | 400 | 12/2019 | Incomplete
18INR0044 | Bluegrove Wind | Alterra Power | tap 138kV 1468 LKAROWHD - 1470 NEWPRT_P | Clay | WIND | 100 | 12/2019 | Incomplete
18INR0038 | Jumbo Hill Wind | Infinity Renewables | 1134 Littman 138kV | Andrews | WIND | 200 | 12/2019 | Incomplete
17INR0038 | Zapata II W | Nextera | 80220 Cenizo 345kV | Zapata | WIND | 400 | 12/2019 | Incomplete
17INR0036 | Grandview 4 Phase A Wind | Eon | tap 345kV 79000 Gray - 79006 Allen | Gray | WIND | 200 | 12/2019 | Incomplete
17INR0033 | Tecovas 2 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 12/2019 | Incomplete
17INR0031 | Espiritu Wind | Apex Clean | 5764 E Rio Hondo 138kV | Cameron | WIND | 148 | 12/2019 | Incomplete
17INR0030 | Estacado Solar | Avangrid | 79502 Windmill 345kV | Deaf Smith | SOLAR | 100 | 12/2019 | Incomplete
16INR0105 | Zapata I W | Nextera | 80230 Molina 138kV | Jim Hogg | WIND | 300 | 12/2019 | Incomplete
16INR0104 | Big Sampson Wind | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WIND | 400 | 12/2019 | Incomplete
16INR0074 | Chocolate Bayou W | Infinity Renewables | tap 138kV 42090 Amoco - 42940 Monsanto | Brazoria | WIND | 150 | 12/2019 | Incomplete
16INR0061 | WIT Ranch Wind | Eon | tap 345kV 60500 Edith Clarke- 60501 Tesla | Hardeman | WIND | 200 | 12/2019 | Incomplete
16INR0014b | Cattleman Wind B | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0014 | Cattleman Wind A | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0012 | Stella 2 Wind | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | WIND | 201 | 12/2019 | Incomplete
15INR0051 | Tierra Blanca W | Eon | 79501 Ogallala 345kV | Randall | WIND | 200 | 12/2019 | Incomplete
15INR0044 | Corazon Solar | Enerverse | 80219 Lobo 345kV | Webb | SOLAR | 200 | 12/2019 | Incomplete
15INR0034 | El Algodon Alto W | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | WIND | 201 | 12/2019 | Incomplete
16INR0117 | Tecovas 1 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 1/2020 | Incomplete
20INR0031 | Rippey Solar | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | SOLAR | 60 | 3/2020 | Incomplete
20INR0026 | Longbow Solar | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | SOLAR | 105 | 3/2020 | Incomplete
20INR0003 | Shorthorn Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 3/2020 | Incomplete
20INR0054 | Taygete Solar | 7x Energy | 6630 Fort Stockton 138kV (AEP) AND 38340 Airport Substation (TNMP) | Pecos | SOLAR | 250 | 4/2020 | Incomplete
19INR0034 | Greasewood Solar | Onpeak Power | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | SOLAR | 200 | 4/2020 | Incomplete
19INR0026 | Holstein 2 Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 100 | 4/2020 | Incomplete
19INR0009 | Holstein Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 200 | 4/2020 | Incomplete
20INR0043 | Gulf Wind 2 | Pattern Energy | 80071 Zorillo 345kV | Kenedy | WIND | 180 | 5/2020 | Incomplete
19INR0020c | SP-Pecos Bend Solar C | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020b | SP-Pecos Bend Solar B | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020 | SP-Pecos Bend Solar A | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
20INR0030 | Rustler Solar | Cypress Creek Renewables | tap 138kV 5827 Moore - 5895 Pearsall | Frio | SOLAR | 113 | 6/2020 | Incomplete
19INR0081 | Anson Solar | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | SOLAR | 600 | 6/2020 | Incomplete
19INR0030 | San Bernard Solar | Sunchase Power | 43340 Tx Gulf Sulphur 138kV | Wharton | SOLAR | 100 | 6/2020 | Incomplete
20INR0002 | Lake Spring Solar | 8minutenergy | 79501 Ogallala 345kV | Castro | SOLAR | 400 | 6/2020 | Complete
20INR0042 | Palmas Altas Wind 2 | Cielo | 5764 E Rio Hondo 138kV | Cameron | WIND | 145 | 7/2020 | Incomplete
20INR0024 | Is 177 | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | SOLAR | 25 | 7/2020 | Incomplete
20INR0021 | Garnet Solar | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOLAR | 20 | 7/2020 | Incomplete
20INR0019 | Trinity Hills Wind repower | Bp | 150751 & 150752 Trinity Hills 34.5kV | Young | WIND | -27 | 7/2020 | Incomplete
20INR0036 | Stillwater Solar | Cypress Creek Renewables | tap 345kV 8455 LONHILL - 8955 NEDIN | Nueces | SOLAR | 216 | 8/2020 | Incomplete
20INR0035 | Angus Solar | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | SOLAR | 188 | 8/2020 | Incomplete
20INR0025 | Spinel Solar | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | SOLAR | 30 | 8/2020 | Incomplete
20INR0023 | Agate Solar | Innovative Solar | 1906 Venus S 345kV | Ellis | SOLAR | 60 | 8/2020 | Incomplete
20INR0022 | Sandine Solar | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | SOLAR | 30 | 8/2020 | Incomplete
20INR0016 | Opal Solar | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | SOLAR | 45 | 8/2020 | Incomplete
20INR0015 | Citrine Solar | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | SOLAR | 45 | 8/2020 | Incomplete
20INR0014 | Obsidian Solar | Innovative Solar | 6131 Padr 69kV | Cottle | SOLAR | 60 | 8/2020 | Incomplete
20INR0013 | Basalt Solar | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOLAR | 20 | 8/2020 | Incomplete
20INR0012 | Lueders Solar | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | SOLAR | 40 | 8/2020 | Incomplete
19INR0099b | Kontiki Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | WIND | 255 | 9/2020 | Incomplete
19INR0042 | Long Point Solar | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Fort Bend | SOLAR | 100 | 9/2020 | Incomplete
20INR0055 | Vaquero 2 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | WIND | 202 | 10/2020 | Incomplete
20INR0005 | Shorthorn 2 Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 10/2020 | Incomplete
15INR0063b | Easter Wind B | TriGlobal | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 152 | 10/2020 | Complete
19INR0134 | Cottonwood Bayou | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | SOLAR | 150 | 11/2020 | Incomplete
19INR0123 | GSE Eleven | Alpin Sun | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | SOLAR | 135 | 11/2020 | Incomplete
20INR0065 | Highwire Solar |  | tap 345kV 8455 Lonhill - 8164 Coleto | Goliad | SOLAR | 375 | 12/2020 | Incomplete
20INR0046 | Maverick Creek II | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WIND | 252 | 12/2020 | Incomplete
20INR0045 | Maverick Creek I | RES Americas | Tap Redcreek 6444 to 76006 Bow Wood 345kV or tap 345kV 76009 TwinB - 1444 Brown | Concho | WIND | 252 | 12/2020 | Incomplete
20INR0041 | Watusi Solar | Cypress Creek Renewables | tap 69kV 6363 Yellowjacket - 60386 Heartland | Menard | SOLAR | 195 | 12/2020 | Incomplete
20INR0038 | Red Mud Creek | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WIND | 201 | 12/2020 | Incomplete
20INR0032 | IP Titan | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | SOLAR | 227 | 12/2020 | Incomplete
19INR0121 | Galloway Solar | 8minutenergy | tap 345kV 6444 Red Creek - 76006 Bowwood OR 1444 Brown - 76009 TwinButtes | Concho | SOLAR | 360 | 12/2020 | Incomplete
19INR0117 | Road Runner Crossing Wind 1 | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | WIND | 201 | 12/2020 | Incomplete
19INR0097 | Shamrock Wind II | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0096 | Shamrock Wind | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0075 | Horseshoe Bend Solar | Clenera | 1444 Brown 345kV | Coleman | SOLAR | 300 | 12/2020 | Incomplete
18INR0005 | Panda Sherman 2 G | Panda Funds | 1758 Payne 138kV | Grayson | GAS | 543 | 12/2020 | Incomplete
17INR0043 | Vaquero 1 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Brooks | WIND | 400 | 12/2020 | Incomplete
16INR0106 | Whatley Solar | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | SOLAR | 150 | 12/2020 | Incomplete
16INR0102 | Owego Solar | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | SOLAR | 74 | 12/2020 | Incomplete
16INR0101 | Chatee Solar | Hecate Energy | 6641 Sun Valley 69kV | Pecos | SOLAR | 57 | 12/2020 | Incomplete
16INR0099 | Hecate Solar | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | SOLAR | 33 | 12/2020 | Incomplete
16INR0085 | Priddy Wind | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | WIND | 300 | 12/2020 | Incomplete
15INR0062b | Hale Community W 2 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 122 | 12/2020 | Incomplete
15INR0062 | Hale Community W 1 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 200 | 12/2020 | Incomplete
08INR0019b | Grandview 5 W | Eon | 79005 Railhead 345kV | Gray | WIND | 249 | 12/2020 | Incomplete
16INR0033 | Hart Wind | Orion | 79501 Ogallala 345kV | Castro | WIND | 150 | 12/2020 | Complete
18INR0009 | Eagle Pines Gas | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | GAS | 1174 | 2/2021 | Incomplete
21INR0007 | Deepwater | Aes | 40450 Deepwater 345kV | Harris | GAS | 462 | 4/2021 | Incomplete
21INR0002 | Hariana Solar | 8minutenergy | 6110 East Munday 138kV | Knox | SOLAR | 200 | 6/2021 | Incomplete
17INR0013 | Site C Brazos G | Brazos Elec Coop | tap one 345kV Venus - 68090 Sam Switch ckt | Hill | GAS | 800 | 8/2021 | Incomplete
18INR0034 | Blanco Canyon Wind | Invenergy | 59904 Cottonwood 345kV | Crosby | WIND | 251 | 12/2021 | Incomplete
16INR0119 | Wake Solar | Invenergy | 59904 Cottonwood 345kV | Crosby | SOLAR | 150 | 12/2021 | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## IA Table
Generation Interconnection Agreements as of March 31, 2018
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name* | Interconnecting Entity | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
16INR0087 | RTS Wind Project | Goldwind | McCulloch | 2018-03-01 | Wind | 160 |  | Yes | Yes | N/A | N/A | Complete
14INR0031 | BTE (Baytown Chiller) | Calpine | Chambers | 2018-03-01 | Gas | 270 |  | Yes | Yes | Yes | N/A | Complete
12INR0059b | HOVEY (Barilla Solar 1B) | First Solar | Pecos | 2018-03-01 | Solar | 7 |  | Yes | Yes | N/A | N/A | Complete
16INR0091 | HICKMAN | Invenergy | Reagan | 2018-04-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
15INR0082 | Flat Top Wind I | Alterra Power | Comanche | 2018-04-01 | Wind | 200 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0045 | RIGGINS | NRG | Pecos | 2018-04-01 | Solar | 150 |  | Yes | Yes | N/A | N/A | Complete
13INR0049 | FEGC | Friendswood Energy Genco | Harris | 2018-04-01 | Gas | 129 |  | Yes | Yes | Yes | Yes | Complete
16INR0054 | NA | NASA | Harris | 2018-05-01 | Gas | 12 |  | Yes | Yes | N/A | N/A | Complete
17INR0068 | Sweetwater 2 repower | Leeward Energy | Nolan | 2018-06-01 | Wind | 7 |  | No | No | N/A | N/A | Complete
16INR0086 | Cactus Flats Wind | Southern Power Company | Concho | 2018-06-01 | Wind | 148 |  | Yes | Yes | N/A | N/A | Complete
16INR0065 | CASL_GAP (Castle Gap Solar) | Vistra Energy/Luminant | Upton | 2018-06-01 | Solar | 180 |  | Yes | Yes | N/A | N/A | Complete
15INR0061 | LASSO | Solaire Direct | Brewster | 2018-06-01 | Solar | 50 |  | Yes | Yes | N/A | N/A | Complete
18INR0013 | Denton Energy Center | Denton Municipal Electric | Denton | 2018-07-01 | Gas | 226 |  | Yes | Yes | Yes | N/A | Complete
13INR0010a | Mariah Del Este | Mariah Acquisition | Parmer | 2018-09-01 | Wind | 152 |  | Yes | Yes | N/A | N/A | Incomplete
18INR0025 | Tahoka Wind | Lincoln Clean | Lynn | 2018-10-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
17INR0022 | MIRAGE | Net Power | Harris | 2018-10-01 | Gas | 11 |  | Yes | Yes | Yes | Yes | Complete
18INR0035 | CityVict | Castleman Power | Victoria | 2018-11-01 | Gas | 100 | NEW | No | No | Yes | No | Incomplete
17INR0045 | VictPort | Castleman Power | Victoria | 2018-11-01 | Gas | 100 | NEW | No | No | No | No | Incomplete
18INR0016 | Heart of Texas Wind | RES Americas | McCulloch | 2018-12-01 | Wind | 150 |  | No | No | N/A | N/A | Complete
16INR0112 | Loma Pinta Wind | Enerverse | La Salle | 2018-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Complete
15INR0064b | Harald (BearKat Wind B) | TriGlobal | Glasscock | 2018-12-01 | Wind | 162 |  | Yes | Yes | N/A | N/A | Complete
14INR0038 | BAC | PHR Holdings | Galveston | 2018-12-01 | Gas | 390 |  | Yes | Yes | Yes | N/A | Complete
16INR0115 | Waymark Solar | 174 Power Global | Pecos | 2018-12-01 | Solar | 182 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0114 | Upton Solar | SunPower | Upton | 2018-12-01 | Solar | 102 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0023b | Lamesa Solar B (Phase II) | RES Americas | Dawson | 2018-12-01 | Solar | 50 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0019 | BlueBell Solar | Nextera | Coke | 2018-12-01 | Solar | 100 | Project Name | No | No | N/A | N/A | Incomplete
15INR0035 | Stella 1 Wind | Eon | Kenedy | 2018-12-01 | Wind | 201 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045b | Torrecillas Wind B | Nextera | Webb | 2018-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045a | Torrecillas Wind A | Nextera | Webb | 2018-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010c | Mariah Del Sur | Mariah Acquisition | Parmer | 2018-12-01 | Wind | 218 |  | Yes | Yes | N/A | N/A | Incomplete
11INR0054 | Midway Wind | Apex Clean | San Patricio | 2018-12-01 | Wind | 163 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
18INR0067 | Gopher Creek Wind | Terna Energy | Scurry | 2019-01-01 | Wind | 158 |  | Yes | Yes | N/A | N/A | Complete
16INR0076 | Hudson (Ineos/Brazoria) | Ineos | Brazoria | 2019-01-01 | Gas | 96 | Project Name | Yes | Yes | Yes | Yes | Complete
16INR0037c | Pumpkin Farm Wind | Apex Clean | Floyd | 2019-01-01 | Wind | 281 |  | Yes | Yes | N/A | N/A | Complete
15INR0023 | Indeck Wharton | Indeck Energy Services | Wharton | 2019-02-01 | Gas | 654 |  | No | No | Yes | Yes | Complete
12INR0055 | Little Mountain Wind | Infinity Renewables | Baylor | 2019-03-01 | Wind | 80 |  | No | No | N/A | N/A | Incomplete
17INR0005 | Cabezon Wind | Longroad Energy | Starr | 2019-04-01 | Wind | 238 |  | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | NRG | Nueces | 2019-04-01 | Wind | 180 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010def | Scandia Wind DEF | Scandia Southwest | Parmer | 2019-05-01 | Wind | 600 |  | No | No | N/A | N/A | Complete
17INR0027b | Coyote Wind | Lincoln Clean | Scurry | 2019-05-01 | Wind | 242 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0059 | Emerald Grove Solar | Cypress Creek Renewables | Pecos | 2019-05-01 | Solar | 108 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0003 | LEVEE (Freeport LNG) | Freeport LNG | Brazoria | 2019-06-01 | Gas | 11 |  | Yes | Yes | Yes | N/A | Complete
19INR0163 | Sage Draw Wind | Lincoln Clean | Lynn | 2019-06-01 | Wind | 300 |  | No | No | N/A | N/A | Incomplete
19INR0019 | Foard City Wind | Alterra Power | Foard | 2019-06-01 | Wind | 350 | NEW | No | No | N/A | N/A | Incomplete
16INR0062b | Lockett Wind | Lincoln Clean | Wilbarger | 2019-06-01 | Wind | 184 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0044 | Halyard Wharton | Halyard Energy | Wharton | 2019-06-01 | Gas | 419 |  | No | No | Yes | Yes | Incomplete
13INR0026 | Canadian Breaks Wind | Macquarie Cap | Oldham | 2019-07-01 | Wind | 210 |  | No | No | N/A | N/A | Complete
18INR0001 | Rockwood G | Lincoln Clean | Colorado | 2019-07-01 | Gas | 1122 |  | No | No | Yes | No | Incomplete
14INR0033 | Goodnight Wind | FGE Power | Armstrong | 2019-08-01 | Wind | 497 | Projected Date | No | No | N/A | N/A | Complete
18INR0043 | Edmondson Ranch Wind | Wind Tex | Glasscock | 2019-09-01 | Wind | 292 |  | Yes | Yes | N/A | N/A | Complete
13INR0038 | Wildrose Wind | S Power | Swisher | 2019-10-01 | Wind | 212 |  | Yes | Yes | N/A | N/A | Complete
18INR0004 | Shawnee G | Lincoln Clean | Hill | 2019-10-01 | Gas | 928 |  | No | No | Yes | No | Incomplete
16INR0049 | Nazareth Solar | Lincoln Clean | Castro | 2019-10-01 | Solar | 201 |  | No | No | N/A | N/A | Incomplete
15INR0079 | Pullman Road Wind | SunEdison | Randall | 2019-10-01 | Wind | 300 |  | No | No | N/A | N/A | Incomplete
15INR0050 | Unity Wind | Miller Wind | Deaf Smith | 2019-10-01 | Wind | 203 |  | No | No | N/A | N/A | Incomplete
14INR0009 | WKN Amadeus Wind | WKN | Kent | 2019-10-01 | Wind | 246 | NEW | No | No | N/A | N/A | Incomplete
12INR0002a | Silver Canyon Wind A | EDP Renewables | Briscoe | 2019-10-01 | Wind | 200 |  | No | No | N/A | N/A | Incomplete
18INR0022 | RES Wink Solar | RES Americas | Winkler | 2019-12-01 | Solar | 150 | NEW | No | No | N/A | N/A | Complete
15INR0090 | Pflugerville Solar | RRE Solar | Travis | 2019-12-01 | Solar | 144 |  | No | No | N/A | N/A | Complete
19INR0074 | Karankawa 2 Wind Farm | Avangrid | San Patricio | 2019-12-01 | Wind | 200 | NEW | No | No | N/A | N/A | Incomplete
18INR0014 | Karankawa Wind Alt A | Avangrid | San Patricio | 2019-12-01 | Wind | 200 |  | No | No | N/A | N/A | Incomplete
17INR0037 | Palmas Altas Wind | Acciona | Cameron | 2019-12-01 | Wind | 145 |  | No | No | N/A | N/A | Incomplete
17INR0020c | RE Maplewood 2c Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020b | RE Maplewood 2b Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020a | RE Maplewood 2a Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0044 | West of Pecos Solar | Eon | Reeves | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0005c | Grandview W 3 | Eon | Carson | 2019-12-01 | Wind | 188 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Avangrid | Swisher | 2019-12-01 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
16INR0006 | Pinecrest G | Coronado Ventures | Angelina | 2020-04-01 | Gas | 785 |  | No | No | Yes | Yes | Incomplete
16INR0045 | Halyard Henderson | Halyard Energy | Henderson | 2020-06-01 | Gas | 432 |  | No | No | Yes | Yes | Complete
18INR0018 | Peyton Creek Wind | Eon | Matagorda | 2020-07-01 | Wind | 150 | NEW | No | No | N/A | N/A | Complete
17INR0010 | FGE Texas 2 Gas | FGE Power | Mitchell | 2020-09-01 | Gas | 743 |  | No | No | Yes | No | Incomplete
16INR0010 | FGE Texas 1 Gas | FGE Power | Mitchell | 2020-10-01 | Gas | 743 |  | No | No | Yes | Yes | Incomplete
15INR0013 | Bethel CAES | Apex CAES | Anderson | 2020-11-01 | Gas/CE | 324 | Fuel | No | No | Yes | Yes | Incomplete
20INR0058 | Longhorn South | EDF Renewables | Briscoe | 2020-12-01 | Wind | 160 | NEW | Yes | Yes | N/A | N/A | Incomplete
17INR0020e | RE Maplewood 2e Solar | Recurrent Energy | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020d | RE Maplewood 2d Solar | Recurrent Energy | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0005 | Brownsville G | Tenaska | Cameron | 2020-12-01 | Gas | 871 |  | No | No | Yes | No | Incomplete
14INR0030c | Panhandle Wind 3 | Pattern Energy | Carson | 2020-12-01 | Wind | 248 |  | Yes | Yes | N/A | N/A | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
16INR0087 | RTS Wind Project | McCulloch | PLANNED | 2018-03-15 | 2015-10-14 | WIND | WT | 160 | 2018 | TRUE
16INR0091 | HICKMAN | Reagan | PLANNED | 2018-04-12 | 2017-01-03 | WIND | WT | 300 | 2018 | TRUE
15INR0082 | Flat Top Wind I | Comanche | PLANNED | 2018-04-30 | 2016-02-19 | WIND | WT | 200 | 2018 | TRUE
17INR0068 | Sweetwater 2 repower | Nolan | PLANNED | 2018-06-01 | 2017-11-17 | WIND | WT | 7 | 2018 | FALSE
16INR0086 | Cactus Flats Wind | Concho | PLANNED | 2018-06-15 | 2017-03-15 | WIND | WT | 148 | 2018 | TRUE
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-09-30 | 2013-01-31 | WIND | WT | 152 | 2018 | TRUE
18INR0025 | Tahoka Wind | Lynn | PLANNED | 2018-10-22 | 2018-01-03 | WIND | WT | 300 | 2018 | TRUE
15INR0064b | Harald (BearKat Wind B) | Glasscock | PLANNED | 2018-12-03 | 2016-12-20 | WIND | WT | 162 | 2018 | TRUE
11INR0054 | Midway Wind | San Patricio | PLANNED | 2018-12-15 | 2017-11-05 | WIND | WT | 163 | 2018 | TRUE
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 218 | 2018 | TRUE
14INR0045a | Torrecillas Wind A | Webb | PLANNED | 2018-12-31 | 2015-01-30 | WIND | WT | 200 | 2018 | TRUE
14INR0045b | Torrecillas Wind B | Webb | PLANNED | 2018-12-31 | 2015-01-30 | WIND | WT | 200 | 2018 | TRUE
15INR0035 | Stella 1 Wind | Kenedy | PLANNED | 2018-12-31 | 2017-08-02 | WIND | WT | 201 | 2018 | TRUE
16INR0112 | Loma Pinta Wind | La Salle | PLANNED | 2018-12-31 | 2017-12-13 | WIND | WT | 200 | 2018 | TRUE
18INR0016 | Heart of Texas Wind | McCulloch | PLANNED | 2018-12-31 | 2017-11-21 | WIND | WT | 150 | 2018 | FALSE
18INR0067 | Gopher Creek Wind | Scurry | PLANNED | 2019-01-22 | 2018-01-26 | WIND | WT | 158 | 2019 | TRUE
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2019-01-31 | 2017-03-24 | WIND | WT | 281 | 2019 | TRUE
12INR0055 | Little Mountain Wind | Baylor | PLANNED | 2019-03-01 | 2017-12-04 | WIND | WT | 80 | 2019 | FALSE
17INR0005 | Cabezon Wind | Starr | PLANNED | 2019-04-01 | 2017-08-03 | WIND | WT | 238 | 2019 | TRUE
11INR0062 | Patriot Wind | Nueces | PLANNED | 2019-04-30 | 2016-10-13 | WIND | WT | 180 | 2019 | TRUE
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2019-05-01 | 2014-04-25 | WIND | WT | 600 | 2019 | FALSE
17INR0027b | Coyote Wind | Scurry | PLANNED | 2019-05-01 | 2016-08-09 | WIND | WT | 242 | 2019 | TRUE
16INR0062b | Lockett Wind | Wilbarger | PLANNED | 2019-06-01 | 2015-03-31 | WIND | WT | 184 | 2019 | TRUE
19INR0163 | Sage Draw Wind | Lynn | PLANNED | 2019-06-15 | 2018-01-03 | WIND | WT | 300 | 2019 | FALSE
19INR0019 | Foard City Wind | Foard | PLANNED | 2019-06-30 | 2018-02-19 | WIND | WT | 350 | 2019 | FALSE
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2019-07-01 | 2016-05-20 | WIND | WT | 210 | 2019 | FALSE
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2019-08-11 | 2018-03-07 | WIND | WT | 497 | 2019 | FALSE
18INR0043 | Edmondson Ranch Wind | Glasscock | PLANNED | 2019-09-01 | 2017-10-04 | WIND | WT | 292 | 2019 | TRUE
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2019-10-01 | 2014-10-03 | WIND | WT | 203 | 2019 | FALSE
13INR0038 | Wildrose Wind | Swisher | PLANNED | 2019-10-30 | 2015-09-06 | WIND | WT | 212 | 2019 | TRUE
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2019-10-31 | 2016-06-22 | WIND | WT | 200 | 2019 | FALSE
14INR0009 | WKN Amadeus Wind | Kent | PLANNED | 2019-10-31 | 2018-03-15 | WIND | WT | 246 | 2019 | FALSE
15INR0079 | Pullman Road Wind | Randall | PLANNED | 2019-10-31 | 2014-05-29 | WIND | WT | 300 | 2019 | FALSE
13INR0005c | Grandview W 3 | Carson | PLANNED | 2019-12-15 | 2014-04-23 | WIND | WT | 188 | 2019 | TRUE
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2019-12-31 | 2013-07-24 | WIND | WT | 500 | 2019 | FALSE
17INR0037 | Palmas Altas Wind | Cameron | PLANNED | 2019-12-31 | 2017-11-30 | WIND | WT | 145 | 2019 | FALSE
18INR0014 | Karankawa Wind Alt A | San Patricio | PLANNED | 2019-12-31 | 2017-11-30 | WIND | WT | 200 | 2019 | FALSE
19INR0074 | Karankawa 2 Wind Farm | San Patricio | PLANNED | 2019-12-31 | 2018-03-02 | WIND | WT | 200 | 2019 | FALSE
18INR0018 | Peyton Creek Wind | Matagorda | PLANNED | 2020-07-31 | 2018-03-19 | WIND | WT | 150 | 2020 | FALSE
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2020-12-01 | 2014-08-25 | WIND | WT | 248 | 2020 | TRUE
20INR0058 | Longhorn South | Briscoe | PLANNED | 2020-12-31 | 2012-12-10 | WIND | WT | 160 | 2020 | TRUE

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | PLANNED | 2018-03-01 | 2013-12-26 | SOLAR | PV | 7 | 2018 | TRUE
15INR0045 | RIGGINS | Pecos | PLANNED | 2018-04-20 | 2015-01-26 | SOLAR | PV | 150 | 2018 | TRUE
15INR0061 | LASSO | Brewster | PLANNED | 2018-06-01 | 2015-11-10 | SOLAR | PV | 50 | 2018 | TRUE
16INR0065 | CASL_GAP (Castle Gap Solar) | Upton | PLANNED | 2018-06-01 | 2015-09-04 | SOLAR | PV | 180 | 2018 | TRUE
16INR0019 | BlueBell Solar | Coke | PLANNED | 2018-12-01 | 2015-08-19 | SOLAR | PV | 100 | 2018 | FALSE
16INR0114 | Upton Solar | Upton | PLANNED | 2018-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2018 | TRUE
16INR0115 | Waymark Solar | Pecos | PLANNED | 2018-12-15 | 2016-09-23 | SOLAR | PV | 182 | 2018 | TRUE
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2018-12-31 | 2016-07-28 | SOLAR | PV | 50 | 2018 | TRUE
15INR0059 | Emerald Grove Solar | Pecos | PLANNED | 2019-05-31 | 2017-12-04 | SOLAR | PV | 108 | 2019 | TRUE
16INR0049 | Nazareth Solar | Castro | PLANNED | 2019-10-01 | 2015-05-15 | SOLAR | PV | 201 | 2019 | FALSE
15INR0090 | Pflugerville Solar | Travis | PLANNED | 2019-12-01 | 2017-06-13 | SOLAR | PV | 144 | 2019 | FALSE
14INR0044 | West of Pecos Solar | Reeves | PLANNED | 2019-12-15 | 2017-02-27 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
18INR0022 | RES Wink Solar | Winkler | PLANNED | 2019-12-31 | 2018-01-23 | SOLAR | PV | 150 | 2019 | FALSE
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE
17INR0020e | RE Maplewood 2e Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE