## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
April 12, 2018

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
  2018 Release Targets
  Planned Project Starts
  2018 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Appendix
  Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2018 April Release – 4/5/2018 – 4/9/2018 In Flight
  NPRR562(b) – Subsynchronous Resonance
    MIS link for posting of annual SSR topology-check report
  SCR792 – Enhance Communications of BAAL Exceedances
2018 May Release – 5/29/2018 – 5/31/2018 In Flight
  NPRR768 – Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories
  NPRR809(b) – GTC or GTL for New Generation Interconnection
    Reporting/posting system changes
  NPRR815 – Revise the Limitation of Load Resources Providing RRS
  OBDRR002 – ORDC OBD Revisions for PUCT Project 47199
June 1 Release In Flight
  NPRR776 – Voltage Set Point Communication
  NOGRR167 – Alignment with NPRR776, Voltage Set Point Communication
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/6 – 2/8 | April 4/5 – 4/9 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/23 – 10/25 | December 12/11 – 12/13
NPRR659 NPRR683 NPRR743 NPRR760 NPRR800 NPRR810 PGRR042 NPRR846 | NPRR562(b) NPRR776 SCR792 | NPRR768 NPRR809(b) NPRR815 OBDRR002 SCR791 NPRR776 NOGRR167 | NPRR819 NPRR844 SCR791 | NPRR817 NPRR843 SCR794 | NPRR519 NPRR620 NPRR741 NPRR755 PGRR057 NPRR842 SCR789
8 | 2 | 6 | 3 | 2 | 6
12/15 – 12/16
(Retail)
6/1
10/27 – 10/28
(Retail)
I
E
P
NS
NS
E
E
E
E
E
NS
8/11 – 8/12
(Retail)
4/7 – 4/8
(Retail)
CMM Release 1a
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
1/1 & 2/1
E
E
E
E
NPRR562(b) – Reporting/posting system changes
NPRR809(b) – Reporting/posting system changes
NPRR831(b) – CRR system changes
E
E
CMM Release 1b
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NPRR664 | None | SCR781 P | NPRR702 P, SCR777, NPRR831(b), NPRR749 E, NPRR833 E, NPRR819, NPRR842, NPRR844, SCR794
1/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
E
E

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR843 – Short-Term System Adequacy and AS Offer Disclosure Reports Additions | May 2018 | 2018-R5 | $70k-$90k | ERCOT
SCR794 – Update SCED Limit Calculation | June 2018 | 2018-R5 | $25k-$35k | ERCOT
NPRR842 – Study Area Load Information | July 2018 | 2018-R6 | $60k-$80k | ERCOT
NPRR817 – Create a Panhandle Hub | Sept 2018 | 2019-R2 | $150k-$200k | DC Energy
NPRR821 – Elimination of the CRR Deration Process for Resource Node to Hub or Load Zone CRRs | Jan 2019 | 2019-R3 | $30k-$50k | DC Energy
NPRR829 – Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL | Aug 2019 | 2020-R1 | $200k-$300k | Enchanted Rock
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | TBD | TBD | $200k-$300k | Rainbow Energy
NPRR841 – Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | TBD | TBD | $60k-$80k | ERCOT
Aging Items Report | Last Action | Status
NPRR664 – Fuel Index Price for Resource Definition and Real-Time Make-Whole Payments for Exceptional Fuel Cost Events | Board approved on 12/9/2014 | Pending submission / approval of alternate approach
Dependent on internal ERCOT project
2019 Priority
2019 Priority
2019 Priority
Moved start date due to higher priorities
Upcoming project initiations

## Slide 6: 2018 Project Spending
2018 PPL Budget = $20.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2018 and 2019, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2018 | 2019
YTD Actuals | $0.24M | 
Approved – In-Flight / Complete | $1.60M | $0.00M
Approved – On Hold | $0.00M | $0.00M
Approved – Not Started | $0.19M | $0.12M
Remaining Funding | $2.21M | $3.88M
Total Allocation | $4.00M | $4.00M
As of 2/28/2018

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR847 | Exceptional Fuel Cost Included in the Mitigated Offer Cap | 2018 | 2210 | MMS impacts Work into the 2018 project plan without disrupting in-flight projects
NPRR857 | Creation of Direct Current Tie Operator Market Participant Role | 2019 | 2530 | Currently timeline anticipates project initiation in mid-2019
Options for…
PPL Rank Information
Next available Rank in Business Strategy = 2210
Next available Rank in Regulatory = 200

## Slide 9
Appendix
  4/1/2018 Project Gantt
    In-flight items sorted by Project End Date
    “On Hold” projects listed separately
    “Not Started” items sorted by Project Start Date

## Slide 10: Project Portfolio Status – as of 4/1/2018

## Slide 11: Project Portfolio Status – as of 4/1/2018

## Slide 12: Project Portfolio Status – as of 4/1/2018

## Slide 13: Project Portfolio Status – as of 4/1/2018

## Slide 14: Project Portfolio Status – as of 4/1/2018

## Slide 15: Project Portfolio Status – as of 4/1/2018 – On Hold

## Slide 16: Project Portfolio Status – as of 4/1/2018