## Projects
Generator Interconnection Status Report | May 2018
Date: 5/31/2018 8:02:48 PM

## Newly Operational & Cancelled
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
13INR0049 | FEGC (Friendswood Energy) | 129 | Harris | 2018-05-09
Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
16INR0091 | HICKMAN | 300 | Reagan | 2018-05-09
16INR0065 | CASL_GAP (Castle Gap Solar) | 180 | Upton | 2018-05-31
15INR0061 | LASSO | 50 | Brewster | 2018-05-24
14INR0031 | BTE (Baytown Chiller) | 270** | Chambers | 2018-04-30
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
**Represents the total capacity studied for this Private Use Network site, which includes both chiller capacity and load.
Projects Cancelled by the Developer*
INR | Project | MW | County | Cancellation Date*
21INR0004 | Hutt Wind I | 204 | Midland | 2018-05-16
20INR0028 | Fossil Ridge | 300 | Denton | 2018-05-14
20INR0027 | Lavaca Wind | 151 | Calhoun | 2018-05-04
20INR0009 | Mariah Del Sur 2 | 350 | Parmer | 2018-05-25
19INR0130 | Buckthorn Solar 2 | 75 | Pecos | 2018-05-15
19INR0126 | Wolfcamp 2 | 100 | Pecos | 2018-05-14
19INR0125 | Wolfcamp 1 | 100 | Pecos | 2018-05-14
19INR0122 | Lone Star 1 | 150 | Robertson | 2018-05-14
19INR0118 | Road Runner Crossing Wind 2 | 102 | Eastland | 2018-05-14
19INR0116 | KMF Wind | 150 | Kenedy | 2018-05-09
19INR0104 | Alpine Solar | 50 | Brewster | 2018-05-29
19INR0070 | Trevino Solar | 180 | Maverick | 2018-05-23
17INR0013 | Site C Brazos G | 800 | Hill | 2018-05-25
*Includes only those projects cancelled after developer makes a Full Interconnection Study request.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | FIS Pending or Completed (MW) | IA Executed, FIS Pending or Approved (MW) | Grand Total (MW)**
Currently tracking 369 generation interconnection or change requests |  | Gas-AllOther | 0 | 1059 | 3485 | 4544
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  | Gas-CombinedCycle | 2241 | 2046 | 4287 | 8574
May 31, 2018 | Number of Projects | Gas-Compressed Air (CE) | 0 | 0 | 324 | 324
Security Screening Studies (SSS) Underway | 33 | Total Gas | 2241 | 3105 | 8096 | 13442
SSS Completed | 36 | Nuclear | 0 |  | 0 | 0
Full Interconnect Study (FIS) Underway | 180 | Coal | 0 | 0 | 0 | 0
FIS Completed | 34 | Wind | 5003 | 17482 | 11314 | 33799
Interconnection Agreement Executed, FIS Pending | 46 | Battery | 0 | 200 | 0 | 200
Interconnection Agreement Executed | 40 | Solar | 7458 | 18034 | 2274 | 27766
Total Interconnection Requests | 369 | Biomass | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 13 | Petroleum Coke | 0 | 0 | 0 | 0
| Capacity, MW | Total | 14702 | 38821 | 21684 | 75207
Total Capacity Under Study * | 75207 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l). If the capacity for a single project is reported in the column, the value is redacted.
Interconnection Agreements Executed | 21684
Cancelled (since last month) | 2712 | ** Redacted project capacity from column E is excluded from the Grand Totals.
* Redacted project capacity is excluded. |  | Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
FIS Pending or Completed column: Total MW capacity for which an FIS is either pending or completed and reviewed by ERCOT. The column total matches the sum of capacity values reported in the Full Study tab.
IA Executed, FIS Pending or Approved column: Total MW capacity for which a FIS has been requested and approved, and an IA has been executed. The column total matches the sum of capacity values reported in the IA Table tab

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement as of May 31, 2018
GINR Reference Number | Project Name* | Interconnecting Entity | Point of Interconnection (POI) | County | Fuel | Capacity to Grid (MW) | Projected COD Month/Year (as specified by the resource developer) | FIS Report Status
18INR0077 | Colorado Bend 2 retune | Exelon |  | Wharton | GAS | 45 | 6/2018 | Incomplete
18INR0076 | Wolf Hollow 2 retune | Exelon |  | Hood | GAS | 44 | 6/2018 | Incomplete
17INR0070 | Desert Sky repower | Invenergy |  | Pecos | WIND | 7 | 6/2018 | Complete
17INR0069 | Trent repower | Invenergy |  | Nolan | WIND | 6 | 6/2018 | Complete
17INR0067 | Sweetwater 1 repower | Leeward Energy | 180151 Sweetwater1 34.5kV | Nolan | WIND | 0 | 6/2018 | Complete
17INR0065 | Capricorn III repower | Nextera |  | Sterling | WIND | 0 | 6/2018 | Complete
17INR0064 | Capricorn II repower | Nextera |  | Sterling | WIND | 0 | 6/2018 | Complete
17INR0060 | Horse Hollow IV repower | Nextera |  | Taylor | WIND | 0 | 6/2018 | Complete
17INR0058 | Horse Hollow II repower | Nextera |  | Taylor | WIND | 0 | 6/2018 | Complete
17INR0057 | Red Canyon repower | Nextera |  | Borden | WIND | 0 | 6/2018 | Complete
18INR0069 | Indian Mesa Repowering | Nextera | 76019 Indian NWP 138kV | Pecos | WIND | 8 | 7/2018 | Incomplete
17INR0104 | Capricorn 4 repower | Nextera |  | Coke | WIND | 0 | 7/2018 | Complete
17INR0103 | Horse 3 repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0101 | Horse 1 repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0063 | Capricorn I repower | Nextera |  | Sterling | WIND | 0 | 7/2018 | Complete
17INR0061 | Capricorn IV repower | Nextera |  | Sterling | WIND | 9 | 7/2018 | Complete
17INR0056 | Callahan repower | Nextera |  | Taylor | WIND | 0 | 7/2018 | Complete
17INR0054 | Capricorn I & III repower | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WIND | 32 | 7/2018 | Complete
17INR0053 | HH3 (HHGT increase) | Nextera | 7046 Kendal 345kV | Taylor | WIND | 44 | 7/2018 | Complete
17INR0052 | HH1 (HHGT increase) | Nextera | 6216 Bluff Creek 138kV | Taylor | WIND | 44 | 7/2018 | Complete
18INR0078 | Bobcat Bluff Repowering | EDF Renewable Energy |  | Archer | WIND | 12 | 12/2018 | Incomplete
18INR0073 | Sweetwater 1 repower | Leeward Energy |  | Nolan | WIND | 3 | 12/2018 | Incomplete
18INR0075 | Gulf Wind 1 Repower | Pattern Energy |  | Kenedy | WIND | 0 | 2/2019 | Incomplete
19INR0036 | Oxbow Solar | BNB Renewables | 59905 Faraday 345kV | Borden | SOLAR | 225 | 3/2019 | Incomplete
18INR0055 | Long Draw Solar | BNB Renewables | 59900 Long Draw 345kV | Borden | SOLAR | 225 | 3/2019 | Incomplete
19INR0094 | GSE Three Solar | Alpin Sun | 6044 Turkey 69kV | Hall | SOLAR | 50 | 4/2019 | Incomplete
19INR0057 | Old Bloomington Road | Castleman Power | 8143 Dupont 138kV | Victoria | GAS | 100 | 4/2019 | Incomplete
16INR0036 | Pecan Creek 1 Gas | NTE Energy | tap 345kV 11420 Sweetwater - 11406 Central Bluff | Nolan | GAS | 280 | 4/2019 | Incomplete
19INR0056 | Chamon Phase 2 | Castleman Power | 40260 Chamon 138kV | Harris | GAS | 100 | 4/2019 | Complete
18INR0053 | Fort Bend Solar | Lendlease Energy | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | SOLAR | 240 | 5/2019 | Incomplete
16INR0111 | Las Lomas Wind | Enerverse | 8957 Lopeno 138kV | Starr | WIND | 200 | 5/2019 | Incomplete
19INR0180 | Friendswood II | Quantum | 47150 HOC 138kV | Harris | GAS | 117 | 6/2019 | Incomplete
19INR0131 | Cutlass Solar | Lendlease Energy | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | SOLAR | 300 | 6/2019 | Incomplete
19INR0017 | Tri-County Solar | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | SOLAR | 207 | 6/2019 | Incomplete
19INR0001 | Texas Solar Nova | SunPower | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | SOLAR | 750 | 6/2019 | Incomplete
18INR0033 | Oveja Wind | Invenergy | 76005 Schneeman Draw 345kV | Irion | WIND | 300 | 6/2019 | Incomplete
18INR0045 | Misae Solar | Latinoamericana de Energia | 60501 Tesla 345kV | Childress | SOLAR | 241 | 6/2019 | Complete
18INR0040 | Soda Lake Solar 1 and 2 | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | SOLAR | 400 | 6/2019 | Complete
18INR0039 | Fowler Ranch | Solar Prime | tap 138kV 60014 Spudder - 76615 Crane | Crane | SOLAR | 150 | 6/2019 | Complete
19INR0044 | Lily Solar | SunChase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | SOLAR | 150 | 7/2019 | Incomplete
19INR0041 | Myrtle Solar | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | SOLAR | 240 | 7/2019 | Incomplete
18INR0065 | Goodranch Solar | EDF Renewable Energy | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | SOLAR | 200 | 7/2019 | Incomplete
18INR0064 | Silver Star repower | Bp | 150511 Flat Creek 34.5kV | Eastland | WIND | -7 | 7/2019 | Complete
13INR0025 | Buffalo Wind 1 | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | WIND | 150 | 7/2019 | Complete
18INR0058 | Texana Solar | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOLAR | 150 | 8/2019 | Incomplete
18INR0050 | Mustang Creek Solar | Sunchase Power | 5523 ETP 138kV | Jackson | SOLAR | 150 | 8/2019 | Incomplete
19INR0138 | Buffalo Gap 4 | Aes | 66216 Bluff Creek 138kV | Nolan | WIND | 175 | 9/2019 | Incomplete
19INR0102 | Queen Solar | Cielo | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | SOLAR | 400 | 9/2019 | Incomplete
16INR0097 | Morada Del Sol Solar | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | SOLAR | 200 | 9/2019 | Incomplete
18INR0030 | Canyon Wind | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WIND | 360 | 9/2019 | Complete
19INR0166 | Loma Pinta II | Enerverse | 5705 Fowlerton 138kV | La Salle | WIND | 202 | 10/2019 | Incomplete
19INR0142 | Bacon Switch Solar | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher OR 138kV 1450 Pleasva – 1485 Ceramic | Wichita | SOLAR | 150 | 10/2019 | Incomplete
19INR0136 | Able Solar | Sunchase Power | 12469 Able Spring 138kV | Kaufman | SOLAR | 50 | 10/2019 | Incomplete
19INR0135 | Hill Solar | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasco | Hill | SOLAR | 80 | 10/2019 | Incomplete
19INR0120 | Sherbino II Wind repower | Bp | 131454 Keo_3 138kV | Pecos | WIND | -13 | 10/2019 | Incomplete
19INR0111 | Tom Green Solar | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | SOLAR | 150 | 10/2019 | Incomplete
19INR0109 | Crockett Solar | EDP Renewables | tap 138kV 6564 Illinois - 76579 Ft Lancaster | Crockett | SOLAR | 150 | 10/2019 | Incomplete
19INR0080 | Whitehorse Wind | Hill Country Wind | 68001 Clayton 345kV | Fisher | WIND | 400 | 10/2019 | Incomplete
19INR0053 | Hidalgo II Wind | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | WIND | 51 | 10/2019 | Incomplete
19INR0045 | Rayos Del Sol | Tradewind Energy | FIS considered tap Wesmer and Rangerville 138 | Cameron | SOLAR | 150 | 10/2019 | Incomplete
19INR0007 | Charbray Solar | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | SOLAR | 200 | 10/2019 | Incomplete
18INR0056 | Hallmark Solar | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | SOLAR | 50 | 10/2019 | Incomplete
18INR0042 | Kaiser Creek Wind | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WIND | 100 | 10/2019 | Incomplete
18INR0027 | Ponwar Solar Farm | 8minutenergy | tap 138kV 76032 N McCamey - 60361 Santa Rita | Upton | SOLAR | 180 | 10/2019 | Incomplete
17INR0025 | Reloj Del Sol Wind | EDP Renewables | 80220 Cenizo 345kV | Zapata | WIND | 202 | 10/2019 | Incomplete
19INR0083 | Oberon Solar | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | SOLAR | 180 | 10/2019 | Complete
19INR0004 | Sanco Solar | 8minutenergy | 79502 Windmill 345kV | Deaf Smith | SOLAR | 400 | 10/2019 | Complete
15INR0063 | Easter Wind A | TriGlobal | 79502 Windmill 345kV | Castro | WIND | 155 | 10/2019 | Complete
19INR0150 | Millhouse Solar | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOLAR | 113 | 11/2019 | Incomplete
19INR0149 | Lapetus Solar | 7x Energy | 1284 Shafter Lake 138kV | Andrews | SOLAR | 50 | 11/2019 | Incomplete
19INR0006 | Bluebonnet Solar | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | SOLAR | 61 | 11/2019 | Incomplete
18INR0031 | Maryneal Wind | Duke Energy | 71050 Bitter Creek 345kV | Nolan | WIND | 180 | 11/2019 | Incomplete
20INR0008 | Yellow Jacket Wind | RES Americas | tap 345kV 7046 Kendal - 60618 Edison | Menard | WIND | 200 | 12/2019 | Incomplete
19INR0177 | Shanghai Wind | Seventus | 8104 Lane City PM 138kV | Wharton | WIND | 153 | 12/2019 | Incomplete
19INR0172 | Dillon Gulch | Aes | tap 345kV 11420 Sweetwater East Switch - 11406 Central Bluff Switch | Nolan | WIND | 175 | 12/2019 | Incomplete
19INR0171 | Concho Valley Solar | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0167 | Gold Creek Solar | S Power | 1163 Lamesa 138kV | Maverick | SOLAR | 140 | 12/2019 | Incomplete
19INR0156 | Grape Creek Wind | Apex Clean | tap 345kV 76009 TwinB - 76090 Divide | Coke | WIND | 524 | 12/2019 | Incomplete
19INR0147 | Delong Solar | Eon | tap 345kV 76009 TwinB - 1444 Brown | Tom Green | SOLAR | 200 | 12/2019 | Incomplete
19INR0133 | Los Porciones II | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0132 | Los Porciones I | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0128 | White Mesa Wind | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WIND | 500 | 12/2019 | Incomplete
19INR0124 | Solemio Springs | Alpin Sun | tap 138kV 1698 Sulphur Springs Switch - 1814 Sulphur Springs | Hopkins | SOLAR | 50 | 12/2019 | Incomplete
19INR0115 | Blackwater Draw Solar | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | SOLAR | 150 | 12/2019 | Incomplete
19INR0114 | Rambler Solar | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0113 | County Line Solar | S Power | 60385 Solstice 138kV, Tap between Pigcreek (60393) and TNFLATTOP (38069) | Pecos | SOLAR | 250 | 12/2019 | Incomplete
19INR0112 | Cranel Wind | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | WIND | 220 | 12/2019 | Incomplete
19INR0108 | WIT Ranch Wind | Eon | 6050 Lake Pauline 138kV | Hardeman | WIND | 200 | 12/2019 | Incomplete
19INR0103 | Rodeo Solar | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | SOLAR | 205 | 12/2019 | Incomplete
19INR0101 | Tehuacana Wind | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | WIND | 600 | 12/2019 | Incomplete
19INR0098 | Pease River Wind | Eon | 60500 Edith Clarke 345kV | Hardeman | WIND | 301 | 12/2019 | Incomplete
19INR0093 | Sole Mio | Alpin Sun | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | SOLAR | 45 | 12/2019 | Incomplete
19INR0088 | Aragorn Solar | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | SOLAR | 186 | 12/2019 | Incomplete
19INR0085 | Blue Jay Solar | Open Road Renewables | 4 Iola 138kV | Grimes | SOLAR | 210 | 12/2019 | Incomplete
19INR0073 | Shakes Solar | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOLAR | 206 | 12/2019 | Incomplete
19INR0055 | Monte Cristo II W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0054 | Monte Cristo 1 W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0052 | Truscott Gilliland East W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0051 | Vera Wind | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 220 | 12/2019 | Incomplete
19INR0049 | Buenos Aires 2 W | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0048 | Buenos Aires 1 W | Terra-Gen | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0035 | Norton Solar | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | SOLAR | 125 | 12/2019 | Incomplete
19INR0033 | Murphy Lake Solar | S Power | 6904 CombinRC 138kV | Kaufman | SOLAR | 100 | 12/2019 | Incomplete
19INR0031 | Bestla Solar | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | SOLAR | 150 | 12/2019 | Incomplete
19INR0028 | Normande Solar Farm | 8minutenergy | 59900 Long Draw 345kV | Borden | SOLAR | 360 | 12/2019 | Incomplete
19INR0023 | West Willacy 3 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0022 | West Willacy 2 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0014 | Formosa Increase | Formosa Plastics |  | Calhoun | GAS | 240 | 12/2019 | Incomplete
19INR0002 | King Mountain Solar | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | SOLAR | 350 | 12/2019 | Incomplete
18INR0060 | Brightside Solar | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOLAR | 50 | 12/2019 | Incomplete
18INR0059 | Raymond Wind | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 202 | 12/2019 | Incomplete
18INR0057 | Green Valley Wind | Eon | Tap 138kV 8255 Hamilton - 8680 Rough Canyon | Val Verde | WIND | 500 | 12/2019 | Incomplete
18INR0051 | Byers Wind | Alterra Power | tap 345kV 6101 Riley - 1730 W Krum | Clay | WIND | 200 | 12/2019 | Incomplete
18INR0049 | Santa Rita Solar | Invenergy | 76005 Schneeman Draw 345kV | Crockett | SOLAR | 400 | 12/2019 | Incomplete
18INR0044 | Bluegrove Wind | Alterra Power | tap 138kV 1468 LKAROWHD - 1470 NEWPRT_P | Clay | WIND | 100 | 12/2019 | Incomplete
17INR0038 | Zapata II W | Nextera | 80220 Cenizo 345kV | Zapata | WIND | 400 | 12/2019 | Incomplete
17INR0036 | Grandview 4 Phase A Wind | Eon | tap 345kV 79000 Gray - 79006 Allen | Gray | WIND | 200 | 12/2019 | Incomplete
17INR0031 | Espiritu Wind | Apex Clean | 5764 E Rio Hondo 138kV | Cameron | WIND | 148 | 12/2019 | Incomplete
17INR0030 | Estacado Solar | Avangrid | 79502 Windmill 345kV | Deaf Smith | SOLAR | 100 | 12/2019 | Incomplete
16INR0105 | Zapata I W | Nextera | 80230 Molina 138kV | Jim Hogg | WIND | 300 | 12/2019 | Incomplete
16INR0104 | Big Sampson Wind | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WIND | 400 | 12/2019 | Incomplete
16INR0074 | Chocolate Bayou W | Infinity Renewables | tap 138kV 42090 Amoco - 42940 Monsanto | Brazoria | WIND | 150 | 12/2019 | Incomplete
16INR0014b | Cattleman Wind B | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0014 | Cattleman Wind A | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0012 | Stella 2 Wind | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | WIND | 201 | 12/2019 | Incomplete
15INR0051 | Tierra Blanca W | Eon | 79501 Ogallala 345kV | Randall | WIND | 200 | 12/2019 | Incomplete
15INR0044 | Corazon Solar | Enerverse | 80219 Lobo 345kV | Webb | SOLAR | 200 | 12/2019 | Incomplete
15INR0034 | El Algodon Alto W | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | WIND | 201 | 12/2019 | Incomplete
19INR0100 | Prairie Hill Wind | Infinity Renewables | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | Limestone | WIND | 300 | 12/2019 | Complete
18INR0038 | Jumbo Hill Wind | Infinity Renewables | 1134 Littman 138kV | Andrews | WIND | 200 | 12/2019 | Complete
20INR0050 | Castro Solar | Oaktree Development | 79501 Ogallala 345kV | Castro | SOLAR | 200 | 1/2020 | Incomplete
20INR0089 | Chisholm Grid Battery Storage | Able Grid Energy | 2081 Hicks 345kV or 2082 Hicks 138kV | Tarrant | BATTERY | 200 | 3/2020 | Incomplete
20INR0037 | Coniglio Solar | Belltown Power | 1809 Boistret 138kV | Fannin | SOLAR | 135 | 3/2020 | Incomplete
20INR0031 | Rippey Solar | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | SOLAR | 60 | 3/2020 | Incomplete
20INR0026 | Longbow Solar | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | SOLAR | 105 | 3/2020 | Incomplete
20INR0003 | Shorthorn Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 3/2020 | Incomplete
19INR0161 | Pierce Wind | Seventus | 345kV ROW between Hillje & WAP | Wharton | WIND | 300 | 3/2020 | Incomplete
19INR0160 | Great Dane Wind | Seventus | 5546 Danevang 138kV | Wharton | WIND | 302 | 3/2020 | Incomplete
19INR0091 | Phoenix Solar | Alpin Sun | 1808 Bonham 138kV | Fannin | SOLAR | 82 | 3/2020 | Incomplete
18INR0029 | Armstrong Wind | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | WIND | 253 | 3/2020 | Complete
20INR0060 | Owen Solar | Belltown Power | tap 138kV 177 Bosque - 181 Cayote | Bosque | SOLAR | 100 | 4/2020 | Incomplete
20INR0059 | Cowboy Newt Solar | Belltown Power | tap 69kV 224 Iasca - 225 Forreston | Hill | SOLAR | 45 | 4/2020 | Incomplete
19INR0179 | Barranca Wind II | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | WIND | 202 | 4/2020 | Incomplete
19INR0165 | Barranca Wind | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | WIND | 202 | 4/2020 | Incomplete
19INR0034 | Greasewood Solar | Onpeak Power | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | SOLAR | 200 | 4/2020 | Incomplete
19INR0026 | Holstein 2 Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 100 | 4/2020 | Incomplete
19INR0009 | Holstein Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 200 | 4/2020 | Incomplete
20INR0043 | Gulf Wind 2 | Pattern Energy | 80071 Zorillo 345kV | Kenedy | WIND | 180 | 5/2020 | Incomplete
19INR0123 | GSE Eleven | Alpin Sun | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | SOLAR | 135 | 5/2020 | Incomplete
19INR0020c | SP-Pecos Bend Solar C | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020b | SP-Pecos Bend Solar B | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020 | SP-Pecos Bend Solar A | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
18INR0062 | Wagyu Solar | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | SOLAR | 122 | 5/2020 | Complete
20INR0030 | Rustler Solar | Cypress Creek Renewables | tap 138kV 5827 Moore - 5895 Pearsall | Frio | SOLAR | 113 | 6/2020 | Incomplete
19INR0173 | Magnet Wind | Seventus | 8127 Lane City 138kV | Wharton | WIND | 125 | 6/2020 | Incomplete
19INR0081 | Anson Solar | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | SOLAR | 600 | 6/2020 | Incomplete
19INR0030 | San Bernard Solar | Sunchase Power | 43340 Tx Gulf Sulphur 138kV | Wharton | SOLAR | 100 | 6/2020 | Incomplete
17INR0033 | Tecovas 2 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 6/2020 | Incomplete
16INR0117 | Tecovas 1 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 6/2020 | Incomplete
20INR0002 | Lake Spring Solar | 8minutenergy | 79501 Ogallala 345kV | Castro | SOLAR | 400 | 6/2020 | Complete
20INR0091 | Misae Solar II | Latinoamericana de Energia | 60501 Tesla 345kV | Childress | SOLAR | 504 | 7/2020 | Incomplete
20INR0054 | Taygete Solar | 7x Energy | 6630 Fort Stockton 138kV or tap 138kV 60393 Pig Creek - 6673 Musquiz | Pecos | SOLAR | 250 | 7/2020 | Incomplete
20INR0042 | Chalupa Wind | Cielo | 5764 E Rio Hondo 138kV | Cameron | WIND | 145 | 7/2020 | Incomplete
20INR0024 | Is 177 | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | SOLAR | 25 | 7/2020 | Incomplete
20INR0021 | Garnet Solar | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOLAR | 20 | 7/2020 | Incomplete
20INR0019 | Trinity Hills Wind repower | Bp | 150751 & 150752 Trinity Hills 34.5kV | Young | WIND | -27 | 7/2020 | Incomplete
20INR0074 | Pitts Dudik Solar | Belltown Power | tap 138kV 234 Chatt - 3515 Hubbard | Hill | SOLAR | 75 | 8/2020 | Incomplete
20INR0036 | Stillwater Solar | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | SOLAR | 216 | 8/2020 | Incomplete
20INR0035 | Angus Solar | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | SOLAR | 188 | 8/2020 | Incomplete
20INR0025 | Spinel Solar | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | SOLAR | 30 | 8/2020 | Incomplete
20INR0023 | Agate Solar | Innovative Solar | 1906 Venus S 345kV | Ellis | SOLAR | 60 | 8/2020 | Incomplete
20INR0022 | Sandine Solar | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | SOLAR | 30 | 8/2020 | Incomplete
20INR0016 | Opal Solar | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | SOLAR | 45 | 8/2020 | Incomplete
20INR0015 | Citrine Solar | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | SOLAR | 45 | 8/2020 | Incomplete
20INR0014 | Obsidian Solar | Innovative Solar | 6131 Padr 69kV | Cottle | SOLAR | 60 | 8/2020 | Incomplete
20INR0013 | Basalt Solar | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOLAR | 20 | 8/2020 | Incomplete
20INR0012 | Lueders Solar | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | SOLAR | 40 | 8/2020 | Incomplete
20INR0046 | Maverick Creek II | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WIND | 252 | 9/2020 | Incomplete
20INR0045 | Maverick Creek I | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WIND | 252 | 9/2020 | Incomplete
19INR0042 | Long Point Solar | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Fort Bend | SOLAR | 100 | 9/2020 | Incomplete
20INR0005 | Shorthorn 2 Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 10/2020 | Incomplete
19INR0155 | Morrow Lake Solar | Sunchase Power | tap 138kV 5895 Pearsall - 5700 Miracle | Frio | SOLAR | 150 | 10/2020 | Incomplete
19INR0110 | Angelina Solar | EDP Renewables | 3349 TMPLinla 138kV | Angelina | SOLAR | 150 | 10/2020 | Incomplete
15INR0063b | Easter Wind B | TriGlobal | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 152 | 10/2020 | Complete
20INR0082 | Vision Solar | Alpin Sun | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | SOLAR | 127 | 11/2020 | Incomplete
19INR0151 | Impact Solar | Alpin Sun | tap 345kV 1695 Moses - 1692 Paris | Lamar | SOLAR | 187 | 11/2020 | Incomplete
19INR0134 | Cottonwood Bayou | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | SOLAR | 150 | 11/2020 | Incomplete
20INR0065 | Highwire Solar | Cypress Creek Renewables | tap 345kV 8164 Coleto - 8455 Lon Hill | Goliad | SOLAR | 375 | 12/2020 | Incomplete
20INR0055 | Vaquero 2 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | WIND | 202 | 12/2020 | Incomplete
20INR0048 | Century Oak Wind | Infinity Renewables | tap 138kV 6670 Putnam - 6317 Cisco | Callahan | WIND | 126 | 12/2020 | Incomplete
20INR0038 | Red Mud Creek | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WIND | 201 | 12/2020 | Incomplete
20INR0032 | IP Titan | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | SOLAR | 227 | 12/2020 | Incomplete
20INR0029 | JA Ranch | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WIND | 242 | 12/2020 | Incomplete
19INR0121 | Galloway Solar | 8minutenergy | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | SOLAR | 360 | 12/2020 | Incomplete
19INR0117 | Road Runner Crossing Wind 1 | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | WIND | 200 | 12/2020 | Incomplete
19INR0097 | Shamrock Wind II | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0096 | Shamrock Wind | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0075 | Horseshoe Bend Solar | Clenera | 1444 Brown 345kV | Coleman | SOLAR | 300 | 12/2020 | Incomplete
18INR0005 | Panda Sherman 2 G | Panda Funds | 1758 Payne 138kV | Grayson | GAS | 543 | 12/2020 | Incomplete
17INR0043 | Vaquero 1 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Brooks | WIND | 400 | 12/2020 | Incomplete
16INR0106 | Whatley Solar | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | SOLAR | 150 | 12/2020 | Incomplete
16INR0102 | Owego Solar | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | SOLAR | 74 | 12/2020 | Incomplete
16INR0101 | Chatee Solar | Hecate Energy | 6641 Sun Valley 69kV | Pecos | SOLAR | 57 | 12/2020 | Incomplete
16INR0099 | Hecate Solar | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | SOLAR | 33 | 12/2020 | Incomplete
16INR0085 | Priddy Wind | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | WIND | 300 | 12/2020 | Incomplete
15INR0062b | Hale Community W 2 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 122 | 12/2020 | Incomplete
15INR0062 | Hale Community W 1 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 200 | 12/2020 | Incomplete
08INR0019b | Grandview 5 W | Eon | 79005 Railhead 345kV | Gray | WIND | 249 | 12/2020 | Incomplete
16INR0033 | Hart Wind | Orion | 79501 Ogallala 345kV | Castro | WIND | 150 | 12/2020 | Complete
18INR0009 | Eagle Pines Gas | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | GAS | 1174 | 2/2021 | Incomplete
21INR0007 | Deepwater | Aes | 40450 Deepwater 345kV | Harris | GAS | 462 | 4/2021 | Incomplete
21INR0019 | Zier Solar | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOLAR | 180 | 11/2021 | Incomplete
18INR0034 | Blanco Canyon Wind | Invenergy | 59904 Cottonwood 345kV | Crosby | WIND | 251 | 12/2021 | Incomplete
16INR0119 | Wake Solar | Invenergy | 59904 Cottonwood 345kV | Crosby | SOLAR | 150 | 12/2021 | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## IA Table
Generation Interconnection Agreements as of May 31, 2018
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name* | Interconnecting Entity | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
18INR0013 | Denton Energy Center | Denton Municipal Electric | Denton | 2018-06-01 | GAS | 226 |  | Yes | Yes | Yes | N/A | Complete
17INR0068 | Sweetwater 2 repower | Leeward Energy | Nolan | 2018-06-01 | Wind | 7 |  | No | No | N/A | N/A | Complete
16INR0087 | RTS 1 Wind | Goldwind | McCulloch | 2018-06-01 | Wind | 160 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0086 | Cactus Flats Wind | Southern Power Company | Concho | 2018-06-01 | Wind | 148 |  | Yes | Yes | N/A | N/A | Complete
16INR0054 | NA | NASA | Harris | 2018-06-01 | Gas | 12 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0082 | Flat Top Wind I | Alterra Power | Comanche | 2018-06-01 | Wind | 200 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0045 | RIGGINS | NRG | Pecos | 2018-06-01 | Solar | 150 | Projected Date | Yes | Yes | N/A | N/A | Complete
13INR0049 | FEGC | Friendswood Energy Genco | Harris | 2018-06-01 | Gas | 129 | Projected Date | Yes | Yes | Yes | Yes | Complete
12INR0059b | HOVEY (Barilla Solar 1B) | First Solar | Pecos | 2018-06-01 | Solar | 7 | Projected Date | Yes | Yes | N/A | N/A | Complete
18INR0025 | Tahoka Wind | Lincoln Clean | Lynn | 2018-10-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
17INR0022 | MIRAGE | Net Power | Harris | 2018-10-01 | Gas | 11 |  | Yes | Yes | Yes | Yes | Complete
17INR0045 | VictPort | Castleman Power | Victoria | 2018-11-01 | Gas | 100 |  | No | Yes | Yes | Yes | Complete
18INR0035 | CityVict | Castleman Power | Victoria | 2018-11-01 | Gas | 100 |  | Yes | Yes | Yes | Yes | Incomplete
18INR0070 | Blue Summit II | Nextera | Wilbarger | 2018-12-01 | Wind | 102 | NEW | Yes | Yes | N/A | N/A | Complete
18INR0068 | Loraine Windpark Phase III | Third Planet Wind Power | Mitchell | 2018-12-01 | Wind | 100 |  | Yes | Yes | N/A | N/A | Complete
18INR0016 | RTS 2 Wind | RES Americas | McCulloch | 2018-12-01 | Wind | 150 | Project Name | No | No | N/A | N/A | Complete
16INR0115 | Waymark Solar | 174 Power Global | Pecos | 2018-12-01 | Solar | 182 |  | Yes | Yes | N/A | N/A | Complete
16INR0023b | Lamesa Solar B (Phase II) | OCI Solar Power | Dawson | 2018-12-01 | Solar | 50 |  | Yes | Yes | N/A | N/A | Complete
16INR0019 | BlueBell Solar | Nextera | Coke | 2018-12-01 | Solar | 30 |  | Yes | Yes | N/A | N/A | Complete
15INR0035 | Stella 1 Wind | Eon | Kenedy | 2018-12-01 | Wind | 201 |  | Yes | Yes | N/A | N/A | Complete
14INR0045 | Torrecillas Wind | Nextera | Webb | 2018-12-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
14INR0038 | BAC | PHR Holdings | Galveston | 2018-12-01 | Gas | 390 |  | Yes | Yes | Yes | N/A | Complete
12INR0060 | Infinity Live Oak Wind | Infinity Renewables | Schleicher | 2018-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Complete
11INR0054 | Midway Wind | Apex Clean | San Patricio | 2018-12-01 | Wind | 163 |  | Yes | Yes | N/A | N/A | Complete
13INR0010c | Mariah Del Sur | Mariah Acquisition | Parmer | 2018-12-01 | Wind | 218 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010a | Mariah Del Este | Mariah Acquisition | Parmer | 2018-12-01 | Wind | 152 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
16INR0076 | Hudson (Ineos/Brazoria) | Ineos | Brazoria | 2019-01-01 | Gas | 96 |  | Yes | Yes | Yes | Yes | Complete
16INR0037c | Pumpkin Farm Wind | Apex Clean | Floyd | 2019-01-01 | Wind | 281 |  | Yes | Yes | N/A | N/A | Complete
12INR0055 | Little Mountain Wind | Infinity Renewables | Baylor | 2019-03-01 | Wind | 80 | SFS | Yes | Yes | N/A | N/A | Incomplete
17INR0005 | Cabezon Wind | Longroad Energy | Starr | 2019-04-01 | Wind | 238 |  | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | NRG | Nueces | 2019-04-01 | Wind | 226 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010def | Scandia Wind DEF | Scandia Southwest | Parmer | 2019-05-01 | Wind | 600 |  | No | No | N/A | N/A | Complete
19INR0092 | Prospero Solar | Longroad Energy | Andrews | 2019-05-01 | Solar | 300 |  | No | No | N/A | N/A | Incomplete
17INR0027b | Coyote Wind | Lincoln Clean | Scurry | 2019-05-01 | Wind | 242 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0059 | Emerald Grove Solar | Cypress Creek Renewables | Pecos | 2019-05-01 | Solar | 108 |  | Yes | Yes | N/A | N/A | Incomplete
18INR0067 | Gopher Creek Wind | Terna Energy | Scurry | 2019-06-01 | Wind | 158 |  | Yes | Yes | N/A | N/A | Complete
16INR0003 | LEVEE (Freeport LNG) | Freeport LNG | Brazoria | 2019-06-01 | Gas | 11 |  | Yes | Yes | Yes | N/A | Complete
20INR0011 | Ranchero Wind | Scout Clean Energy | Crockett | 2019-06-01 | Wind | 300 | NEW | No | No | N/A | N/A | Incomplete
19INR0019 | Foard City Wind | Alterra Power | Foard | 2019-06-01 | Wind | 350 |  | No | No | N/A | N/A | Incomplete
16INR0062b | Lockett Wind | Lincoln Clean | Wilbarger | 2019-06-01 | Wind | 184 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0049 | Nazareth Solar | Lendlease Energy | Castro | 2019-06-01 | Solar | 201 | Projected Date | No | No | N/A | N/A | Incomplete
16INR0044 | Halyard Wharton | Halyard Energy | Wharton | 2019-06-01 | Gas | 419 |  | No | No | Yes | Yes | Incomplete
13INR0026 | Canadian Breaks Wind | Macquarie Cap | Oldham | 2019-07-01 | Wind | 210 |  | No | No | N/A | N/A | Complete
18INR0001 | Rockwood G | Lincoln Clean | Colorado | 2019-07-01 | Gas | 1122 |  | No | No | Yes | No | Incomplete
15INR0064b | Harald (BearKat Wind B) | TriGlobal | Glasscock | 2019-08-01 | Wind | 162 |  | Yes | Yes | N/A | N/A | Complete
14INR0033 | Goodnight Wind | FGE Power | Armstrong | 2019-08-01 | Wind | 497 |  | No | No | N/A | N/A | Complete
18INR0043 | Edmondson Ranch Wind | Wind Tex | Glasscock | 2019-09-01 | Wind | 292 |  | Yes | Yes | N/A | N/A | Complete
19INR0099a | Kontiki 1 Wind | TriGlobal | Glasscock | 2019-09-01 | Wind | 255 | NEW | Yes | Yes | N/A | N/A | Incomplete
19INR0163 | Sage Draw Wind | Lincoln Clean | Lynn | 2019-10-01 | Wind | 300 | Projected Date | No | No | N/A | N/A | Incomplete
19INR0029 | Phoebe Solar | Longroad Energy | Winkler | 2019-10-01 | Solar | 250 | NEW | Yes | Yes | N/A | N/A | Incomplete
18INR0004 | Shawnee G | Lincoln Clean | Hill | 2019-10-01 | Gas | 928 |  | No | No | Yes | No | Incomplete
15INR0079 | Pullman Road Wind | SunEdison | Randall | 2019-10-01 | Wind | 300 |  | No | No | N/A | N/A | Incomplete
15INR0050 | Unity Wind | Miller Wind | Deaf Smith | 2019-10-01 | Wind | 203 |  | No | No | N/A | N/A | Incomplete
14INR0009 | WKN Amadeus Wind | WKN | Kent | 2019-10-01 | Wind | 246 |  | No | No | N/A | N/A | Incomplete
13INR0038 | Wildrose Wind | S Power | Swisher | 2019-10-01 | Wind | 212 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0002a | Silver Canyon Wind A | EDP Renewables | Briscoe | 2019-10-01 | Wind | 200 |  | No | No | N/A | N/A | Incomplete
16INR0112 | Loma Pinta Wind | Enerverse | La Salle | 2019-11-01 | Wind | 200 | Projected Date, SFS | No | No | N/A | N/A | Complete
19INR0038 | High Lonesome W | Swift Current Energy | Crockett | 2019-11-01 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
18INR0022 | Winkler Solar | RES Americas | Winkler | 2019-12-01 | Solar | 150 | Project Name | No | No | N/A | N/A | Complete
18INR0018 | Peyton Creek Wind | Eon | Matagorda | 2019-12-01 | Wind | 150 | Projected Date, SFS | Yes | Yes | N/A | N/A | Complete
16INR0081 | Mesteno Wind | Duke Energy | Starr | 2019-12-01 | Wind | 202 | NEW | Yes | Yes | N/A | N/A | Complete
15INR0090 | Pflugerville Solar | RRE Solar | Travis | 2019-12-01 | Solar | 144 |  | No | No | N/A | N/A | Complete
19INR0074 | Karankawa 2 Wind | Avangrid | San Patricio | 2019-12-01 | Wind | 200 | Project Name, SFS | Yes | Yes | N/A | N/A | Incomplete
18INR0023 | Lost Mines Wind | RES Americas | Schleicher | 2019-12-01 | Wind | 201 | NEW | No | No | N/A | N/A | Incomplete
18INR0014 | Karankawa Wind | Avangrid | San Patricio | 2019-12-01 | Wind | 200 | Project Name, SFS | Yes | Yes | N/A | N/A | Incomplete
17INR0037 | Palmas Altas Wind | Acciona | Cameron | 2019-12-01 | Wind | 145 |  | No | No | N/A | N/A | Incomplete
17INR0020c | RE Maplewood 2c Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020b | RE Maplewood 2b Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020a | RE Maplewood 2a Solar | Recurrent Energy | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0114 | Upton Solar | SunPower | Upton | 2019-12-01 | Solar | 102 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0044 | West of Pecos Solar | Eon | Reeves | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0005c | Grandview W 3 | Eon | Carson | 2019-12-01 | Wind | 188 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Avangrid | Swisher | 2019-12-01 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
16INR0006 | Pinecrest G | Coronado Ventures | Angelina | 2020-04-01 | Gas | 785 |  | No | No | Yes | Yes | Incomplete
16INR0045 | Halyard Henderson | Halyard Energy | Henderson | 2020-06-01 | Gas | 432 |  | No | No | Yes | Yes | Complete
19INR0099b | Kontiki 2 Wind | TriGlobal | Glasscock | 2020-09-01 | Wind | 255 | NEW | Yes | Yes | N/A | N/A | Incomplete
17INR0010 | FGE Texas 2 Gas | FGE Power | Mitchell | 2020-09-01 | Gas | 743 |  | No | No | Yes | No | Incomplete
17INR0035 | Las Majadas Wind | EDF Renewable Energy | Willacy | 2020-10-01 | Wind | 227 | NEW | No | No | N/A | N/A | Incomplete
16INR0010 | FGE Texas 1 Gas | FGE Power | Mitchell | 2020-10-01 | Gas | 743 |  | No | No | Yes | Yes | Incomplete
15INR0013 | Apex Bethel CAES | Apex CAES | Anderson | 2020-11-01 | Gas/CE | 324 |  | No | No | Yes | Yes | Incomplete
20INR0058 | Longhorn South | EDF Renewable Energy | Briscoe | 2020-12-01 | Wind | 160 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020e | RE Maplewood 2e Solar | Recurrent Energy | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020d | RE Maplewood 2d Solar | Recurrent Energy | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0005 | Brownsville G | Tenaska | Cameron | 2020-12-01 | Gas | 871 |  | No | No | Yes | No | Incomplete
14INR0030c | Panhandle Wind 3 | Pattern Energy | Carson | 2020-12-01 | Wind | 248 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0023 | Indeck Wharton | Indeck | Wharton | 2021-09-01 | Gas | 654 |  | No | No | Yes | Yes | Complete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## QSA Units
GIR under Quarterly Stability Assessment (Study Period: May 1 ~ July 31, 2018)
INR | Project Name
11INR0054 | Midway Wind
12INR0060 | Infinity Live Oak Wind
15INR0035 | Stella 1 Wind
16INR0019 | BlueBell Solar
16INR0023b | Lamesa Solar B (Phase II)
16INR0037c | Pumpkin Farm Wind
16INR0076 | Hudson (Ineos/Brazoria)
16INR0115 | Waymark Solar
17INR0045 | VictPort
18INR0068 | Loraine Windpark Phase III
18INR0072 | Blue Summit Repower
13INR0010a | Mariah Del Este
14INR0045 | Torrecillas Wind

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
17INR0068 | Sweetwater 2 repower | Nolan | PLANNED | 2018-06-01 | 2017-11-17 | WIND | WT | 7 | 2018 | FALSE
15INR0082 | Flat Top Wind I | Comanche | PLANNED | 2018-06-15 | 2016-02-19 | WIND | WT | 200 | 2018 | TRUE
16INR0086 | Cactus Flats Wind | Concho | PLANNED | 2018-06-15 | 2017-03-15 | WIND | WT | 148 | 2018 | TRUE
16INR0087 | RTS 1 Wind | McCulloch | PLANNED | 2018-06-15 | 2015-10-14 | WIND | WT | 160 | 2018 | TRUE
18INR0025 | Tahoka Wind | Lynn | PLANNED | 2018-10-31 | 2018-01-03 | WIND | WT | 300 | 2018 | TRUE
12INR0060 | Infinity Live Oak Wind | Schleicher | PLANNED | 2018-12-01 | 2018-05-21 | WIND | WT | 200 | 2018 | TRUE
18INR0070 | Blue Summit II | Wilbarger | PLANNED | 2018-12-03 | 2018-04-28 | WIND | WT | 102 | 2018 | TRUE
11INR0054 | Midway Wind | San Patricio | PLANNED | 2018-12-15 | 2017-11-05 | WIND | WT | 163 | 2018 | TRUE
18INR0068 | Loraine Windpark Phase III | Mitchell | PLANNED | 2018-12-21 | 2018-04-10 | WIND | WT | 100 | 2018 | TRUE
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 152 | 2018 | TRUE
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 218 | 2018 | TRUE
14INR0045 | Torrecillas Wind | Webb | PLANNED | 2018-12-31 | 2018-04-12 | WIND | WT | 300 | 2018 | TRUE
15INR0035 | Stella 1 Wind | Kenedy | PLANNED | 2018-12-31 | 2017-08-02 | WIND | WT | 201 | 2018 | TRUE
18INR0016 | RTS 2 Wind | McCulloch | PLANNED | 2018-12-31 | 2017-11-21 | WIND | WT | 150 | 2018 | FALSE
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2019-01-31 | 2017-03-24 | WIND | WT | 281 | 2019 | TRUE
12INR0055 | Little Mountain Wind | Baylor | PLANNED | 2019-03-01 | 2017-12-04 | WIND | WT | 80 | 2019 | TRUE
11INR0062 | Patriot Wind | Nueces | PLANNED | 2019-04-01 | 2018-04-13 | WIND | WT | 226 | 2019 | TRUE
17INR0005 | Cabezon Wind | Starr | PLANNED | 2019-04-01 | 2017-08-03 | WIND | WT | 238 | 2019 | TRUE
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2019-05-01 | 2014-04-25 | WIND | WT | 600 | 2019 | FALSE
17INR0027b | Coyote Wind | Scurry | PLANNED | 2019-05-01 | 2016-08-09 | WIND | WT | 242 | 2019 | TRUE
16INR0062b | Lockett Wind | Wilbarger | PLANNED | 2019-06-01 | 2015-03-31 | WIND | WT | 184 | 2019 | TRUE
20INR0011 | Ranchero Wind | Crockett | PLANNED | 2019-06-04 | 2018-05-02 | WIND | WT | 300 | 2019 | FALSE
18INR0067 | Gopher Creek Wind | Scurry | PLANNED | 2019-06-26 | 2018-01-26 | WIND | WT | 158 | 2019 | TRUE
19INR0019 | Foard City Wind | Foard | PLANNED | 2019-06-30 | 2018-02-19 | WIND | WT | 350 | 2019 | FALSE
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2019-07-01 | 2016-05-20 | WIND | WT | 210 | 2019 | FALSE
15INR0064b | Harald (BearKat Wind B) | Glasscock | PLANNED | 2019-08-02 | 2016-12-20 | WIND | WT | 162 | 2019 | TRUE
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2019-08-11 | 2018-03-07 | WIND | WT | 497 | 2019 | FALSE
18INR0043 | Edmondson Ranch Wind | Glasscock | PLANNED | 2019-09-01 | 2017-10-04 | WIND | WT | 292 | 2019 | TRUE
19INR0099a | Kontiki 1 Wind | Glasscock | PLANNED | 2019-09-01 | 2018-05-07 | WIND | WT | 255 | 2019 | TRUE
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2019-10-01 | 2014-10-03 | WIND | WT | 203 | 2019 | FALSE
13INR0038 | Wildrose Wind | Swisher | PLANNED | 2019-10-30 | 2015-09-06 | WIND | WT | 212 | 2019 | TRUE
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2019-10-31 | 2016-06-22 | WIND | WT | 200 | 2019 | FALSE
14INR0009 | WKN Amadeus Wind | Kent | PLANNED | 2019-10-31 | 2018-03-15 | WIND | WT | 246 | 2019 | FALSE
15INR0079 | Pullman Road Wind | Randall | PLANNED | 2019-10-31 | 2014-05-29 | WIND | WT | 300 | 2019 | FALSE
19INR0163 | Sage Draw Wind | Lynn | PLANNED | 2019-10-31 | 2018-01-03 | WIND | WT | 300 | 2019 | FALSE
16INR0112 | Loma Pinta Wind | La Salle | PLANNED | 2019-11-30 | 2017-12-13 | WIND | WT | 200 | 2019 | FALSE
19INR0038 | High Lonesome W | Crockett | PLANNED | 2019-11-30 | 2018-04-17 | WIND | WT | 500 | 2019 | FALSE
18INR0018 | Peyton Creek Wind | Matagorda | PLANNED | 2019-12-01 | 2018-03-19 | WIND | WT | 150 | 2019 | TRUE
13INR0005c | Grandview W 3 | Carson | PLANNED | 2019-12-15 | 2014-04-23 | WIND | WT | 188 | 2019 | TRUE
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2019-12-31 | 2013-07-24 | WIND | WT | 500 | 2019 | FALSE
16INR0081 | Mesteno Wind | Starr | PLANNED | 2019-12-31 | 2018-04-25 | WIND | WT | 202 | 2019 | TRUE
17INR0037 | Palmas Altas Wind | Cameron | PLANNED | 2019-12-31 | 2017-11-30 | WIND | WT | 145 | 2019 | FALSE
18INR0014 | Karankawa Wind | San Patricio | PLANNED | 2019-12-31 | 2017-11-30 | WIND | WT | 200 | 2019 | TRUE
18INR0023 | Lost Mines Wind | Schleicher | PLANNED | 2019-12-31 | 2018-05-11 | WIND | WT | 201 | 2019 | FALSE
19INR0074 | Karankawa 2 Wind | San Patricio | PLANNED | 2019-12-31 | 2018-03-02 | WIND | WT | 200 | 2019 | TRUE
19INR0099b | Kontiki 2 Wind | Glasscock | PLANNED | 2020-09-01 | 2018-05-07 | WIND | WT | 255 | 2020 | TRUE
17INR0035 | Las Majadas Wind | Willacy | PLANNED | 2020-10-01 | 2018-04-13 | WIND | WT | 227 | 2020 | FALSE
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2020-12-01 | 2014-08-25 | WIND | WT | 248 | 2020 | TRUE
20INR0058 | Longhorn South | Briscoe | PLANNED | 2020-12-31 | 2012-12-10 | WIND | WT | 160 | 2020 | TRUE

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | PLANNED | 2018-06-30 | 2013-12-26 | SOLAR | PV | 7 | 2018 | TRUE
15INR0045 | RIGGINS | Pecos | PLANNED | 2018-06-30 | 2015-01-26 | SOLAR | PV | 150 | 2018 | TRUE
16INR0019 | BlueBell Solar | Coke | PLANNED | 2018-12-01 | 2015-08-19 | SOLAR | PV | 30 | 2018 | TRUE
16INR0115 | Waymark Solar | Pecos | PLANNED | 2018-12-15 | 2016-09-23 | SOLAR | PV | 182 | 2018 | TRUE
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2018-12-31 | 2016-07-28 | SOLAR | PV | 50 | 2018 | TRUE
19INR0092 | Prospero Solar | Andrews | PLANNED | 2019-05-01 | 2018-04-20 | SOLAR | PV | 300 | 2019 | FALSE
15INR0059 | Emerald Grove Solar | Pecos | PLANNED | 2019-05-31 | 2017-12-04 | SOLAR | PV | 108 | 2019 | TRUE
16INR0049 | Nazareth Solar | Castro | PLANNED | 2019-06-01 | 2018-05-10 | SOLAR | PV | 201 | 2019 | FALSE
19INR0029 | Phoebe Solar | Winkler | PLANNED | 2019-10-01 | 2018-03-05 | SOLAR | PV | 250 | 2019 | TRUE
15INR0090 | Pflugerville Solar | Travis | PLANNED | 2019-12-01 | 2017-06-13 | SOLAR | PV | 144 | 2019 | FALSE
16INR0114 | Upton Solar | Upton | PLANNED | 2019-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2019 | TRUE
14INR0044 | West of Pecos Solar | Reeves | PLANNED | 2019-12-15 | 2017-02-27 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
18INR0022 | Winkler Solar | Winkler | PLANNED | 2019-12-31 | 2018-01-23 | SOLAR | PV | 150 | 2019 | FALSE
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE
17INR0020e | RE Maplewood 2e Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE