## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 5/15-16/2018
Agenda Item: | Decision / Resolution | Action Items :
April 2018 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will have the finalized notes posted to the April 2018 meeting page.
Retail Market Subcommittee (RMS) Updates
NPRR850, Market Suspension and Restart—Left tabled waiting for comments to be submitted by other groups. | The Texas SET Chair provided the update.
Texas SET Additional Webpage Changes-- RMS determined that no vote was required, but RMS edits were added to the changes. | The Texas SET Chair provided the update.
RMGRR152, Additional Alignment with NPRR778, Modifications to Date Change and Cancellation Evaluation Window --Voted to approve with RMS edits. | The Texas SET Chair provided the update.
RMGRR153, Modifications to TDSP References and Processes in the Retail Market Guide—RMS voted to approve | The Texas SET Chair provided the update.
TX Market Test Plan Update/Revision-- RMS voted to table for one month. | The Texas SET Chair provided the update.
Flight Testing
Bank Change Type of Payment Sent Only--Testing Required?--Review TMTP Changes Feedback | No further changes were made to the TMTP. | The Texas SET Chair will present the updates at the June RMS meeting and request a vote to approve.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Discussion Items
o Issue with information not contained in 650_02 responses for Meter Tests.--Review CNP Feedback • CRs would like to have the meter test results contained in the free form text for the response. | Centerpoint is waiting for the feedback from their internal team. | Centerpoint will provide the update at the June 2018 meeting.
Extended Unplanned Outage Market Interface Service Provider (MISP)--Feedback Review | Texas SET finalized the analysis and updated the Lessons Learned document to be used by RMS leadership to create an agenda for a potential future RMS workshop. RMS leadership will present the findings and request direction from the Technical Advisory Committee (TAC) and discuss the need for an RMS workshop at the next RMS meeting. | The Texas SET Chair will have the updated document posted to the May 15th meeting page and send it to the Texas SET email distribution list.
Proposed Texas SET Release Changes.--Review Feedback | Texas SET leadership conducted a discussion on the current document and made changes where needed. Texas SET discussed how to re-instate a switch hold when a CR submits and completes a Switch Hold Removal MarkeTrak issue; then subsequently cancels the MVI due to an error on ESI ID. -Texas SET attendees suggested that the original CR submit the 650_01 to re-instate the DPP Switch Hold and submit a MarkeTrak issue to have the TDSP re-instate the Tampering Switch Hold. Texas SET discussed the possibility of automating the Inadvertent Gain / Loss process and will continue the discussion at the June 2018 meeting. Proposed new 650 codes were created for Turn Off and Turn On scenarios where a matching BGN number will not be required in order to have the reconnect transaction process successfully. Texas SET leadership will create a matrix of existing DCxxx and RCxxx codes contained in the 650s to facilitate future discussions. | Texas SET leadership will create a matrix of current DCxxx and RCxxx codes from the 650s to be used to document the current use of each code; then review at the next meeting. The updated document will be sent to the Texas SET email distribution list for discussion at the June meeting.
Mass Transition Yearly / Biannual Testing Needs? | Discussion was delayed until the next Texas SET meeting.
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
RMS assignments: | No new assignements
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Update on Draft RMGRR Progress-- 10/5/2017 Review PUCT Staff Feedback 10/19/2017 Review and make recommendation to RMS. | Oh Hold until 2018
Next Meeting--ERCOT MET Center--Joint TDTMS / Texas SET meeting | 2018-06-20
Attendees F-T-F
Diana Rehfeldt TNMP | Kyle Patrick NRG
Kaci Jacobs TXU Energy | Jim Lee AEP
Lindsay Butterfield ERCOT | Carolyn Reed Centerpoint Energy
Sam Pak ONCOR
Kathy Scott Centerpoint Energy
Attendees Webex
Becky Taylor Centerpoint Energy | Deb Belin MarketWise
Jacqueline Stevenson ECI | Kathryn Thurman ERCOT
Teresa Rodriguez Stream Energy | Mary Sithihao Stream Energy
Dave Pagliai ERCOT | Dave Michelsen ERCOT
Clint Sandage Calpine | Kim Wall (Hansen Technologies)
Deborah Croce ECInfoSystems