PWG Meeting Notes – June 18th, 2018

WebEx

1:30 – 3:00 pm

Attendees:

Lindsay Butterfield – ERCOT				
Bill Boswell – ERCOT

Calvin Opheim - ERCOT

Sam Pak – Oncor					
Sheri Wiegand – TXU

Kathy Scott - CNP

Carolyn Reed – CNP

Diana Rehfeldt – TNMP

Jim Lee – AEP

NRG

- Meeting minutes from May 23rd were approved as proposed with minor typo corrections.  Bill Boswell will post corrected meeting minutes to the meeting page.

- DRAFT NPRR & LPGRR, Annual Validation Process Revisions

  - Working Group reviewed ‘Revision Description’ and ‘Business Case’ language for both NPRR and LPGRR.  It was proposed the change of the default BUS profile from BUSMED to BUSLO would become effective January 1st, 2019 to allow TDSPs to prepare their systems/processes for the new default profile.

  - Kathy Scott and Sheri Wiegand will jointly sponsor both revisions.

  - Sheri will present both at the July RMS:

    - Endorsement of the NPRR

    - Approval of language of the LPGRR

  - The following is a timeline for both RRs:

| - NPRR posting deadline | PRS Language Consideration | PRS IA Review | TAC Consideration | Board Consideration | Effective Date |
| --- | --- | --- | --- | --- | --- |
| 7/3/2018 | 7/19/2018 | 8/16/2018 | 8/30/2018 | 10/9/2018 | 11/1/2018 |

| LPGRR posting deadline | RMS Language Consideration | RMS IA Review | TAC Consideration | Effective Date |  | Board Consideration (if project required or "Related" Revision Request) | Effective Date (if project required or "Related" Revision Request) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6/25/2018 | 7/10/2018 | 8/14/2018 | 8/30/2018 | 9/1/2018 |  | 10/9/2018 | 11/1/2018 |

*This LPGRR is related to the NPRR, so they will be implemented at the same time.

- Additional clean up from the TAC Structural Review revisions will be added to the NPRR and LPGRR where reference was made “to the appropriate TAC Subcommittee”.  Lindsay will also include a statement in the Revision Description and Business Case for clarity.  By including language in these (NPRR and LPGRR), an additional RR will not be needed.

- Annual Validation Update

- There will be no additional updates until after 9/30 – the deadline for the all 814_20 transactions to be completed by the TDSPs

- Visibility into DG for BUSIDRRQ profiles

  - Oncor reported they provided a count of the BUSIDRRQ customers for which they had an interconnect agreement and hence DG

  - Calvin confirmed with Oncor’s proposed NPRR allowing BUSIDRRQ customers to ‘opt-out’ of the profile and remain on a BUS profile, this will allow greater visibility into any DG behind those meters

- Questions/Issues for discussion at upcoming IDR workshop

  - Clarification, however, is needed around LPG Decision Tree on assignment of BUS profile for which a customer has installed some distributed generation (DG, PV, or WD) behind the meter.

    - Is the DG profile assigned only if the customer intends to inject surplus generation back onto the grid?

    - Is the DG profile assigned if an interconnection agreement is made with the customer at the premise?

    - Is the DG profile assigned only if a bi-directional or two channel (in and out) meter is installed/provisioned at the premise?

    - Are bi-directional or two channel meters only installed/provisioned if the customer has the potential to inject back onto the grid?

  - Clarity of these questions will assist ERCOT in assessing the amount of DG on the ERCOT grid.  For example…

    - If a large customer has back up generation behind the meter, at what point will they be given a DG profile?

    - If a customer installs PV panels, at what point will they be given a DG profile?

  - Sheri will forward these questions to the party facilitating the IDR workshop to ensure they are included in the discussion.

NEXT MEETING:  July 23rd only if language revisions/clarifications to the DRAFT NPRR/LPGRR are required.  Decision will be made after PRS on Thursday, July 19th.

Sam Pak to inform the WG if the meeting will be cancelled.

If this is the case, there will also be no meetings held August 29th nor September 26th.

Next meeting will be moved from October 22nd to October 9th @ 9:30 am – WebEx only.