## Projects
Generator Interconnection Status Report | July 2018
Date: 7/31/2018 7:17:37 PM

## Newly Operational & Cancelled
New Resources Approved for Synchronization
INR | Project | MW | Fuel | County | Part 2 Synch Approval
Resources Approved for Commercial Operation
INR | Project | MW | Fuel | County | Resource Commissioning Date*
18INR0013 | Denton Energy Center | 226 | Gas | Denton | 2018-07-11
14INR0038 | BAC | 390 | Gas | Galveston | 2018-07-11
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
Projects Cancelled by the Developer*
INR | Project | MW | Fuel | County | Cancellation Date*
20INR0058 | Longhorn South | 160 | Wind | Briscoe | 2018-07-20
19INR0152 | GSE Thirteen | 135 | Solar | Freestone | 2018-07-10
19INR0148 | Simmental Solar | 200 | Solar | Bexar | 2018-07-11
16INR0036 | Pecan Creek 1 Gas | 280 | Gas | Nolan | 2018-07-10
18INR0001 | Rockwood G | 1122 | Gas | Colorado | 2018-07-31
18INR0004 | Shawnee G | 928 | Gas | Hill | 2018-07-31
*Includes only those projects cancelled after the developer makes a Full Interconnection Study request.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | FIS Pending or Completed (MW) | IA Executed, FIS Pending or Approved (MW) | Grand Total (MW)**
Currently tracking 404 generation interconnection or change requests |  | Gas-AllOther | 0 | 779 | 1972 | 2751
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  | Gas-CombinedCycle | 3292 | 2046 | 3165 | 8503
July 31, 2018 | Number of Projects | Gas-Compressed Air (CE) | 0 | 0 | 324 | 324
Security Screening Studies (SSS) Underway | 34 | Total Gas | 3292 | 2825 | 5461 | 11578
SSS Completed | 60 | Nuclear | 0 |  | 0 | 0
Full Interconnect Study (FIS) Underway | 197 | Coal | 0 | 0 | 0 | 0
FIS Completed | 25 | Wind | 7624 | 18046 | 12027 | 37697
Interconnection Agreement Executed, FIS Pending | 41 | Battery | 322 | 200 | 0 | 522
Interconnection Agreement Executed | 47 | Solar | 8186 | 19318 | 2551 | 30055
Total Interconnection Requests | 404 | Biomass | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 6 | Petroleum Coke | 0 | 0 | 0 | 0
| Capacity, MW | Total | 19424 | 40389 | 20039 | 79852
Total Capacity Under Study * | 79852 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l). If the capacity for a single project is reported in the column, the value is redacted.
Interconnection Agreements Executed | 20039
Cancelled (since last month) | 2825 | ** Redacted project capacity from column E is excluded from the Grand Totals.
* Redacted project capacity is excluded. |  | Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
FIS Pending or Completed column: Total MW capacity for which an FIS is either pending or completed and reviewed by ERCOT. The column total matches the sum of capacity values reported in the Full Study tab.
IA Executed, FIS Pending or Approved column: Total MW capacity for which a FIS has been requested and approved, and an IA has been executed. The column total matches the sum of capacity values reported in the IA Table tab

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement as of July 31, 2018
GINR Reference Number | Project Name* | Interconnecting Entity | Point of Interconnection (POI) | County | Fuel | Capacity to Grid (MW) | Projected COD Month/Year (as specified by the resource developer) | FIS Report Status
18INR0077 | Colorado Bend 2 retune | Exelon |  | Wharton | GAS | 45 | 8/2018 | Incomplete
18INR0076 | Wolf Hollow 2 retune | Exelon |  | Hood | GAS | 44 | 8/2018 | Incomplete
17INR0070 | Desert Sky repower | Invenergy |  | Pecos | WIND | 7 | 8/2018 | Complete
17INR0067 | Sweetwater 1 repower | Leeward Energy | 180151 Sweetwater1 34.5kV | Nolan | WIND | 0 | 8/2018 | Complete
17INR0065 | Capricorn III repower | Nextera |  | Sterling | WIND | 0 | 8/2018 | Complete
17INR0064 | Capricorn II repower | Nextera |  | Sterling | WIND | 0 | 8/2018 | Complete
17INR0060 | Horse Hollow IV repower | Nextera |  | Taylor | WIND | 0 | 8/2018 | Complete
17INR0058 | Horse Hollow II repower | Nextera |  | Taylor | WIND | 0 | 8/2018 | Complete
17INR0057 | Red Canyon repower | Nextera |  | Borden | WIND | 0 | 8/2018 | Complete
17INR0069 | Trent repower | Invenergy |  | Nolan | WIND | 6 | 9/2018 | Complete
17INR0103 | Horse 3 repower | Nextera |  | Taylor | WIND | 0 | 11/2018 | Complete
17INR0101 | Horse 1 repower | Nextera |  | Taylor | WIND | 0 | 11/2018 | Complete
17INR0063 | Capricorn I repower | Nextera |  | Sterling | WIND | 0 | 11/2018 | Complete
17INR0061 | Capricorn IV repower | Nextera |  | Sterling | WIND | 9 | 11/2018 | Complete
17INR0056 | Callahan repower | Nextera |  | Taylor | WIND | 0 | 11/2018 | Complete
17INR0054 | Capricorn I & III repower | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WIND | 32 | 11/2018 | Complete
17INR0053 | HH3 (HHGT increase) | Nextera | 7046 Kendal 345kV | Taylor | WIND | 44 | 11/2018 | Complete
17INR0052 | HH1 (HHGT increase) | Nextera | 6216 Bluff Creek 138kV | Taylor | WIND | 44 | 11/2018 | Complete
18INR0080 | Woodward 2 repower | Nextera |  | Pecos | WIND | 0 | 12/2018 | Incomplete
18INR0078 | Bobcat Bluff Repowering | EDF Renewable Energy | 1475 Windthorst Switch 138-kV | Archer | WIND | 12 | 12/2018 | Incomplete
18INR0073 | Sweetwater 1 repower | Leeward Energy |  | Nolan | WIND | 3 | 12/2018 | Incomplete
18INR0072 | Blue Summit Repower | Nextera | 140382 Blue Summit 1.6 34.5kV | Wilbarger | WIND | 10 | 12/2018 | Incomplete
18INR0079 | Woodward I repower | Nextera |  | Pecos | WIND | 0 | 1/2019 | Incomplete
18INR0075 | Gulf Wind 1 Repower | Pattern Energy |  | Kenedy | WIND | 0 | 2/2019 | Incomplete
19INR0036 | Oxbow Solar | BNB Renewables | 59905 Faraday 345kV | Borden | SOLAR | 225 | 3/2019 | Incomplete
18INR0055 | Long Draw Solar | Engie | 59900 Long Draw 345kV | Borden | SOLAR | 225 | 3/2019 | Incomplete
19INR0057 | Old Bloomington Road | Castleman Power | 8143 Dupont 138kV | Victoria | GAS | 100 | 4/2019 | Incomplete
19INR0182 | Blue Summit Wind III | Nextera | 61001 Jim Treece 345kV | Wilbarger | WIND | 200 | 5/2019 | Incomplete
16INR0111 | Las Lomas Wind | Enerverse | 8957 Lopeno 138kV | Starr | WIND | 200 | 5/2019 | Incomplete
19INR0001 | Texas Solar Nova | SunPower | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | SOLAR | 750 | 6/2019 | Incomplete
18INR0040 | Soda Lake Solar 1 and 2 | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | SOLAR | 400 | 6/2019 | Complete
19INR0044 | Lily Solar | SunChase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | SOLAR | 150 | 7/2019 | Incomplete
19INR0041 | Myrtle Solar | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | SOLAR | 240 | 7/2019 | Incomplete
18INR0058 | Texana Solar | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOLAR | 150 | 8/2019 | Incomplete
18INR0050 | Mustang Creek Solar | Sunchase Power | 5523 ETP 138kV | Jackson | SOLAR | 150 | 8/2019 | Incomplete
19INR0174 | Elbow Creek repower | Nrg |  | Howard | WIND | 0 | 9/2019 | Incomplete
19INR0138 | Buffalo Gap 4 | Aes | 66216 Bluff Creek 138kV | Nolan | WIND | 175 | 9/2019 | Incomplete
18INR0039 | Fowler Ranch | Solar Prime | tap 138kV 60014 Spudder - 76615 Crane | Crane | SOLAR | 150 | 9/2019 | Incomplete
16INR0097 | Morada Del Sol Solar | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | SOLAR | 200 | 9/2019 | Incomplete
18INR0030 | Canyon Wind | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WIND | 360 | 9/2019 | Complete
19INR0166 | Loma Pinta II | Enerverse | 5705 Fowlerton 138kV | La Salle | WIND | 202 | 10/2019 | Incomplete
19INR0144 | Bird Dog Wind | Americlean | 1301 Willow Valley 138kV | Borden | WIND | 300 | 10/2019 | Incomplete
19INR0142 | Bacon Switch Solar | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher OR 138kV 1450 Pleasva – 1485 Ceramic | Wichita | SOLAR | 150 | 10/2019 | Incomplete
19INR0136 | Able Solar | Sunchase Power | 12469 Able Spring 138kV | Kaufman | SOLAR | 50 | 10/2019 | Incomplete
19INR0120 | Sherbino II Wind repower | Bp | 131454 Keo_3 138kV | Pecos | WIND | -13 | 10/2019 | Incomplete
19INR0080 | Whitehorse Wind | Hill Country Wind | 68001 Clayton 345kV | Fisher | WIND | 479 | 10/2019 | Incomplete
19INR0053 | Hidalgo II Wind | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | WIND | 51 | 10/2019 | Incomplete
18INR0056 | Hallmark Solar | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | SOLAR | 43 | 10/2019 | Incomplete
18INR0042 | Kaiser Creek Wind | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WIND | 100 | 10/2019 | Incomplete
18INR0027 | Ponwar Solar Farm | 8minutenergy | tap 138kV 76032 N McCamey - 60361 Santa Rita | Upton | SOLAR | 180 | 10/2019 | Incomplete
17INR0025 | Reloj Del Sol Wind | EDP Renewables | 80220 Cenizo 345kV | Zapata | WIND | 202 | 10/2019 | Incomplete
19INR0083 | Oberon Solar | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | SOLAR | 180 | 10/2019 | Complete
19INR0180 | Friendswood II | Quantum | 47170 HOC 138kV | Harris | GAS | 117 | 11/2019 | Incomplete
19INR0150 | Millhouse Solar | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOLAR | 113 | 11/2019 | Incomplete
19INR0149 | Lapetus Solar | 7x Energy | 1284 Shafter Lake 138kV | Andrews | SOLAR | 50 | 11/2019 | Incomplete
19INR0102 | Queen Solar | Cielo | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | SOLAR | 400 | 11/2019 | Incomplete
19INR0006 | Bluebonnet Solar | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | SOLAR | 61 | 11/2019 | Incomplete
18INR0031 | Maryneal Wind | Duke Energy | 71050 Bitter Creek 345kV | Nolan | WIND | 180 | 11/2019 | Incomplete
18INR0064 | Silver Star repower | Bp | 150511 Flat Creek 34.5kV | Eastland | WIND | -7 | 11/2019 | Complete
19INR0177 | Shanghai Wind | Seventus | 8104 Lane City PM 138kV | Wharton | WIND | 153 | 12/2019 | Incomplete
19INR0171 | Concho Valley Solar | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0156 | Grape Creek Wind | Apex Clean | tap 345kV 76009 TwinB - 76090 Divide | Coke | WIND | 524 | 12/2019 | Incomplete
19INR0145 | Hubbard Wind | Nextera | Loop into Tradinghouse to Sam Switch 345-kV line | Hill | WIND | 202 | 12/2019 | Incomplete
19INR0139 | Craver Ranch | S Power | tap 138kV 562 Aubrey - 672 Rector | Denton | SOLAR | 100 | 12/2019 | Incomplete
19INR0133 | Los Porciones II | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0132 | Los Porciones I | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0129 | Flatland Solar | Sunfinity Renewables | 1309 Bluftap 138kV or tap 138kV 1032 Morgan - 1064 Sun | Scurry | SOLAR | 180 | 12/2019 | Incomplete
19INR0128 | White Mesa Wind | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WIND | 500 | 12/2019 | Incomplete
19INR0124 | Solemio Springs | Alpin Sun | tap 138kV 1698 Sulphur Springs Switch - 1814 Sulphur Springs | Hopkins | SOLAR | 40 | 12/2019 | Incomplete
19INR0115 | Blackwater Draw Solar | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | SOLAR | 152 | 12/2019 | Incomplete
19INR0114 | Rambler Solar | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | SOLAR | 150 | 12/2019 | Incomplete
19INR0112 | Cranel Wind | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | WIND | 220 | 12/2019 | Incomplete
19INR0108 | WIT Ranch Wind | Eon | 6050 Lake Pauline 138kV | Hardeman | WIND | 200 | 12/2019 | Incomplete
19INR0103 | Rodeo Solar | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | SOLAR | 205 | 12/2019 | Incomplete
19INR0101 | Tehuacana Wind | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | WIND | 600 | 12/2019 | Incomplete
19INR0098 | Pease River Wind | Eon | 60500 Edith Clarke 345kV | Hardeman | WIND | 301 | 12/2019 | Incomplete
19INR0093 | Sole Mio | Alpin Sun | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | SOLAR | 45 | 12/2019 | Incomplete
19INR0085 | Blue Jay Solar | Open Road Renewables | 4 Iola 138kV | Grimes | SOLAR | 210 | 12/2019 | Incomplete
19INR0073 | Shakes Solar | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOLAR | 206 | 12/2019 | Incomplete
19INR0055 | Monte Cristo II W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0054 | Monte Cristo 1 W | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0052 | Truscott Gilliland East W | Chermac | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WIND | 278 | 12/2019 | Incomplete
19INR0049 | Buenos Aires 2 W | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0048 | Buenos Aires 1 W | Terra-Gen | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | WIND | 200 | 12/2019 | Incomplete
19INR0035 | Norton Solar | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | SOLAR | 125 | 12/2019 | Incomplete
19INR0033 | Murphy Lake Solar | S Power | 6904 CombinRC 138kV | Kaufman | SOLAR | 100 | 12/2019 | Incomplete
19INR0031 | Bestla Solar | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | SOLAR | 150 | 12/2019 | Incomplete
19INR0028 | Normande Solar Farm | 8minutenergy | 59900 Long Draw 345kV | Borden | SOLAR | 360 | 12/2019 | Incomplete
19INR0023 | West Willacy 3 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0022 | West Willacy 2 W | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 12/2019 | Incomplete
19INR0014 | Formosa Increase | Formosa Plastics |  | Calhoun | GAS | 240 | 12/2019 | Incomplete
19INR0002 | King Mountain Solar | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | SOLAR | 350 | 12/2019 | Incomplete
18INR0060 | Brightside Solar | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOLAR | 50 | 12/2019 | Incomplete
18INR0059 | Raymond Wind | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 202 | 12/2019 | Incomplete
18INR0057 | Green Valley Wind | Eon | Tap 138kV 8255 Hamilton - 8680 Rough Canyon | Val Verde | WIND | 500 | 12/2019 | Incomplete
18INR0051 | Byers Wind | Innergex | tap 345kV 6101 Riley - 1730 W Krum | Clay | WIND | 200 | 12/2019 | Incomplete
18INR0049 | Santa Rita Solar | Invenergy | 76005 Schneeman Draw 345kV | Crockett | SOLAR | 400 | 12/2019 | Incomplete
18INR0044 | Bluegrove Wind | Innergex | tap 138kV 1468 LKAROWHD - 1470 NEWPRT_P | Clay | WIND | 100 | 12/2019 | Incomplete
17INR0038 | Zapata II W | Nextera | 80220 Cenizo 345kV | Zapata | WIND | 400 | 12/2019 | Incomplete
17INR0036 | Grandview 4 Phase A Wind | Eon | tap 345kV 79000 Gray - 79006 Allen | Gray | WIND | 200 | 12/2019 | Incomplete
17INR0031 | Espiritu Wind | Apex Clean | 5764 E Rio Hondo 138kV | Cameron | WIND | 148 | 12/2019 | Incomplete
17INR0030 | Estacado Solar | Avangrid | 79502 Windmill 345kV | Deaf Smith | SOLAR | 100 | 12/2019 | Incomplete
16INR0105 | Zapata I W | Nextera | 80230 Molina 138kV | Jim Hogg | WIND | 300 | 12/2019 | Incomplete
16INR0104 | Big Sampson Wind | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WIND | 400 | 12/2019 | Incomplete
16INR0074 | Chocolate Bayou W | Infinity Renewables | tap 138kV 42090 Amoco - 42940 Monsanto | Brazoria | WIND | 150 | 12/2019 | Incomplete
16INR0014b | Cattleman Wind B | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0014 | Cattleman Wind A | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | WIND | 202 | 12/2019 | Incomplete
16INR0012 | Stella 2 Wind | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | WIND | 201 | 12/2019 | Incomplete
15INR0051 | Tierra Blanca W | Eon | 79501 Ogallala 345kV | Randall | WIND | 200 | 12/2019 | Incomplete
15INR0044 | Corazon Solar | Enerverse | 80219 Lobo 345kV | Webb | SOLAR | 200 | 12/2019 | Incomplete
15INR0034 | El Algodon Alto W | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | WIND | 201 | 12/2019 | Incomplete
19INR0100 | Prairie Hill Wind | Infinity Renewables | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | Limestone | WIND | 300 | 12/2019 | Complete
20INR0050 | Castro Solar | Oaktree Development | 79501 Ogallala 345kV | Castro | SOLAR | 200 | 1/2020 | Incomplete
18INR0062 | Wagyu Solar | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | SOLAR | 122 | 2/2020 | Incomplete
20INR0089 | Chisholm Grid Battery Storage | Able Grid Energy | 2081 Hicks 345kV or 2082 Hicks 138kV | Tarrant | STORAGE | 200 | 3/2020 | Incomplete
20INR0037 | Coniglio Solar | Belltown Power | 1809 Boistret 138kV | Fannin | SOLAR | 135 | 3/2020 | Incomplete
20INR0031 | Rippey Solar | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | SOLAR | 60 | 3/2020 | Incomplete
20INR0026 | Longbow Solar | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | SOLAR | 105 | 3/2020 | Incomplete
20INR0003 | Shorthorn Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 3/2020 | Incomplete
19INR0172 | Dillon Gulch | Aes | tap 345kV 11420 Sweetwater East Switch - 11406 Central Bluff Switch | Nolan | WIND | 175 | 3/2020 | Incomplete
19INR0161 | Pierce Wind | Seventus | 345kV ROW between Hillje & WAP | Wharton | WIND | 300 | 3/2020 | Incomplete
19INR0160 | Great Dane Wind | Seventus | 5546 Danevang 138kV | Wharton | WIND | 302 | 3/2020 | Incomplete
19INR0091 | Phoenix Solar | Alpin Sun | 1808 Bonham 138kV | Fannin | SOLAR | 82 | 3/2020 | Incomplete
18INR0053 | Fort Bend Solar | Lendlease Energy | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | SOLAR | 240 | 3/2020 | Incomplete
18INR0029 | Armstrong Wind | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | WIND | 253 | 3/2020 | Complete
20INR0060 | Owen Solar | Belltown Power | tap 138kV 177 Bosque - 181 Cayote | Bosque | SOLAR | 100 | 4/2020 | Incomplete
20INR0059 | Cowboy Newt Solar | Belltown Power | tap 69kV 224 Iasca - 225 Forreston | Hill | SOLAR | 45 | 4/2020 | Incomplete
19INR0179 | Barranca Wind II | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | WIND | 202 | 4/2020 | Incomplete
19INR0165 | Barranca Wind | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | WIND | 202 | 4/2020 | Incomplete
19INR0034 | Greasewood Solar | Onpeak Power | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | SOLAR | 200 | 4/2020 | Incomplete
19INR0026 | Holstein 2 Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 100 | 4/2020 | Incomplete
19INR0009 | Holstein Solar | 8minutenergy | 11406 Central Bluff 345kV | Nolan | SOLAR | 200 | 4/2020 | Incomplete
20INR0129 | Foxtrot Wind | Lincoln Clean Energy |  | Karnes | WIND | 504 | 5/2020 | Incomplete
20INR0043 | Gulf Wind 2 | Pattern Energy | 80071 Zorillo 345kV | Kenedy | WIND | 180 | 5/2020 | Incomplete
19INR0123 | GSE Eleven | Alpin Sun | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | SOLAR | 135 | 5/2020 | Incomplete
19INR0020c | SP-Pecos Bend Solar C | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020b | SP-Pecos Bend Solar B | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0020 | SP-Pecos Bend Solar A | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | SOLAR | 180 | 5/2020 | Incomplete
19INR0056 | Chamon 2 | Castleman Power | 40260 Chamon 138kV | Harris | GAS | 100 | 5/2020 | Complete
20INR0030 | Rustler Solar | Cypress Creek Renewables | tap 138kV 5827 Moore - 5895 Pearsall | Frio | SOLAR | 113 | 6/2020 | Incomplete
19INR0173 | Magnet Wind | Seventus | 43190 S_LANE_B138 (South Lane City) | Wharton | WIND | 125 | 6/2020 | Incomplete
19INR0168 | Philosun | Alpin Sun | tap 345kV 1906 Venus - 68090 Sam Switch | Hill | SOLAR | 127 | 6/2020 | Incomplete
19INR0131 | Cutlass Solar | Lendlease Energy | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | SOLAR | 300 | 6/2020 | Incomplete
19INR0081 | Anson Solar | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | SOLAR | 600 | 6/2020 | Incomplete
19INR0030 | San Bernard Solar | Sunchase Power | 43340 Tx Gulf Sulphur 138kV | Wharton | SOLAR | 100 | 6/2020 | Incomplete
17INR0033 | Tecovas 2 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 6/2020 | Incomplete
16INR0117 | Tecovas 1 W | Infinity Renewables | 79503 Tule Canyon 345kV | Briscoe | WIND | 200 | 6/2020 | Incomplete
20INR0091 | Misae Solar II | Latinoamericana de Energia | 60501 Tesla 345kV | Childress | SOLAR | 504 | 7/2020 | Incomplete
20INR0054 | Taygete Solar | 7x Energy | 6630 Fort Stockton 138kV or tap 138kV 60393 Pig Creek - 6673 Musquiz | Pecos | SOLAR | 250 | 7/2020 | Incomplete
20INR0042 | Chalupa Wind | Cielo | 5764 E Rio Hondo 138kV | Cameron | WIND | 145 | 7/2020 | Incomplete
20INR0024 | Is 177 | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | SOLAR | 25 | 7/2020 | Incomplete
20INR0021 | Garnet Solar | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOLAR | 20 | 7/2020 | Incomplete
20INR0074 | Pitts Dudik Solar | Belltown Power | tap 138kV 234 Chatt - 3515 Hubbard | Hill | SOLAR | 75 | 8/2020 | Incomplete
20INR0036 | Stillwater Solar | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | SOLAR | 216 | 8/2020 | Incomplete
20INR0035 | Angus Solar | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | SOLAR | 188 | 8/2020 | Incomplete
20INR0025 | Spinel Solar | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | SOLAR | 30 | 8/2020 | Incomplete
20INR0023 | Agate Solar | Innovative Solar | 1906 Venus S 345kV | Ellis | SOLAR | 60 | 8/2020 | Incomplete
20INR0022 | Sandine Solar | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | SOLAR | 30 | 8/2020 | Incomplete
20INR0016 | Opal Solar | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | SOLAR | 45 | 8/2020 | Incomplete
20INR0015 | Citrine Solar | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | SOLAR | 45 | 8/2020 | Incomplete
20INR0014 | Obsidian Solar | Innovative Solar | 6131 Padr 69kV | Cottle | SOLAR | 60 | 8/2020 | Incomplete
20INR0013 | Basalt Solar | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOLAR | 20 | 8/2020 | Incomplete
20INR0012 | Lueders Solar | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | SOLAR | 40 | 8/2020 | Incomplete
20INR0088 | West Raymond Wind | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | WIND | 200 | 9/2020 | Incomplete
20INR0046 | Maverick Creek II | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WIND | 252 | 9/2020 | Incomplete
20INR0045 | Maverick Creek I | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WIND | 252 | 9/2020 | Incomplete
19INR0147 | Delong Solar | Eon | tap 345kV 76009 TwinB - 1444 Brown | Tom Green | SOLAR | 200 | 9/2020 | Incomplete
19INR0042 | Long Point Solar | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Fort Bend | SOLAR | 100 | 9/2020 | Incomplete
20INR0033 | Cooke Wind II | EDP Renewables | tap 345kV 1730 KrumW - 2373 Anna | Cooke | WIND | 152 | 10/2020 | Incomplete
20INR0005 | Shorthorn 2 Solar | 8minutenergy | 60501 Tesla 345kV | Childress | SOLAR | 200 | 10/2020 | Incomplete
19INR0155 | Morrow Lake Solar | Sunchase Power | tap 138kV 5895 Pearsall - 5700 Miracle | Frio | SOLAR | 150 | 10/2020 | Incomplete
19INR0135 | Hill Solar | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasco | Hill | SOLAR | 80 | 10/2020 | Incomplete
19INR0007 | Charbray Solar | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | SOLAR | 200 | 10/2020 | Incomplete
20INR0082 | Vision Solar | Alpin Sun | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | SOLAR | 127 | 11/2020 | Incomplete
20INR0081 | Strategic Energy | Alpin Sun | Tap 345kV 2435 Watermill - 68091 Navarro OR Tap 138kV ENNS_W_8(2241) to ENNSTRAC_8 (12241) | Ellis | SOLAR | 135 | 11/2020 | Incomplete
20INR0019 | Trinity Hills Wind repower | Bp | 150751 & 150752 Trinity Hills 34.5kV | Young | WIND | -27 | 11/2020 | Incomplete
19INR0151 | Impact Solar | Alpin Sun | tap 345kV 1695 Moses - 1692 Paris | Lamar | SOLAR | 197 | 11/2020 | Incomplete
19INR0134 | Cottonwood Bayou | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | SOLAR | 150 | 11/2020 | Incomplete
20INR0126 | Robles Solar | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOLAR | 300 | 12/2020 | Incomplete
20INR0111 | Dusky Solar | Cypress Creek Renewables | tap 138kV 3522 Hillsboro -3546 Lake Whitney | Hill | SOLAR | 248 | 12/2020 | Incomplete
20INR0065 | Highwire Solar | Cypress Creek Renewables | tap 345kV 8164 Coleto - 8455 Lon Hill | Goliad | SOLAR | 375 | 12/2020 | Incomplete
20INR0055 | Vaquero 2 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | WIND | 202 | 12/2020 | Incomplete
20INR0053 | Bravepost Solar | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | SOLAR | 200 | 12/2020 | Incomplete
20INR0048 | Century Oak Wind | Infinity Renewables | tap 138kV 6670 Putnam - 6317 Cisco | Callahan | WIND | 126 | 12/2020 | Incomplete
20INR0038 | Red Mud Creek | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WIND | 201 | 12/2020 | Incomplete
20INR0032 | IP Titan | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | SOLAR | 227 | 12/2020 | Incomplete
20INR0029 | JA Ranch | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WIND | 242 | 12/2020 | Incomplete
19INR0169 | Sun Valley | Alpin Sun | tap 345kV 68091 Navarro - 68040 Kopperl | Hill | SOLAR | 135 | 12/2020 | Incomplete
19INR0167 | Gold Creek Solar | S Power | 1163 Lamesa 138kV | Dawson | SOLAR | 140 | 12/2020 | Incomplete
19INR0121 | Galloway Solar | 8minutenergy | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | SOLAR | 360 | 12/2020 | Incomplete
19INR0117 | Road Runner Crossing Wind 1 | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | WIND | 200 | 12/2020 | Incomplete
19INR0113 | County Line Solar | S Power | 60385 Solstice 138kV, Tap between Pigcreek (60393) and TNFLATTOP (38069) | Pecos | SOLAR | 250 | 12/2020 | Incomplete
19INR0097 | Shamrock Wind II | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0096 | Shamrock Wind | Eon | 76005 Schneeman Draw 345kV | Crockett | WIND | 202 | 12/2020 | Incomplete
19INR0075 | Horseshoe Bend Solar | Clenera | 1444 Brown 345kV | Coleman | SOLAR | 300 | 12/2020 | Incomplete
19INR0070 | Trevino Solar | S Power | 78015 Rosita 138kV | Maverick | SOLAR | 216 | 12/2020 | Incomplete
19INR0017 | Tri-County Solar | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | SOLAR | 207 | 12/2020 | Incomplete
18INR0065 | Goodranch Solar | EDF Renewable Energy | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | SOLAR | 200 | 12/2020 | Incomplete
18INR0005 | Panda Sherman 2 G | Panda Funds | 1758 Payne 138kV | Grayson | GAS | 543 | 12/2020 | Incomplete
17INR0043 | Vaquero 1 Wind | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Brooks | WIND | 400 | 12/2020 | Incomplete
16INR0106 | Whatley Solar | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | SOLAR | 150 | 12/2020 | Incomplete
16INR0102 | Owego Solar | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | SOLAR | 74 | 12/2020 | Incomplete
16INR0101 | Chatee Solar | Hecate Energy | 6641 Sun Valley 69kV | Pecos | SOLAR | 57 | 12/2020 | Incomplete
16INR0099 | Hecate Solar | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | SOLAR | 33 | 12/2020 | Incomplete
16INR0085 | Priddy Wind | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | WIND | 300 | 12/2020 | Incomplete
15INR0062b | Hale Community W 2 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 122 | 12/2020 | Incomplete
15INR0062 | Hale Community W 1 | Nextera | 79506 Abernathy 345kV | Hale | WIND | 200 | 12/2020 | Incomplete
08INR0019b | Grandview 5 W | Eon | 79005 Railhead 345kV | Gray | WIND | 249 | 12/2020 | Incomplete
19INR0045 | Rayos Del Sol | Tradewind Energy | FIS considered tap Wesmer and Rangerville 138 | Cameron | SOLAR | 150 | 12/2020 | Complete
16INR0033 | Hart Wind | Orion | 79501 Ogallala 345kV | Castro | WIND | 150 | 12/2020 | Complete
21INR0020 | El Zorro Solar | Cypress Creek Renewables | 8297 Bruni 138kV or tap 80439 La Quinta - 8297 Bruni 138kV | Webb | SOLAR | 375 | 2/2021 | Incomplete
18INR0009 | Eagle Pines Gas | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | GAS | 1174 | 2/2021 | Incomplete
21INR0007 | Deepwater | Aes | 40450 Deepwater 345kV | Harris | GAS | 462 | 4/2021 | Incomplete
21INR0019 | Zier Solar | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOLAR | 180 | 5/2021 | Incomplete
21INR0022 | Red Holly | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | SOLAR | 250 | 7/2021 | Incomplete
21INR0021 | Green Holly | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | SOLAR | 450 | 8/2021 | Incomplete
19INR0111 | Tom Green Solar | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | SOLAR | 150 | 10/2021 | Incomplete
19INR0110 | Angelina Solar | EDP Renewables | 3349 TMPLinla 138kV | Angelina | SOLAR | 150 | 10/2021 | Incomplete
20INR0040 | Montgomery Ranch Wind | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WIND | 200 | 12/2021 | Incomplete
20INR0039 | Red Mud Creek II | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WIND | 102 | 12/2021 | Incomplete
18INR0034 | Blanco Canyon Wind | Invenergy | 59904 Cottonwood 345kV | Crosby | WIND | 251 | 12/2021 | Incomplete
16INR0119 | Wake Solar | Invenergy | 59904 Cottonwood 345kV | Crosby | SOLAR | 150 | 12/2021 | Incomplete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## IA Table
Generation Interconnection Agreements as of July 31, 2018
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name* | Interconnecting Entity | Point of Interconnection (POI) | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
17INR0068 | Sweetwater 2 repower | Leeward Energy | 180153 Sweetwater3 34.5kV | Nolan | 2018-08-01 | WIND | 7 |  | No | No | N/A | N/A | Complete
16INR0087 | RTS 1 Wind | Goldwind | 76006 Bow Wood 345kV | McCulloch | 2018-08-01 | WIND | 160 |  | Yes | Yes | N/A | N/A | Complete
16INR0086 | Cactus Flats Wind | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | 2018-08-01 | WIND | 148 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0082 | Flat Top Wind I | Alterra Power | 11441 Flat Top 345kV | Comanche | 2018-08-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Complete
13INR0049 | FEGC | Friendswood Energy Genco | 47150 HOC 138kV | Harris | 2018-08-01 | GAS | 129 | Projected Date | Yes | Yes | Yes | Yes | Complete
12INR0059b | HOVEY (Barilla Solar 1B) | First Solar | 181651 Hovey 34.5kV | Pecos | 2018-08-01 | SOLAR | 7 |  | Yes | Yes | N/A | N/A | Complete
16INR0054 | NA | NASA | 42970 Nasa 138kV | Harris | 2018-09-01 | GAS | 12 |  | Yes | Yes | N/A | N/A | Complete
18INR0025 | Tahoka Wind | Lincoln Clean | 79641 Farmland 345kV | Lynn | 2018-10-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Complete
17INR0022 | MIRAGE | Net Power | 111161 Mirage 13.8kV | Harris | 2018-10-01 | GAS | 11 |  | Yes | Yes | Yes | Yes | Complete
18INR0035 | CityVict | Castleman Power | 8172 Victoria 138kV | Victoria | 2018-11-01 | GAS | 100 |  | Yes | Yes | Yes | Yes | Complete
17INR0104 | Capricorn 4 repower | Nextera |  | Coke | 2018-11-01 | WIND | 0 | Projected Date | No | No | N/A | N/A | Complete
17INR0045 | VictPort | Castleman Power | 8143 Dupont 138kV | Victoria | 2018-11-01 | GAS | 100 |  | No | Yes | Yes | Yes | Complete
18INR0068 | Loraine Windpark Phase III | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | 2018-12-01 | WIND | 100 |  | Yes | Yes | N/A | N/A | Complete
16INR0115 | Waymark Solar | 174 Power Global | 76002 Bakersfield 345kV | Pecos | 2018-12-01 | SOLAR | 182 |  | Yes | Yes | N/A | N/A | Complete
16INR0023b | Lamesa Solar B (Phase II) | OCI Solar Power | 1163 Lamesa 138kV | Dawson | 2018-12-01 | SOLAR | 50 |  | Yes | Yes | N/A | N/A | Complete
16INR0019 | BlueBell Solar | Nextera | 76090 Divide 345kV | Coke | 2018-12-01 | SOLAR | 30 |  | Yes | Yes | N/A | N/A | Complete
15INR0035 | Stella 1 Wind | Eon | 80076 Ajo 345kV | Kenedy | 2018-12-01 | WIND | 201 |  | Yes | Yes | N/A | N/A | Complete
14INR0045 | Torrecillas Wind | Nextera | 161252, 161301 Torrecillas 34.5kV | Webb | 2018-12-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Complete
12INR0060 | Wilson Ranch | ENGIE | 76003 Big Hill 345kV | Schleicher | 2018-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Complete
11INR0054 | Midway Wind | Apex Clean | 8961 Whitepoint 138kV | San Patricio | 2018-12-01 | WIND | 163 |  | Yes | Yes | N/A | N/A | Complete
13INR0010c | Mariah Del Sur | Mariah Acquisition | 141765 Mariah 345kV | Parmer | 2018-12-01 | WIND | 218 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010a | Mariah Del Este | Mariah Acquisition | 141765 Mariah 345kV | Parmer | 2018-12-01 | WIND | 152 |  | Yes | Yes | N/A | N/A | Incomplete
18INR0070 | Blue Summit II | Nextera | 61001 Jim Treece 345kV | Wilbarger | 2019-01-01 | WIND | 102 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0076 | Hudson (Ineos/Brazoria) | Ineos | 42100 Hudson 138kV | Brazoria | 2019-01-01 | GAS | 96 |  | Yes | Yes | Yes | Yes | Complete
18INR0069 | Indian Mesa Repower | Nextera | 76019 Indian NWP 138kV | Pecos | 2019-01-01 | WIND | 0 |  | No | No | N/A | N/A | Incomplete
17INR0005 | Cabezon Wind | Longroad Energy | 80355 Del Sol 345kV | Starr | 2019-04-01 | WIND | 238 |  | Yes | Yes | N/A | N/A | Complete
12INR0055 | S_Hills Wind | Engie | tap 69kV radial LakeKempSw 782 - LakeKemp 783 | Baylor | 2019-04-01 | WIND | 30 | Project Name, MW For Grid | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | NRG | 85000 Nelson Sharpe 345kV | Nueces | 2019-04-01 | WIND | 226 |  | Yes | Yes | N/A | N/A | Complete
13INR0010def | Scandia Wind DEF | Scandia Southwest | 141765 Mariah 345kV | Parmer | 2019-05-01 | WIND | 600 |  | No | No | N/A | N/A | Complete
19INR0092 | Prospero Solar | Longroad Energy | 79650 Clearfork 345kV | Andrews | 2019-05-01 | SOLAR | 300 |  | No | No | N/A | N/A | Incomplete
18INR0067 | Gopher Creek Wind | Terna Energy | 11306 Dermott 138kV | Scurry | 2019-06-01 | WIND | 158 |  | Yes | Yes | N/A | N/A | Complete
18INR0033 | Oveja Wind | Invenergy | 76005 Schneeman Draw 345kV | Irion | 2019-06-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Complete
16INR0003 | LEVEE (Freeport LNG) | Freeport LNG | 43336 Oyster Cr 138kV | Brazoria | 2019-06-01 | GAS | 11 |  | Yes | Yes | Yes | N/A | Complete
20INR0011 | Ranchero Wind | Scout Clean Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | 2019-06-01 | WIND | 300 | SFS | Yes | Yes | N/A | N/A | Incomplete
16INR0049 | Nazareth Solar | Lendlease Energy | 79501 Ogallala 345kV | Castro | 2019-06-01 | SOLAR | 201 |  | No | No | N/A | N/A | Incomplete
15INR0064b | Harald (BearKat Wind B) | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2019-08-01 | WIND | 162 |  | Yes | Yes | N/A | N/A | Complete
14INR0033 | Goodnight Wind | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | 2019-08-01 | WIND | 497 |  | No | No | N/A | N/A | Complete
17INR0037 | Palmas Altas Wind | Acciona | 5760 PALMAS 138 kV | Cameron | 2019-08-01 | WIND | 145 | Projected Date | No | No | N/A | N/A | Incomplete
18INR0043 | Edmondson Ranch Wind | Wind Tex | 59903 Bearkat 345kV | Glasscock | 2019-09-01 | WIND | 292 |  | Yes | Yes | N/A | N/A | Complete
13INR0026 | Canadian Breaks Wind | Macquarie Cap | Tap 345kV 79502 Windmill - 79504 AJ Swope | Oldham | 2019-09-01 | WIND | 210 |  | No | No | N/A | N/A | Complete
13INR0025 | Northdraw Wind | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | 2019-09-01 | WIND | 150 |  | No | No | N/A | N/A | Complete
19INR0099a | Kontiki 1 Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2019-09-01 | WIND | 255 |  | Yes | Yes | N/A | N/A | Incomplete
19INR0019 | Foard City Wind | Alterra Power | 60500 Edith Clarke 345kV | Foard | 2019-09-01 | WIND | 350 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0062b | Lockett Wind | Lincoln Clean | 141355-6 Electra 34.5kV | Wilbarger | 2019-09-01 | WIND | 184 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
18INR0045 | Misae Solar |  | 60501 Tesla 345kV | Childress | 2019-10-01 | SOLAR | 241 |  | No | No | N/A | N/A | Complete
18INR0016 | RTS 2 Wind | RES Americas | 76006 Bow Wood 345kV | McCulloch | 2019-10-01 | WIND | 150 | Projected Date | Yes | Yes | N/A | N/A | Complete
19INR0163 | Sage Draw Wind | Lincoln Clean | 79641 Farmland 345kV | Lynn | 2019-10-01 | WIND | 300 |  | No | No | N/A | N/A | Incomplete
19INR0029 | Phoebe Solar | Longroad Energy | tap 138kV 1250 Yukon - 1252 Vest | Winkler | 2019-10-01 | SOLAR | 250 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0050 | Unity Wind | Miller Wind | 79502 Windmill 345kV | Deaf Smith | 2019-10-01 | WIND | 203 |  | No | No | N/A | N/A | Incomplete
14INR0009 | WKN Amadeus Wind | WKN | tap 345kV 11305 Dermott - 60704 Kirchhof | Kent | 2019-10-01 | WIND | 246 |  | No | No | N/A | N/A | Incomplete
13INR0038 | Wildrose Wind | S Power | 79501 Ogallala 345kV | Swisher | 2019-10-01 | WIND | 212 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0002a | Silver Canyon Wind A | EDP Renewables | 79503 Tule Canyon 345kV | Briscoe | 2019-10-01 | WIND | 200 |  | No | No | N/A | N/A | Incomplete
16INR0112 | Loma Pinta Wind | Enerverse | 5705 Fowlerton 138kV | La Salle | 2019-11-01 | WIND | 200 |  | No | No | N/A | N/A | Complete
19INR0038 | High Lonesome W | Swift Current Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | 2019-11-01 | WIND | 500 |  | No | No | N/A | N/A | Incomplete
18INR0038 | Barrow Ranch | Engie | 1134 Littman 138kV | Andrews | 2019-12-01 | WIND | 200 | Project Name, SFS | Yes | Yes | N/A | N/A | Complete
18INR0023 | Darmstadt | RES Americas | 60708 Orsted 345kV - Big Hill | Schleicher | 2019-12-01 | WIND | 201 |  | No | No | N/A | N/A | Complete
18INR0022 | Winkler Solar | RES Americas | tap 138kV 1009 Yucca - 1146 Notrees | Winkler | 2019-12-01 | SOLAR | 150 |  | No | No | N/A | N/A | Complete
18INR0018 | Peyton Creek Wind | Eon | tap 345kV 5915 STP - 42500 Dow | Matagorda | 2019-12-01 | WIND | 150 |  | Yes | Yes | N/A | N/A | Complete
16INR0081 | Mesteno Wind | Duke Energy | 80355 Del Sol 345kV | Starr | 2019-12-01 | WIND | 202 |  | Yes | Yes | N/A | N/A | Complete
16INR0037c | Pumpkin Farm Wind | Apex Clean | 79505 White River 345kV | Floyd | 2019-12-01 | WIND | 281 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0090 | Pflugerville Solar | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | 2019-12-01 | SOLAR | 144 |  | No | No | N/A | N/A | Complete
14INR0044 | West of Pecos Solar | Eon | 1094 Mason 138kV | Reeves | 2019-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Complete
19INR0088 | Aragorn Solar | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | 2019-12-01 | SOLAR | 186 |  | No | No | N/A | N/A | Incomplete
19INR0074 | Karankawa 2 Wind | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | 2019-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
19INR0051 | Vera Wind | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | 2019-12-01 | WIND | 220 |  | No | No | N/A | N/A | Incomplete
18INR0014 | Karankawa Wind | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | 2019-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0027b | Coyote Wind | Lincoln Clean | 11305 Dermott 345kV | Scurry | 2019-12-01 | WIND | 242 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
17INR0020c | RE Maplewood 2c Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2019-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020b | RE Maplewood 2b Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2019-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020a | RE Maplewood 2a Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2019-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0114 | Upton Solar | SunPower | 132581 Upton 34.5kV | Upton | 2019-12-01 | SOLAR | 102 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0059 | Emerald Grove Solar | Cypress Creek Renewables | 6601 Rio Pecos 138kV | Pecos | 2019-12-01 | SOLAR | 108 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
13INR0005c | Grandview W 3 | Eon | 140653 Alibates 345kV | Carson | 2019-12-01 | WIND | 188 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Avangrid | 79501 Ogallala 345kV | Swisher | 2019-12-01 | WIND | 500 |  | No | No | N/A | N/A | Incomplete
16INR0006 | Pinecrest G | Coronado Ventures | 3117 Lufkin 345kV | Angelina | 2020-04-01 | GAS | 785 |  | No | No | Yes | Yes | Incomplete
16INR0044 | Halyard Wharton | Halyard Energy | tap 345kV 9073 Holman - 44200 Hillje | Wharton | 2020-06-01 | GAS | 398 |  | No | No | Yes | Yes | Incomplete
19INR0099b | Kontiki 2 Wind | TriGlobal | 59903 Bearkat 345kV | Glasscock | 2020-09-01 | WIND | 255 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0010 | FGE Texas 2 Gas | FGE Power | Tap 345kV 1030 Morgan – 1058 Longshore | Mitchell | 2020-09-01 | GAS | 743 |  | No | No | Yes | No | Incomplete
15INR0063 | Easter Wind | TriGlobal | 79502 Windmill 345kV | Castro | 2020-10-01 | WIND | 308 |  | No | No | N/A | N/A | Complete
17INR0035 | Las Majadas Wind | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | 2020-10-01 | WIND | 273 | MW For Grid | No | No | N/A | N/A | Incomplete
16INR0010 | FGE Texas 1 Gas | FGE Power | Tap 345kV 1030 Morgan - 1025 Falcon | Mitchell | 2020-10-01 | GAS | 743 |  | No | No | Yes | Yes | Incomplete
15INR0013 | Apex Bethel CAES | Apex CAES | tap 345kV 3380 Big Brown - 3133 Richland Chambers | Anderson | 11/1/2020/CE | GAS | 324 |  | No | No | Yes | Yes | Incomplete
17INR0020e | RE Maplewood 2e Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2020-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020d | RE Maplewood 2d Solar | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | 2020-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0005 | Brownsville G | Tenaska | Tap 345kV 5966 Palmito - 80137 Stewart | Cameron | 2020-12-01 | GAS | 871 |  | No | No | Yes | No | Incomplete
14INR0030c | Panhandle Wind 3 | Pattern Energy | 79005 Railhead 345kV | Carson | 2020-12-01 | WIND | 248 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0045 | Halyard Henderson | Halyard Energy | tap 345kV 3109 Stryker - 3123 Trinidad | Henderson | 2021-05-01 | GAS | 484 |  | No | No | Yes | Yes | Incomplete
15INR0023 | Indeck Wharton | Indeck | tap 345kV 44200 Hillje - 44000 WAP | Wharton | 2021-09-01 | GAS | 654 |  | No | No | Yes | Yes | Complete
* The capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative values.

## QSA Units
GIR under Quarterly Stability Assessment (Study Period: May 1 ~ July 31, 2018)
INR | Project Name
11INR0054 | Midway Wind
12INR0060 | Infinity Live Oak Wind
15INR0035 | Stella 1 Wind
16INR0019 | BlueBell Solar
16INR0023b | Lamesa Solar B (Phase II)
16INR0037c | Pumpkin Farm Wind
16INR0076 | Hudson (Ineos/Brazoria)
16INR0115 | Waymark Solar
17INR0045 | VictPort
18INR0068 | Loraine Windpark Phase III
18INR0072 | Blue Summit Repower
13INR0010a | Mariah Del Este
14INR0045 | Torrecillas Wind

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
15INR0082 | Flat Top Wind I | Comanche | PLANNED | 2018-08-01 | 2016-02-19 | WIND | WT | 200 | 2018 | TRUE
16INR0087 | RTS 1 Wind | McCulloch | PLANNED | 2018-08-01 | 2015-10-14 | WIND | WT | 160 | 2018 | TRUE
17INR0068 | Sweetwater 2 repower | Nolan | PLANNED | 2018-08-01 | 2017-11-17 | WIND | WT | 7 | 2018 | FALSE
16INR0086 | Cactus Flats Wind | Concho | PLANNED | 2018-08-15 | 2017-03-15 | WIND | WT | 148 | 2018 | TRUE
18INR0025 | Tahoka Wind | Lynn | PLANNED | 2018-10-31 | 2018-01-03 | WIND | WT | 300 | 2018 | TRUE
17INR0104 | Capricorn 4 repower | Coke | PLANNED | 2018-11-01 | 2018-05-01 | WIND | WT | 0 | 2018 | FALSE
12INR0060 | Wilson Ranch | Schleicher | PLANNED | 2018-12-05 | 2018-05-21 | WIND | WT | 200 | 2018 | TRUE
11INR0054 | Midway Wind | San Patricio | PLANNED | 2018-12-15 | 2017-11-05 | WIND | WT | 163 | 2018 | TRUE
18INR0068 | Loraine Windpark Phase III | Mitchell | PLANNED | 2018-12-21 | 2018-04-10 | WIND | WT | 100 | 2018 | TRUE
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 152 | 2018 | TRUE
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-12-31 | 2013-01-31 | WIND | WT | 218 | 2018 | TRUE
14INR0045 | Torrecillas Wind | Webb | PLANNED | 2018-12-31 | 2018-04-12 | WIND | WT | 300 | 2018 | TRUE
15INR0035 | Stella 1 Wind | Kenedy | PLANNED | 2018-12-31 | 2017-08-02 | WIND | WT | 201 | 2018 | TRUE
18INR0069 | Indian Mesa Repower | Pecos | PLANNED | 2019-01-01 | 2018-05-29 | WIND | WT | 0 | 2019 | FALSE
18INR0070 | Blue Summit II | Wilbarger | PLANNED | 2019-01-15 | 2018-04-28 | WIND | WT | 102 | 2019 | TRUE
11INR0062 | Patriot Wind | Nueces | PLANNED | 2019-04-01 | 2018-04-13 | WIND | WT | 226 | 2019 | TRUE
12INR0055 | S_Hills Wind | Baylor | PLANNED | 2019-04-01 | 2017-12-04 | WIND | WT | 30 | 2019 | TRUE
17INR0005 | Cabezon Wind | Starr | PLANNED | 2019-04-01 | 2017-08-03 | WIND | WT | 238 | 2019 | TRUE
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2019-05-01 | 2014-04-25 | WIND | WT | 600 | 2019 | FALSE
20INR0011 | Ranchero Wind | Crockett | PLANNED | 2019-06-04 | 2018-05-02 | WIND | WT | 300 | 2019 | TRUE
18INR0067 | Gopher Creek Wind | Scurry | PLANNED | 2019-06-26 | 2018-01-26 | WIND | WT | 158 | 2019 | TRUE
18INR0033 | Oveja Wind | Irion | PLANNED | 2019-06-30 | 2018-07-24 | WIND | WT | 300 | 2019 | TRUE
17INR0037 | Palmas Altas Wind | Cameron | PLANNED | 2019-08-01 | 2017-11-30 | WIND | WT | 145 | 2019 | FALSE
15INR0064b | Harald (BearKat Wind B) | Glasscock | PLANNED | 2019-08-02 | 2018-05-30 | WIND | WT | 162 | 2019 | TRUE
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2019-08-11 | 2018-03-07 | WIND | WT | 497 | 2019 | FALSE
18INR0043 | Edmondson Ranch Wind | Glasscock | PLANNED | 2019-09-01 | 2017-10-04 | WIND | WT | 292 | 2019 | TRUE
19INR0019 | Foard City Wind | Foard | PLANNED | 2019-09-01 | 2018-02-19 | WIND | WT | 350 | 2019 | TRUE
19INR0099a | Kontiki 1 Wind | Glasscock | PLANNED | 2019-09-01 | 2018-05-07 | WIND | WT | 255 | 2019 | TRUE
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2019-09-13 | 2016-05-20 | WIND | WT | 210 | 2019 | FALSE
13INR0025 | Northdraw Wind | Randall | PLANNED | 2019-09-30 | 2018-04-25 | WIND | WT | 150 | 2019 | FALSE
16INR0062b | Lockett Wind | Wilbarger | PLANNED | 2019-09-30 | 2015-03-31 | WIND | WT | 184 | 2019 | TRUE
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2019-10-01 | 2014-10-03 | WIND | WT | 203 | 2019 | FALSE
18INR0016 | RTS 2 Wind | McCulloch | PLANNED | 2019-10-01 | 2017-11-21 | WIND | WT | 150 | 2019 | TRUE
13INR0038 | Wildrose Wind | Swisher | PLANNED | 2019-10-30 | 2015-09-06 | WIND | WT | 212 | 2019 | TRUE
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2019-10-31 | 2016-06-22 | WIND | WT | 200 | 2019 | FALSE
14INR0009 | WKN Amadeus Wind | Kent | PLANNED | 2019-10-31 | 2018-03-15 | WIND | WT | 246 | 2019 | FALSE
19INR0163 | Sage Draw Wind | Lynn | PLANNED | 2019-10-31 | 2018-01-03 | WIND | WT | 300 | 2019 | FALSE
16INR0112 | Loma Pinta Wind | La Salle | PLANNED | 2019-11-30 | 2017-12-13 | WIND | WT | 200 | 2019 | FALSE
19INR0038 | High Lonesome W | Crockett | PLANNED | 2019-11-30 | 2018-04-17 | WIND | WT | 500 | 2019 | FALSE
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2019-12-01 | 2017-03-24 | WIND | WT | 281 | 2019 | TRUE
18INR0018 | Peyton Creek Wind | Matagorda | PLANNED | 2019-12-01 | 2018-03-19 | WIND | WT | 150 | 2019 | TRUE
18INR0038 | Barrow Ranch | Andrews | PLANNED | 2019-12-01 | 2018-06-26 | WIND | WT | 200 | 2019 | TRUE
19INR0051 | Vera Wind | Knox | PLANNED | 2019-12-01 | 2018-07-10 | WIND | WT | 220 | 2019 | FALSE
17INR0027b | Coyote Wind | Scurry | PLANNED | 2019-12-02 | 2016-08-09 | WIND | WT | 242 | 2019 | TRUE
13INR0005c | Grandview W 3 | Carson | PLANNED | 2019-12-15 | 2014-04-23 | WIND | WT | 188 | 2019 | TRUE
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2019-12-31 | 2013-07-24 | WIND | WT | 500 | 2019 | FALSE
16INR0081 | Mesteno Wind | Starr | PLANNED | 2019-12-31 | 2018-04-25 | WIND | WT | 202 | 2019 | TRUE
18INR0014 | Karankawa Wind | San Patricio | PLANNED | 2019-12-31 | 2017-11-30 | WIND | WT | 200 | 2019 | TRUE
18INR0023 | Darmstadt | Schleicher | PLANNED | 2019-12-31 | 2018-05-11 | WIND | WT | 201 | 2019 | FALSE
19INR0074 | Karankawa 2 Wind | San Patricio | PLANNED | 2019-12-31 | 2018-03-02 | WIND | WT | 200 | 2019 | TRUE
19INR0099b | Kontiki 2 Wind | Glasscock | PLANNED | 2020-09-01 | 2018-05-07 | WIND | WT | 255 | 2020 | TRUE
17INR0035 | Las Majadas Wind | Willacy | PLANNED | 2020-10-01 | 2018-04-13 | WIND | WT | 273 | 2020 | FALSE
15INR0063 | Easter Wind | Castro | PLANNED | 2020-10-31 | 2018-06-01 | WIND | WT | 308 | 2020 | FALSE
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2020-12-01 | 2014-08-25 | WIND | WT | 248 | 2020 | TRUE

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | PLANNED | 2018-08-06 | 2013-12-26 | SOLAR | PV | 7 | 2018 | TRUE
16INR0019 | BlueBell Solar | Coke | PLANNED | 2018-12-01 | 2015-08-19 | SOLAR | PV | 30 | 2018 | TRUE
16INR0115 | Waymark Solar | Pecos | PLANNED | 2018-12-15 | 2016-09-23 | SOLAR | PV | 182 | 2018 | TRUE
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2018-12-31 | 2016-07-28 | SOLAR | PV | 50 | 2018 | TRUE
19INR0092 | Prospero Solar | Andrews | PLANNED | 2019-05-01 | 2018-04-20 | SOLAR | PV | 300 | 2019 | FALSE
16INR0049 | Nazareth Solar | Castro | PLANNED | 2019-06-01 | 2018-05-10 | SOLAR | PV | 201 | 2019 | FALSE
19INR0029 | Phoebe Solar | Winkler | PLANNED | 2019-10-01 | 2018-03-05 | SOLAR | PV | 250 | 2019 | TRUE
18INR0045 | Misae Solar | Childress | PLANNED | 2019-10-20 | 2018-07-18 | SOLAR | PV | 241 | 2019 | FALSE
15INR0059 | Emerald Grove Solar | Pecos | PLANNED | 2019-12-01 | 2018-06-27 | SOLAR | PV | 108 | 2019 | TRUE
15INR0090 | Pflugerville Solar | Travis | PLANNED | 2019-12-01 | 2017-06-13 | SOLAR | PV | 144 | 2019 | FALSE
16INR0114 | Upton Solar | Upton | PLANNED | 2019-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2019 | TRUE
14INR0044 | West of Pecos Solar | Reeves | PLANNED | 2019-12-15 | 2017-02-27 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
18INR0022 | Winkler Solar | Winkler | PLANNED | 2019-12-31 | 2018-01-23 | SOLAR | PV | 150 | 2019 | FALSE
19INR0088 | Aragorn Solar | Culberson | PLANNED | 2019-12-31 | 2018-05-31 | SOLAR | PV | 186 | 2019 | FALSE
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE
17INR0020e | RE Maplewood 2e Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE