## List
Area | # | Name | Model Status Summary | RESOURCE SITE CODE | COMMENTS
Panhandle | 14INR0030b | Panhandle Wind 2 | New Model Submitted (no user experience to report) - based on submitted checklist, fully satisfies Model Guidelines | PH2_UNIT1 & PH2_UNIT2
Panhandle | 14INR0030c | Panhandle Wind 3 (Planned) | New Model Submitted (no user experience to report) - based on submitted checklist, fully satisfies Model Guidelines | PH3_UNIT1 & PH3_UNIT2
Panhandle | 14INR0047 | Wake Wind | New Model Submitted (no user experience to report) - based on submitted checklist, fully satisfies Model Guidelines | WAKEWE_G1 & WAKEWE_G2
Panhandle | 14INR0062 | Salt Fork Wind (DVAR) | New Model Submitted (no user experience to report) - based on submitted checklist, fully satisfies Model Guidelines | SALTFORK_UNIT1 & SALTFORK_UNIT2
Panhandle | 12INR0075 | Blue Summit Wind farm | Lacks Minor Usability Features | BLSUMMIT_BLSMT1_5 & BLSUMMIT_BLSMT1_6 | Requested extension to supply model by August 31
Panhandle | 13INR0005a | Grandview Phase I | Lacks Minor Usability Features | GRANDVW1_GV1A & GRANDVW1_GV1B
Panhandle | 13INR0005b | Colbeck's Corner W | Lacks Minor Usability Features | GRANDVW1_COLA & GRANDVW1_COLB
Panhandle | 13INR0010b | Mariah Del Norte | Lacks Minor Usability Features | MARIAH_NORTE1 & MARIAH_NORTE2
Panhandle | 13INR0048 | Spinning Spur Wind Two | Lacks Minor Usability Features | SSPURTWO_WIND_1
Panhandle | 13INR0059a | Hereford Wind | Lacks Minor Usability Features | HRFDWIND_WIND_G
Panhandle | 13INR0059b | Jumbo Road Wind | Lacks Minor Usability Features | HRFDWIND_JRDWIND1 & HRFDWIND_JRDWIND2
Panhandle | 14INR0012a | Miami Wind 1 Project | Lacks Minor Usability Features | MIAM1_G1 & MIAM1_G2
Panhandle | 14INR0030a | Panhandle Wind 1 | Lacks Minor Usability Features | PH1_UNIT1 & PH1_UNIT2
Panhandle | 14INR0072 | Briscoe Wind Farm | Lacks Minor Usability Features | BRISCOE_WIND
Panhandle | 15INR0074 | Happy Whiteface Wind | Lacks Minor Usability Features | ASTRA_UNIT1
Panhandle | 16INR0037a | Cotton Plains Wind | Lacks Minor Usability Features | COTPLNS_COTTONPL
Panhandle | 16INR0037b | Old Settler Wind | Lacks Minor Usability Features | COTPLNS_OLDSETLR
Panhandle | 14INR0060 | Horse Creek Wind | New Model Submitted (no user experience to report) - based on submitted checklist, Lacks Minor Usability Features | HORSECRK_UNIT1 & HORSECRK_UNIT2
Panhandle | 16INR0062a | Electra Wind | New Model Submitted (no user experience to report) - based on submitted checklist, Lacks Minor Usability Features | DIGBY_UNIT1 & DIGBY_UNIT2
Panhandle | 13INR0059a | Hereford Wind | Lacks Significant Efficiency Features | HRFDWIND_WIND_V
Panhandle | 14INR0023a | Longhorn Energy Center North (DVAR) | Lacks Significant Efficiency Features | LHORN_N_UNIT1 & LHORN_N_UNIT2
Panhandle | 14INR0053 | Spinning Spur Wind Three | Lacks Significant Efficiency Features | SSPURTWO_SS3WIND1 & SSPURTWO_SS3WIND2
Panhandle | 14INR0025a | South Plains I (DVAR) | Lacks PPC Representation & Significant Efficiency Features | SPLAIN1_WIND1 & SPLAIN1_WIND2
Panhandle | 14INR0025b | South Plains 2a | Lacks PPC Representation & Significant Efficiency Features | SPLAIN2_WIND21
Panhandle | 14INR0025c | South Plains 2b | Lacks PPC Representation & Significant Efficiency Features | SPLAIN2_WIND22
Panhandle | 14INR0032a | Route66 Wind (DVAR) | Lacks PPC Representation & Significant Efficiency Features | ROUTE_66_WIND1 | Requested extension to supply model by October 31
Panhandle | 16INR0037c | Pumpkin Farm Wind (Planned) | Lacks PPC Representation & Significant Efficiency Features | PUMWIND_UNIT3 & PUMWIND_UNIT4
Panhandle | 09INR0051 | Mesquite Creek | No Model Submitted | MESQCRK_WND1 & MESQCRK_WND2 | Requested extension to supply model by September 30
Panhandle | 13INR0005c | Grandview W 3 (Planned) | No Model Submitted | GRANDVW3_GV3A & GRANDVW3_GV3B
Panhandle | 13INR0010c | Mariah Del Sur (Planned) | No Model Submitted | MARIAHS_UNIT1 & MARIAHS_UNIT2
Panhandle | 13INR0038 | Wildrose (Swisher) (Planned) | No Model Submitted | WILDROSE_WIND_1
Panhandle | 16INR0062b | Lockett Wind Farm (Planned) | No Model Submitted | LOCKETT_UNIT1 & LOCKETT_UNIT2
Panhandle | 17INR0027b | Coyote Wind (Planned) | No Model Submitted | COYOTEWI_UNIT1 & COYOTEWI_UNIT2
Panhandle | 20INR0058 | Longhorn Energy Center South (Planned) | No Model Submitted | LHSOUTH_UNIT1
Panhandle | 12INR0034a | Stephens Ranch Wind | New Model Submitted without Checklist (no user experience to report) | SRWE1_UNIT1
Panhandle | 12INR0034b | Stephens Ranch Wind B | New Model Submitted without Checklist (no user experience to report) | SRWE1_SRWE2
Panhandle | 13INR0010a | Mariah Del Este (Planned) | New Model Submitted without Checklist (no user experience to report) | MARIAEST_UNIT_1
Panhandle | 13INR0056 | Fluvanna Wind | New Model Submitted without Checklist (no user experience to report) | FLUVANNA_UNIT1 & FLUVANNA_UNIT2
Panhandle | 14INR0060b | Salvation (Willow Springs) | New Model Submitted without Checklist (no user experience to report) | SALVTION_UNIT1 & SALVTION_UNIT2
Panhandle | 17INR0027a | Dermott Wind | New Model Submitted without Checklist (no user experience to report) | DERMOTT_UNIT1 & DERMOTT_UNIT2
Panhandle | 18INR0025 | Tahoka Wind (Planned) | New Model Submitted without Checklist (no user experience to report) | TAHOKA_UNIT_1 & TAHOKA_UNIT_2
Panhandle | 18INR0067 | Gopher Creek Wind (Planned) | New Model Submitted without Checklist (no user experience to report) | GOPHER_UNIT_1 & GOPHER_UNIT_2 | Requested extension to supply model by October 31
Panhandle | 18INR0070 | Blue Summit II (Planned) | New Model Submitted without Checklist (no user experience to report) | BLSUMMIT_BLSMT2_2_5 & BLSUMMIT_BLSMT2_1_715 | Requested extension to supply model by August 31
South Texas | 09INR0082 | Cedro Hill Wind | Lacks Minor Usability Features | CEDROHIL_CHW1 & CEDROHIL_CHW2
South Texas | 11INR0091 | Whitetail Wind Energy Project | Lacks Minor Usability Features | EXGNWTL_WIND_1
South Texas | 12INR0068 | Sendero Wind | Lacks Minor Usability Features | EXGNSND_WIND_1
South Texas | 13INR0055 | Javelina Wind | Lacks Minor Usability Features | BORDAS_JAVEL18 & BORDAS_JAVEL20
South Texas | 15INR0049 | Albercas Wind (Javelina 2) | Lacks Minor Usability Features | BORDAS2_JAVEL2_A, BORDAS2_JAVEL2_B & BORDAS2_JAVEL2_C
South Texas | 13INR0052 | Los Vientos III (DVAR) | Lacks Significant Efficiency Features | LV3_UNIT_1
South Texas | 11INR0062 | Patriot Wind (Planned) | New Model Submitted (no user experience to report) - based on submitted checklist, Lacks Significant Efficiency Features | PATWIND_UNIT1
South Texas | 17INR0005 | Cabezon Wind (Planned) | New Model Submitted (no user experience to report) - based on submitted checklist, Lacks Significant Efficiency Features | CABEZON_WIND1 & CABEZON_WIND2
South Texas | 14INR0013 | San Roman Wind 1 | New Model Submitted without Checklist (no user experience to report) - based on preliminary review, Lacks Significant Efficiency Features | SANROMAN_WIND_1
South Texas | 06INR0022c | Baffin Wind | Lacks PPC Representation & Significant Efficiency Features | BAFFIN_UNIT1 & BAFFIN_UNIT2
South Texas | 10INR0060 | Redfish Wind (Magic Valley)(DVAR) | Lacks PPC Representation & Significant Efficiency Features | REDFISH_MV1A & REDFISH_MV1B
South Texas | 11INR0033 | Los Vientos 1A | Lacks PPC Representation & Significant Efficiency Features | LV1_LV1A
South Texas | 11INR0057 | Cameron County Wind | Lacks PPC Representation & Significant Efficiency Features | CAMWIND_UNIT1
South Texas | 14INR0041a | Bruennings Breeze | Lacks PPC Representation & Significant Efficiency Features | BBREEZE_UNIT1 & BBREEZE_UNIT2
South Texas | 15INR0021 | Los Vientos V | Lacks PPC Representation & Significant Efficiency Features | LV5_UNIT_1
South Texas | 15INR0037 | Los Vientos IV | Lacks PPC Representation & Significant Efficiency Features | LV4_UNIT_1
South Texas | 16INR0024 | Hidalgo & Starr Wind (DVAR) | Lacks PPC Representation & Significant Efficiency Features | MIRASOLE_MIR11, MIRASOLE_MIR12 & MIRASOLE_MIR21 | Requested extension to supply model by December 31, 2019
South Texas | 16INR0055 | Chapman Ranch Wind I | Lacks PPC Representation & Significant Efficiency Features | SANTACRU_UNIT1 & SANTACRU_UNIT2
South Texas | 05INR0015a | Gulf Wind | Lacks PPC Representation & Significant Accuracy and Efficiency Features | TGW_T1 & TGW_T2
South Texas | 06INR0022ab | Penascal Wind Farm | Lacks PPC Representation & Significant Accuracy and Efficiency Features | PENA_UNIT1, PENA_UNIT2 & PENA3_UNIT3
South Texas | 11INR0033 | Los Vientos 1B | Lacks PPC Representation & Significant Accuracy and Efficiency Features | LV1_LV1B
South Texas | 15INR0035 | Stella 1 Wind (Planned) | New Model Submitted (no user experience to report) - based on submitted checklist, Lacks PPC Representation & Significant Efficiency Features | STELLA_UNIT1
South Texas | 14INR0045 | Torrecillas Wind (Planned) | New Model Submitted without Checklist (no user experience to report) | TORCILAS_TORCILAS_2_5 & TORCILAS_TORCILAS_2_3

## Summary
| Panhandle | South Texas
# of Wind Generation Resources | 43 | 23
No Deficiencies in Model | 4 | 0
Model Okay But Lacks Certain Usability/Efficiency Features | 18 | 9
Model Significantly Deficient or No Model Submitted | 12 | 13
New Model Submitted without Checklist | 9 | 1