## Slide 1
ERCOT – Southern Cross Transmission
ROS/WMS Working Group Assignments
Matt Mereness
ERCOT
August 2018

## Slide 2: ERCOT – Southern Cross Transmission Working Group Assignments Status Dashboard
Directive | Status | Target Dates
Directive #1 – Registration and market segment | TAC NPRR857 for registration. Endorsed at WMS, ROS, PRS. Currently at TAC for approval. NOGRR177 language endorsed at ROS. Currently at TAC for approval. Proposed bylaw segment definition amendment withdrawn at this time. Expected to reinitiate at a later date. | TAC 8/30/18 TAC 8/30/18 No planned activity
Directive #5 - Planning model considerations | PLWG (ROS) Whitepaper outlining Planning model assumptions and documenting that ERCOT proposes no changes to criteria for transmission system improvements endorsed by ROS. Update provided to TAC 7/26/18. Currently at Board for information only. PGRR068, Addition of a Proposed DC Tie to the Planning Models will be discussed at ROS. | Board 8/7/18 ROS 8/9/18
Directive #6 - Planning studies for transmission upgrades | RPG (Other) Studies underway. | Results by 12/31/18
Directive #7 – Congestion management | Joint QMWG/CMWG (WMS) Discussions starting Q2-18 postponed pending results of Directive #6 planning studies for transmission upgrades | QMWG/CMWG pending

## Slide 3: ERCOT – Southern Cross Transmission Working Group Assignments Status Dashboard
Directive | Status | Target Dates
Directive #8 - Frequency response and voltage support | PDCWG (ROS) Primary frequency response whitepaper endorsed by ROS and TAC. Currently at Board for approval. RPG (Other) Studies underway to consider whether voltage support is needed. | Board 8/7/18 Results by 12/31/18
Directive #9 - Ancillary services | OWG & PDCWG (ROS) MSSC whitepaper endorsed by OWG (7/18/18). Currently at ROS for possible vote to approve. PDCWG (ROS) Address issues related to NSRS and Regulation Service will follow the MSSC determination. DWG (ROS) Address issues related to study frequency overshoot and LRs UFR setting will follow the MSSC determination. | ROS 8/9/18 PDCWG 8/23/18 DWG pending
Directive #10 – Price formation in emergency conditions | QMWG (WMS) Price formation in emergency conditions whitepaper endorsed by QMWG (7/9/18). Currently at WMS. Following WMS endorsement, ERCOT will seek endorsement at TAC. | WMS 8/8/18 TAC 8/30/18

## Slide 4: Appendix

## Slide 5: PUC Order 46304 Directives
 |  | Anticipated Start
Directive #1 – Registration and market segment | ERCOT shall (a) determine the appropriate market participation category for Southern Cross Transmission LLC and for any other entity associated with the Southern Cross DC tie for which a new market participant category may be appropriate (creating new ones if necessary), (b) implement the modifications to the standard-form market-participant agreement and its protocols, bylaws, operating guides, and systems required for Southern Cross Transmission's participation and any other entity’s participation, and (c) determine the appropriate market segment for Southern Cross Transmission and any other entity. | 
Directive # 2 – Coordination agreement | ERCOT shall execute a coordination agreement or agreements with any necessary independent system operator, regional transmission organization, or reliability coordinator on the eastern end of the Southern Cross line. ERCOT shall consult Southern Cross Transmission as needed during negotiations of such agreement(s) for technical input and guidance. | 
Directive #3 -- Ramp rate restrictions | ERCOT shall determine what ramp rate restrictions, if any, will be necessary to accommodate the interconnection of the Southern Cross DC tie and shall implement those restrictions and shall certify to the Commission when it has completed these actions | 
Directive #4 -- Outage coordination | ERCOT shall develop and implement a methodology to reliably and cost-effectively coordinate outages following the interconnection of the Southern Cross DC tie and shall certify to the Commission when it has completed these actions. | 
Directive #5 - Planning model considerations | ERCOT shall study and determine how best to model the Southern Cross DC tie in its transmission planning cases, make any necessary revisions to its standards, guides, systems, and protocols as appropriate, and certify to the Commission when it has completed these actions. | 
Directive #6 - Planning studies for transmission upgrades | ERCOT shall study and determine what transmission upgrades, if any, are necessary to manage congestion resulting from power flows over the Southern Cross DC tie, make any necessary revisions to its standards, guides, systems, and protocols as appropriate, and certify to the Commission when it has completed these actions. | 
Directive #7 – Congestion management | ERCOT shall (a) study and determine whether some or all DC ties should be economically dispatched or whether implementing a congestion-management plan or special protection scheme would more reliably and cost-effectively manage congestion caused by DC tie flows, (b) implement any necessary revisions to its protocols, guides, standards, and systems as appropriate, and (c) certify to the Commission when it has completed these actions. | 
Started
Q2-2020
Q1-2019
Q1-2019
Started
Q1-2019
Started

## Slide 6: PUC Order 46304 Directives
 |  | Anticipated Start
Directive #8 - Frequency response and voltage support | ERCOT shall (a) study and determine whether Southern Cross Transmission or any other entity scheduling flows across the Southern Cross DC tie should be required to provide or procure voltage support service or primary frequency response, or their technical equivalents, (b) implement any necessary revisions to its standards, guides, systems, and protocols, as appropriate, and (c) certify to the Commission when it has completed these actions. | 
Directive #9 - Ancillary services | ERCOT shall (a) evaluate what modifications to existing and additional ancillary services, if any, are necessary for the reliable interconnection of the Southern Cross DC tie, (b) implement any needed modifications to ancillary-services procurement, (c) recommend how the costs of such required ancillary services are to be allocated, and (d) certify to the Commission when it has completed these actions. | 
Directive #10 – Price formation under emergency conditions | ERCOT shall study price formation issues to determine whether, to avoid the flows over the DC ties adversely affecting price formation in the ERCOT wholesale market or otherwise causing outcomes inconsistent with a properly functioning energy market, any changes to pricing within the ERCOT market during emergencies are necessary. ERCOT shall certify to the Commission when it has completed these actions. | 
Directive #11 | ERCOT shall study and recommend appropriate responsibility for, and allocation of, the costs identified in the Commission's final order in Docket No. 45624, including costs common to the ERCOT system and special costs that are specific to the Garland line and Southern Cross DC tie, and shall identify any existing protocols that need to be modified or new protocols that need to be created, or (if appropriate) any existing Commission rules that need to be modified or new rules that need to be enacted, to appropriately address those costs. | 
Directive #12 | ERCOT shall study and determine for export-related costs whether the qualified scheduling entity should be assigned costs that ordinarily would ultimately be paid by the end-use customer. | 
Directive #13 – Status Reporting | ERCOT shall periodically update the Commission regarding its progress in completing the above tasks. | 
Directive #14 – Status Reporting | ERCOT shall, as soon as practicable, notify the Commission of reasonable completion dates for the above tasks and shall report any changes to those completion dates as changes become known. | 
Started
TBD
Ongoing
Started
Started
TBD
Ongoing