## Projects
Generator Interconnection Status Report | March 2017
Date: 4/3/2017 2:37:02 PM

## New Units
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
15INR0074 | Falvez Astra W | 163.2 | Deaf Smith | 2017-03-01
14INR0038 | PHR Peakers (BAC) | 390 | Galveston | 2018-03-22
15INR0061 | SolaireHolman1 | 50 | Brewster | 2017-03-30
New Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
13INR0010b | Mariah Del Norte | 230.4 | Parmer | 2017-03-08
15INR0070_1 | West Texas Solar | 110 | Pecos | 2017-03-16
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | FIS Pending or Completed (MW) | IA Executed, FIS Pending or Approved (MW) | IA Executed, FIS Pending (MW) | Grand Total (MW)**
Currently tracking 266 generation interconnection or change requests |  | Gas-AllOther | 0 | 2636 | 5572 |  | 8208
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY * |  | Gas-CombinedCycle | 0 | 2177 | 7796 |  | 9973
March 2017 | Number of Projects | Gas-Compressed Air | 0 | 270 | 324 |  | 594
Security Screening Studies (SSS) Underway | 10 | Total Gas | 0 | 5083 | 13692 |  | 18775
SSS Completed | 27 | Nuclear | 0 |  | 0 |  | 0
Full Interconnect Study (FIS) Underway | 132 | Coal | 0 | 0 | 240 |  | 240
FIS Completed | 3 | Wind | 1700 | 14797 | 10068 |  | 26565
Interconnection Agreement Executed, FIS Pending or Completed | 41 | Battery | 0 | 0 | 30 |  | 30
Interconnection Agreement Executed | 53 | Solar | 5126 | 8203 | 2009 |  | 15338
Total Interconnection Requests | 266 | Biomass | 0 | 0 | 0 |  | 0
Cancelled Studies (since last month) | 3 | Petroleum Coke | 0 | 0 | 0 |  | 0
| Capacity, MW | Total | 6826 | 28083 | 26039 |  | 60948
Total Capacity Under Study | 60948 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l). If the capacity for a single project is reported in the column, the value is redacted.
Interconnection Agreements Executed | 26040
Cancelled (since last month) | 650 | ** Redacted project capacity from column E is excluded from the Grand Totals.
* Excludes new projects for which interconnection applications have not been approved and Security Screen Studies have not yet commenced. Redacted project capacity is excluded as well. |  | Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
FIS Pending or Completed column: Total MW capacity for which an FIS is either pending or completed and reviewed by ERCOT. The column total matches the sum of capacity values reported in the Full Study tab.
IA Executed, FIS Pending or Approved column: Total MW capacity for which a FIS has been requested and approved, and an IA has been executed. The column total matches the sum of capacity values reported in the IA Table tab

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement
GINR Reference Number | County | Fuel | Capacity to Grid (MW) | Projected Date (as specified by the resource developer) | Status
18INR0048 | Anderson | Gas | 100 | 2018-01-01 | Incomplete
16INR0102 | Pecos | Solar | 130 | 2018-01-01 | Incomplete
16INR0101 | Pecos | Solar | 57 | 2018-01-01 | Incomplete
17INR0046b | Upton | Solar | 50 | 2018-03-15 | Incomplete
17INR0045 | Victoria | Gas | 100 | 2018-04-01 | Incomplete
17INR0053 | Taylor | Wind | 44 | 2018-04-05 | Incomplete
17INR0052 | Taylor | Wind | 44 | 2018-04-05 | Incomplete
15INR0057 | Wharton | Gas | 142 | 2018-05-01 | Incomplete
15INR0055 | Austin | Gas | 142 | 2018-05-01 | Incomplete
18INR0025 | Lynn | Wind | 506 | 2018-05-01 | Complete
18INR0043 | Glasscock | Wind | 292 | 2018-05-07 | Incomplete
15INR0062b | Hale | Wind | 122 | 2018-05-15 | Incomplete
17INR0054 | Sterling | Wind | 32 | 2018-05-31 | Incomplete
18INR0054 | Glasscock | Wind | 138 | 2018-06-01 | Incomplete
18INR0033 | Irion | Wind | 301 | 2018-06-01 | Incomplete
17INR0048 | Harris | Gas | 149 | 2018-06-01 | Incomplete
12INR0055 | Baylor | Wind | 80 | 2018-06-01 | Incomplete
17INR0046c | Upton | Solar | 50 | 2018-06-15 | Incomplete
18INR0060 | Bee | Solar | 50 | 2018-06-30 | Incomplete
18INR0056 | Hunt | Solar | 50 | 2018-06-30 | Incomplete
17INR0024 | Nolan | Gas | 350 | 2018-06-30 | Incomplete
16INR0036 | Nolan | Gas | 280 | 2018-06-30 | Incomplete
18INR0059 | Willacy | Wind | 201 | 2018-07-01 | Incomplete
16INR0014 | Castro | Wind | 200 | 2018-07-01 | Incomplete
14INR0074 | Williamson | Gas | 92 | 2018-07-01 | Incomplete
14INR0011 | Swisher | Gas | 270 | 2018-07-01 | Incomplete
18INR0037 | Wichita | Solar | 75 | 2018-08-01 | Incomplete
18INR0036 | Wichita | Solar | 150 | 2018-08-25 | Incomplete
18INR0045 | Childress | Solar | 241 | 2018-09-01 | Incomplete
18INR0029 | Armstrong | Wind | 278 | 2018-09-01 | Incomplete
18INR0042 | Callahan | Wind | 100 | 2018-10-01 | Incomplete
18INR0040 | Crane | Solar | 400 | 2018-10-01 | Incomplete
18INR0027 | Upton | Solar | 150 | 2018-10-01 | Incomplete
16INR0093 | Reeves | Solar | 48 | 2018-10-01 | Incomplete
16INR0089 | Andrews | Solar | 60 | 2018-10-01 | Incomplete
13INR0056b | Scurry | Wind | 152 | 2018-10-01 | Incomplete
18INR0022 | Winkler | Solar | 150 | 2018-10-31 | Incomplete
17INR0025 | Zapata | Wind | 202 | 2018-10-31 | Incomplete
12INR0002b | Briscoe | Wind | 200 | 2018-10-31 | Incomplete
18INR0035 | Victoria | Gas | 100 | 2018-11-01 | Incomplete
18INR0050 | Jackson | Solar | 120 | 2018-11-30 | Incomplete
17INR0035 | Willacy | Wind | 227 | 2018-11-30 | Incomplete
14INR0048_1 | Wilbarger | Wind | 114 | 2018-11-30 | Incomplete
18INR0039 | Crane | Solar | 300 | 2018-12-01 | Incomplete
18INR0031 | Nolan | Wind | 150 | 2018-12-01 | Incomplete
17INR0033 | Briscoe | Wind | 200 | 2018-12-01 | Incomplete
16INR0117 | Briscoe | Wind | 200 | 2018-12-01 | Incomplete
16INR0076 | Brazoria | Gas | 135 | 2018-12-01 | Incomplete
16INR0061 | Hardeman | Wind | 200 | 2018-12-01 | Incomplete
16INR0033 | Castro | Wind | 150 | 2018-12-01 | Incomplete
16INR0014b | Castro | Wind | 200 | 2018-12-01 | Incomplete
16INR0012 | Kenedy | Wind | 200 | 2018-12-01 | Incomplete
15INR0072 | Pecos | Solar | 140 | 2018-12-01 | Incomplete
15INR0051 | Castro | Wind | 200 | 2018-12-01 | Incomplete
15INR0034 | San Patricio | Wind | 201 | 2018-12-01 | Incomplete
13INR0006 | Gray | Wind | 750 | 2018-12-01 | Incomplete
08INR0019c | Gray | Wind | 250 | 2018-12-01 | Incomplete
08INR0019b | Gray | Wind | 250 | 2018-12-01 | Incomplete
08INR0019a | Gray | Wind | 250 | 2018-12-01 | Incomplete
18INR0057 | Val Verde | Wind | 500 | 2018-12-15 | Incomplete
17INR0046a | Upton | Solar | 50 | 2018-12-15 | Incomplete
16INR0115 | Pecos | Solar | 182 | 2018-12-15 | Incomplete
15INR0062 | Hale | Wind | 200 | 2018-12-15 | Incomplete
15INR0054 | Reeves | Gas | 123 | 2018-12-29 | Incomplete
15INR0053 | Winkler | Gas | 123 | 2018-12-29 | Incomplete
18INR0061 | Zavala | Solar | 75 | 2018-12-30 | Incomplete
18INR0058 | Wharton | Solar | 150 | 2018-12-30 | Incomplete
14INR0014 | Val Verde | Solar | 100 | 2018-12-30 | Incomplete
18INR0062 | Brazoria | Solar | 100 | 2018-12-31 | Incomplete
18INR0055 | Borden | Solar | 225 | 2018-12-31 | Incomplete
18INR0051 | Clay | Wind | 200 | 2018-12-31 | Incomplete
18INR0044 | Clay | Wind | 100 | 2018-12-31 | Incomplete
18INR0034 | Crosby | Wind | 251 | 2018-12-31 | Incomplete
18INR0030 | Scurry | Wind | 301 | 2018-12-31 | Incomplete
18INR0023 | Menard | Wind | 250 | 2018-12-31 | Incomplete
18INR0014 | San Patricio | Wind | 200 | 2018-12-31 | Incomplete
17INR0043 | Brooks | Wind | 400 | 2018-12-31 | Incomplete
17INR0038 | Zapata | Wind | 400 | 2018-12-31 | Incomplete
17INR0037 | Cameron | Wind | 145 | 2018-12-31 | Incomplete
17INR0032 | Duval | Wind | 53 | 2018-12-31 | Incomplete
17INR0031 | Cameron | Wind | 150 | 2018-12-31 | Incomplete
17INR0030 | Deaf Smith | Solar | 100 | 2018-12-31 | Incomplete
17INR0005 | Starr | Wind | 200 | 2018-12-31 | Incomplete
16INR0119 | Crosby | Solar | 150 | 2018-12-31 | Incomplete
16INR0112 | La Salle | Wind | 200 | 2018-12-31 | Incomplete
16INR0111 | Starr | Wind | 200 | 2018-12-31 | Incomplete
16INR0106 | Andrews | Solar | 150 | 2018-12-31 | Incomplete
16INR0105 | Jim Hogg | Wind | 300 | 2018-12-31 | Incomplete
16INR0104 | Crockett | Wind | 400 | 2018-12-31 | Incomplete
16INR0100 | Brewster | Solar | 150 | 2018-12-31 | Incomplete
16INR0099 | Brewster | Solar | 50 | 2018-12-31 | Incomplete
16INR0098 | Brewster | Solar | 50 | 2018-12-31 | Incomplete
16INR0097 | Upton | Solar | 200 | 2018-12-31 | Incomplete
16INR0092 | Brewster | Solar | 50 | 2018-12-31 | Incomplete
16INR0085 | Mills | Wind | 300 | 2018-12-31 | Incomplete
16INR0081 | Starr | Wind | 200 | 2018-12-31 | Incomplete
16INR0029 | Hill | Wind | 200 | 2018-12-31 | Incomplete
16INR0027 | Grayson | Wind | 100 | 2018-12-31 | Incomplete
15INR0081 | Mason | Wind | 62 | 2018-12-31 | Incomplete
15INR0063b | Castro | Wind | 101 | 2018-12-31 | Incomplete
15INR0063 | Castro | Wind | 200 | 2018-12-31 | Incomplete
15INR0044 | Webb | Solar | 200 | 2018-12-31 | Incomplete
15INR0035 | Kenedy | Wind | 200 | 2018-12-31 | Incomplete
14INR0056 | Mills | Wind | 101 | 2018-12-31 | Incomplete
13INR0025 | Randall | Wind | 150 | 2018-12-31 | Incomplete
18INR0016 | McCulloch | Wind | 150 | 2018-12-31 | Complete
15INR0090 | Travis | Solar | 120 | 2018-12-31 | Complete
19INR0031 | Winkler | Solar | 150 | 2019-01-25 | Incomplete
19INR0029 | Winkler | Solar | 300 | 2019-01-25 | Incomplete
19INR0030 | Wharton | Solar | 180 | 2019-01-30 | Incomplete
19INR0020c | Pecos | Solar | 180 | 2019-03-01 | Incomplete
19INR0020b | Pecos | Solar | 180 | 2019-03-01 | Incomplete
19INR0020 | Pecos | Solar | 180 | 2019-03-01 | Incomplete
14INR0009 | Kent | Wind | 248 | 2019-03-29 | Incomplete
17INR0013 | Hill | Gas | 800 | 2019-04-01 | Incomplete
19INR0009 | Nolan | Solar | 200 | 2019-06-01 | Incomplete
19INR0001 | Kent | Solar | 750 | 2019-06-01 | Incomplete
17INR0002 | Henderson | Gas | 478 | 2019-06-01 | Incomplete
19INR0019 | Foard | Wind | 350 | 2019-06-30 | Incomplete
18INR0009 | Cherokee | Gas | 1156 | 2019-08-01 | Incomplete
19INR0004 | Deaf Smith | Solar | 400 | 2019-10-01 | Incomplete
19INR0045 | Cameron | Solar | 150 | 2019-10-31 | Incomplete
19INR0039 | McLennan | Wind | 201 | 2019-12-01 | Incomplete
19INR0026 | Nolan | Solar | 100 | 2019-12-01 | Incomplete
19INR0002 | Upton | Solar | 350 | 2019-12-01 | Incomplete
18INR0018 | Matagorda | Wind | 150 | 2019-12-01 | Incomplete
17INR0036 | Gray | Wind | 200 | 2019-12-01 | Incomplete
19INR0024 | Glasscock | Wind | 400 | 2019-12-31 | Incomplete
19INR0023 | Willacy | Wind | 200 | 2019-12-31 | Incomplete
19INR0022 | Willacy | Wind | 200 | 2019-12-31 | Incomplete
20INR0003 | Childress | Solar | 200 | 2020-03-01 | Incomplete
20INR0002 | Castro | Solar | 360 | 2020-06-01 | Incomplete
20INR0005 | Childress | Solar | 200 | 2020-10-01 | Incomplete
18INR0005 | Grayson | Gas | 543 | 2020-12-01 | Incomplete
20INR0008 | Menard | Wind | 200 | 2020-12-31 | Incomplete

## IA Table
Generation Interconnection Agreements as of March 2017
Planning Guide Section 6.9 Requirements
(Other than model date submission)
GINR Reference Number | Project Name | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
16INR0037b | Old Settler Wind | Floyd | 2017-02-01 | Wind | 150 |  | Yes | Yes | N/A | N/A | Complete
14INR0038 | PHR Peakers | Galveston | 2017-03-01 | Gas | 390 |  | Yes | Yes | Yes | N/A | Complete
16INR0073 | East Pecos Solar | Pecos | 2017-03-01 | Solar | 120 |  | Yes | Yes | N/A | N/A | Complete
12INR0059b | Barilla Solar 1B | Pecos | 2017-04-01 | Solar | 7 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0062 | Salt Fork 1 Wind | Gray | 2017-04-01 | Wind | 174 |  | Yes | Yes | N/A | N/A | Complete
15INR0081 | SolaireHolman 1 | Brewster | 2017-04-01 | Solar | 50 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0070_1b | Pearl Solar | Pecos | 2017-04-01 | Solar | 50 |  | Yes | Yes | N/A | N/A | Complete
15INR0085 | Tyler Bluff Wind | Cooke | 2017-04-01 | Wind | 126 |  | Yes | Yes | N/A | N/A | Complete
16INR0023 | BNB Lamesa Solar (Phase I) | Dawson | 2017-04-01 | Solar | 102 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0037 | Cotton Plains Wind | Floyd | 2017-04-01 | Wind | 50 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0054 | NASA-JSC CHP | Harris | 2017-04-01 | Gas | 12 |  | Yes | Yes | N/A | N/A | Complete
16INR0122 | Blue Summit Battery | Wilbarger | 2017-04-01 | Wind/Battery | 30 | Fuel | No | No | N/A | N/A | Incomplete
15INR0074 | Falvez Astra W | Deaf Smith | 2017-05-01 | Wind | 163 |  | Yes | Yes | N/A | N/A | Complete
16INR0055 | Chapman Ranch Wind I | Nueces | 2017-05-01 | Wind | 250 |  | Yes | Yes | N/A | N/A | Complete
17INR0009 | Wolf Hollow 2 | Hood | 2017-05-01 | Gas | 1118 |  | Yes | Yes | Yes | Yes | Complete
14INR0031 | Baytown Chiller | Chambers | 2017-06-01 | Gas | 270 |  | Yes | Yes | Yes | N/A | Incomplete
16INR0009 | Port Comfort | Calhoun | 2017-06-01 | Gas | 100 |  | Yes | Yes | Yes | Yes | Complete
17INR0007 | Colorado Bend II | Wharton | 2017-06-01 | Gas | 1148 |  | Yes | Yes | Yes | Yes | Complete
17INR0022 | NET Power LaPorte | Harris | 2017-06-01 | Gas | 11 |  | No | Yes | Yes | No | Complete
13INR0049 | Friendswood G | Harris | 2017-07-01 | Gas | 129 |  | Yes | Yes | Yes | Yes | Complete
17INR0042 | Castleman Chamon | Harris | 2017-07-01 | Gas | 100 | Projected Date, PG Section 6.9 | Yes | Yes | Yes | Yes | Complete
11INR0054 | Midway Wind | San Patricio | 2017-08-01 | Wind | 161 |  | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | Nueces | 2017-08-01 | Wind | 180 |  | Yes | Yes | N/A | N/A | Incomplete
11INR0082a | Val Verde Wind | Val Verde | 2017-08-01 | Wind | 149 |  | Yes | Yes | N/A | N/A | Complete
16INR0065b | SP-TX-12-Phase B | Upton | 2017-08-01 | Solar | 120 |  | Yes | Yes | N/A | N/A | Complete
15INR0064 | BearKat Wind A | Glasscock | 2017-09-01 | Wind | 197 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0027 | Dermott Wind 1 | Scurry | 2017-09-01 | Wind | 250 |  | Yes | Yes | N/A | N/A | Complete
12INR0002a | Silver Canyon Wind A | Briscoe | 2017-10-01 | Wind | 200 |  | No | No | N/A | N/A | Incomplete
13INR0056 | Fluvanna Renewable 1 | Scurry | 2017-10-01 | Wind | 155 |  | Yes | Yes | N/A | N/A | Complete
14INR0057 | Buckthorn Wind 1 | Erath | 2017-10-01 | Wind | 96 |  | Yes | Yes | N/A | N/A | Complete
14INR0060b | Willow Springs Wind | Haskell | 2017-10-01 | Wind | 230 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0049 | Nazareth Solar | Castro | 2017-10-01 | Solar | 201 |  | No | No | N/A | N/A | Complete
16INR0062b | Lockett Wind Farm | Wilbarger | 2017-10-01 | Wind | 184 |  | Yes | Yes | N/A | N/A | Complete
15INR0082 | Flat Top Wind I | Comanche | 2017-11-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0059c | Barilla Solar 2 | Pecos | 2017-12-01 | Solar | 21 |  | No | No | N/A | N/A | Incomplete
12INR0060 | Infinity Live Oak Wind | Schleicher | 2017-12-01 | Wind | 201 |  | No | No | N/A | N/A | Complete
13INR0005c | Grandview W 3 | Carson | 2017-12-01 | Wind | 188 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0038 | Swisher Wind | Swisher | 2017-12-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
14INR0023b | Longhorn South | Briscoe | 2017-12-01 | Wind | 160 |  | Yes | Yes | N/A | N/A | Complete
14INR0030c | Panhandle Wind 3 | Carson | 2017-12-01 | Wind | 248 |  | No | No | N/A | N/A | Incomplete
14INR0041a | Bruenning's Breeze | Willacy | 2017-12-01 | Wind | 228 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0044 | West of Pecos Solar | Reeves | 2017-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045a | Torrecillas Wind A | Webb | 2017-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045b | Torrecillas Wind B | Webb | 2017-12-01 | Wind | 200 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0045 | Riggins Solar | Pecos | 2017-12-01 | Solar | 150 |  | Yes | Yes | N/A | N/A | Complete
16INR0019 | Capricorn Ridge Solar | Coke | 2017-12-01 | Solar | 100 |  | No | No | N/A | N/A | Incomplete
16INR0091 | Santa Rita Wind | Reagan | 2017-12-01 | Wind | 300 |  | Yes | Yes | N/A | N/A | Complete
16INR0121 | Salt Fork Wind Expansion | Carson | 2017-12-01 | Wind | 54 |  | No | No | N/A | N/A | Incomplete
16INR0003 | Freeport LNG | Brazoria | 2018-02-01 | Gas | 11 |  | Yes | Yes | Yes | N/A | Complete
12INR0018 | Pampa Wind | Gray | 2018-03-01 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
14INR0033 | Goodnight Wind | Armstrong | 2018-03-01 | Wind | 500 |  | No | No | N/A | N/A | Incomplete
16INR0023b | Lamesa Solar B (Phase II) | Dawson | 2018-03-01 | Solar | 98 |  | No | No | N/A | N/A | Incomplete
16INR0087 | RTS Wind | McCulloch | 2018-03-01 | Wind | 160 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0064b | BearKat Wind B | Glasscock | 2018-04-01 | Wind | 163 |  | Yes | Yes | N/A | N/A | Incomplete
18INR0001 | Rockwood G | Colorado | 2018-04-01 | Gas | 1122 |  | No | No | Yes | No | Complete
13INR0010a | Mariah Del Este | Parmer | 2018-06-01 | Wind | 139 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010c | Mariah Del Sur | Parmer | 2018-06-01 | Wind | 230 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0026 | Canadian Breaks Wind | Oldham | 2018-06-01 | Wind | 201 |  | No | No | N/A | N/A | Complete
16INR0044 | Halyard Wharton | Wharton | 2018-06-01 | Gas | 419 |  | No | No | Yes | Yes | Complete
16INR0045 | Halyard Henderson | Henderson | 2018-06-01 | Gas | 450 |  | No | No | Yes | Yes | Incomplete
16INR0074 | Chocolate Bayou | Brazoria | 2018-06-01 | Wind | 150 |  | No | No | N/A | N/A | Complete
16INR0086 | Cactus Flats Wind | Concho | 2018-06-01 | Wind | 150 | NEW | No | No | N/A | N/A | Incomplete
17INR0003 | SPC Jackson G | Jackson | 2018-06-01 | Gas | 916 |  | No | No | No | No | Complete
17INR0016 | Navasota South Peaker | Wilson | 2018-06-01 | Gas | 582 |  | No | No | Yes | No | Complete
17INR0017 | Clear Springs G | Guadalupe | 2018-06-01 | Gas | 558 |  | No | No | Yes | No | Complete
18INR0013 | Denton Energy Center | Denton | 2018-07-01 | Gas | 226 | NEW | No | No | No | No | Incomplete
17INR0027b | Coyote Wind | Scurry | 2018-09-01 | Wind | 250 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010def | Scandia Wind DEF | Parmer | 2018-10-01 | Wind | 600 |  | No | No | N/A | N/A | Incomplete
15INR0050 | Unity Wind | Deaf Smith | 2018-10-01 | Wind | 203 |  | No | No | N/A | N/A | Incomplete
15INR0079 | Pullman Road | Randall | 2018-10-01 | Wind | 300 |  | No | No | N/A | N/A | Complete
18INR0004 | Shawnee G | Hill | 2018-10-01 | Gas | 928 |  | No | No | Yes | No | Incomplete
10INR0009 | Caprock Wind | Castro | 2018-12-01 | Wind | 300 |  | No | No | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Swisher | 2018-12-01 | Wind | 500 |  | No | No | N/A | N/A | Complete
13INR0045 | Changing Winds | Castro | 2018-12-01 | Wind | 288 |  | No | No | N/A | N/A | Incomplete
16INR0005 | Brownsville G | Cameron | 2018-12-01 | Gas | 871 |  | No | No | Yes | No | Complete
16INR0114 | Upton Solar | Upton | 2018-12-01 | Solar | 102 |  | Yes | Yes | N/A | N/A | Complete
17INR0020a | RE Maplewood 2a Solar | Pecos | 2018-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0059 | Pecos Solar I | Pecos | 2019-01-01 | Solar | 108 |  | No | No | N/A | N/A | Incomplete
16INR0037c | Pumpkin Farm Wind | Floyd | 2019-01-01 | Wind | 281 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0065 | Castle Gap Solar | Upton | 2019-01-01 | Solar | 150 |  | Yes | Yes | N/A | N/A | Complete
15INR0023 | Indeck Wharton | Wharton | 2019-02-01 | Gas | 654 |  | No | No | Yes | Yes | Complete
16INR0008 | Tenaska Roans Prairie | Grimes | 2019-04-01 | Gas | 663 |  | No | No | Yes | No | Complete
16INR0010 | FGE Texas 1 | Mitchell | 2019-04-01 | Gas | 745 |  | No | No | Yes | Yes | Incomplete
14INR0027 | Guadalupe II | Guadalupe | 2019-06-01 | Gas | 362 |  | No | Yes | Yes | No | Complete
17INR0010 | FGE Texas II | Mitchell | 2019-09-01 | Gas | 799 |  | No | No | Yes | No | Incomplete
13INR0023 | Texas Clean C | Ector | 2019-12-01 | Coal | 240 |  | No | No | Yes | Yes | Complete
17INR0020b | RE Maplewood 2b Solar | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020c | RE Maplewood 2c Solar | Pecos | 2019-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0065a | Castle Gap Solar 2 | Upton | 2020-01-01 | Solar | 30 |  | Yes | Yes | N/A | N/A | Complete
16INR0006 | Pinecrest G | Angelina | 2020-04-01 | Gas | 785 |  | No | No | Yes | Yes | Incomplete
13INR0020b | Rattlesnake W 2 | Glasscock | 2020-05-01 | Wind | 158 |  | No | No | N/A | N/A | Complete
15INR0013 | Bethel CAES | Anderson | 2020-11-01 | Gas | 324 | Fuel | No | No | Yes | Yes | Complete
17INR0020d | RE Maplewood 2d Solar | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete
17INR0020e | RE Maplewood 2e Solar | Pecos | 2020-12-01 | Solar | 100 |  | Yes | Yes | N/A | N/A | Incomplete

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
16INR0037b | Old Settler Wind | Floyd | PLANNED | 2017-02-05 | 2015-08-03 | WIND | WT | 150 | 2017 | TRUE
14INR0062 | Salt Fork 1 Wind | Gray | PLANNED | 2017-04-01 | 2014-08-27 | WIND | WT | 174 | 2017 | TRUE
15INR0085 | Tyler Bluff Wind | Cooke | PLANNED | 2017-04-01 | 2015-06-18 | WIND | WT | 126 | 2017 | TRUE
16INR0122 | Blue Summit Battery | Wilbarger | PLANNED | 2017-04-05 | 2017-01-11 | WIND | BA | 30 | 2017 | FALSE
16INR0037 | Cotton Plains Wind | Floyd | PLANNED | 2017-04-15 | 2015-08-03 | WIND | WT | 50 | 2017 | TRUE
15INR0074 | Falvez Astra W | Deaf Smith | PLANNED | 2017-05-04 | 2016-08-18 | WIND | WT | 163 | 2017 | TRUE
16INR0055 | Chapman Ranch Wind I | Nueces | PLANNED | 2017-05-31 | 2015-07-16 | WIND | WT | 250 | 2017 | TRUE
11INR0054 | Midway Wind | San Patricio | PLANNED | 2017-08-01 | 2012-09-24 | WIND | WT | 161 | 2017 | TRUE
11INR0062 | Patriot Wind | Nueces | PLANNED | 2017-08-15 | 2016-10-13 | WIND | WT | 180 | 2017 | TRUE
11INR0082a | Val Verde Wind | Val Verde | PLANNED | 2017-08-31 | 2015-08-12 | WIND | WT | 149 | 2017 | TRUE
17INR0027 | Dermott Wind 1 | Scurry | PLANNED | 2017-09-01 | 2016-08-09 | WIND | WT | 250 | 2017 | TRUE
15INR0064 | BearKat Wind A | Glasscock | PLANNED | 2017-09-15 | 2016-12-20 | WIND | WT | 197 | 2017 | TRUE
14INR0060b | Willow Springs Wind | Haskell | PLANNED | 2017-10-01 | 2015-05-01 | WIND | WT | 230 | 2017 | TRUE
16INR0062b | Lockett Wind Farm | Wilbarger | PLANNED | 2017-10-01 | 2015-03-31 | WIND | WT | 184 | 2017 | TRUE
13INR0056 | Fluvanna Renewable 1 | Scurry | PLANNED | 2017-10-17 | 2015-09-24 | WIND | WT | 155 | 2017 | TRUE
14INR0057 | Buckthorn Wind 1 | Erath | PLANNED | 2017-10-27 | 2015-09-10 | WIND | WT | 96 | 2017 | TRUE
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2017-10-31 | 2016-06-22 | WIND | WT | 200 | 2017 | FALSE
15INR0082 | Flat Top Wind I | Comanche | PLANNED | 2017-11-30 | 2016-02-19 | WIND | WT | 200 | 2017 | TRUE
12INR0060 | Infinity Live Oak Wind | Schleicher | PLANNED | 2017-12-01 | 2016-11-03 | WIND | WT | 201 | 2017 | FALSE
14INR0041a | Bruenning's Breeze | Willacy | PLANNED | 2017-12-01 | 2015-08-12 | WIND | WT | 228 | 2017 | TRUE
16INR0121 | Salt Fork Wind Expansion | Carson | PLANNED | 2017-12-01 | 2016-06-28 | WIND | WT | 54 | 2017 | FALSE
13INR0005c | Grandview W 3 | Carson | PLANNED | 2017-12-15 | 2014-04-23 | WIND | WT | 188 | 2017 | TRUE
13INR0038 | Swisher Wind | Swisher | PLANNED | 2017-12-15 | 2015-09-06 | WIND | WT | 300 | 2017 | TRUE
14INR0023b | Longhorn South | Briscoe | PLANNED | 2017-12-15 | 2012-12-10 | WIND | WT | 160 | 2017 | TRUE
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2017-12-30 | 2014-08-25 | WIND | WT | 248 | 2017 | FALSE
14INR0045a | Torrecillas Wind A | Webb | PLANNED | 2017-12-31 | 2015-01-30 | WIND | WT | 200 | 2017 | TRUE
14INR0045b | Torrecillas Wind B | Webb | PLANNED | 2017-12-31 | 2015-01-30 | WIND | WT | 200 | 2017 | TRUE
16INR0091 | Santa Rita Wind | Reagan | PLANNED | 2017-12-31 | 2017-01-03 | WIND | WT | 300 | 2017 | TRUE
16INR0087 | RTS Wind | McCulloch | PLANNED | 2018-03-15 | 2015-10-14 | WIND | WT | 160 | 2018 | TRUE
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2018-03-28 | 2016-08-09 | WIND | WT | 500 | 2018 | FALSE
12INR0018 | Pampa Wind | Gray | PLANNED | 2018-03-31 | 2013-11-12 | WIND | WT | 500 | 2018 | FALSE
15INR0064b | BearKat Wind B | Glasscock | PLANNED | 2018-04-15 | 2016-12-20 | WIND | WT | 163 | 2018 | TRUE
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-06-01 | 2013-01-31 | WIND | WT | 139 | 2018 | TRUE
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-06-01 | 2013-01-31 | WIND | WT | 230 | 2018 | TRUE
16INR0086 | Cactus Flats Wind | Concho | PLANNED | 2018-06-15 | 2017-03-15 | WIND | WT | 150 | 2018 | TRUE
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2018-06-29 | 2016-05-20 | WIND | WT | 201 | 2018 | FALSE
16INR0074 | Chocolate Bayou | Brazoria | PLANNED | 2018-06-30 | 2016-08-05 | WIND | WT | 150 | 2018 | FALSE
17INR0027b | Coyote Wind | Scurry | PLANNED | 2018-09-01 | 2016-08-09 | WIND | WT | 250 | 2018 | TRUE
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2018-10-01 | 2014-04-25 | WIND | WT | 600 | 2018 | FALSE
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2018-10-01 | 2014-10-03 | WIND | WT | 203 | 2018 | FALSE
15INR0079 | Pullman Road | Randall | PLANNED | 2018-10-31 | 2014-05-29 | WIND | WT | 300 | 2018 | FALSE
10INR0009 | Caprock Wind | Castro | PLANNED | 2018-12-31 | 2014-10-31 | WIND | WT | 300 | 2018 | FALSE
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2018-12-31 | 2013-07-24 | WIND | WT | 500 | 2018 | FALSE
13INR0045 | Changing Winds | Castro | PLANNED | 2018-12-31 | 2015-02-27 | WIND | WT | 288 | 2018 | FALSE
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2019-01-15 | 2016-02-26 | WIND | WT | 281 | 2019 | TRUE
13INR0020b | Rattlesnake W 2 | Glasscock | PLANNED | 2020-05-06 | 2013-06-28 | WIND | WT | 158 | 2020 | FALSE

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year | FS Posted
16INR0073 | East Pecos Solar | Pecos | PLANNED | 2017-03-01 | 2015-03-06 | SOLAR | PV | 120 | 2017 | TRUE
12INR0059b | Barilla Solar 1B | Pecos | PLANNED | 2017-04-15 | 2013-12-26 | SOLAR | PV | 7 | 2017 | TRUE
16INR0023 | BNB Lamesa Solar (Phase I) | Dawson | PLANNED | 2017-04-15 | 2016-07-28 | SOLAR | PV | 102 | 2017 | TRUE
15INR0061 | SolaireHolman 1 | Brewster | PLANNED | 2017-04-25 | 2015-11-10 | SOLAR | PV | 50 | 2017 | TRUE
15INR0070_1b | Pearl Solar | Pecos | PLANNED | 2017-04-28 | 2014-12-17 | SOLAR | PV | 50 | 2017 | TRUE
16INR0065b | SP-TX-12-Phase B | Upton | PLANNED | 2017-08-15 | 2015-10-29 | SOLAR | PV | 120 | 2017 | TRUE
16INR0049 | Nazareth Solar | Castro | PLANNED | 2017-10-01 | 2015-05-15 | SOLAR | PV | 201 | 2017 | FALSE
14INR0044 | West of Pecos Solar | Reeves | PLANNED | 2017-12-01 | 2017-02-27 | SOLAR | PV | 100 | 2017 | TRUE
16INR0019 | Capricorn Ridge Solar | Coke | PLANNED | 2017-12-01 | 2015-08-19 | SOLAR | PV | 100 | 2017 | FALSE
15INR0045 | Riggins Solar | Pecos | PLANNED | 2017-12-22 | 2015-01-26 | SOLAR | PV | 150 | 2017 | TRUE
12INR0059c | Barilla Solar 2 | Pecos | PLANNED | 2017-12-31 | 2013-12-26 | SOLAR | PV | 21 | 2017 | FALSE
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2018-03-31 | 2015-06-25 | SOLAR | PV | 98 | 2018 | FALSE
16INR0114 | Upton Solar | Upton | PLANNED | 2018-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2018 | TRUE
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2018-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2018 | TRUE
15INR0059 | Pecos Solar I | Pecos | PLANNED | 2019-01-01 | 2015-06-09 | SOLAR | PV | 108 | 2019 | TRUE
16INR0065 | Castle Gap Solar | Upton | PLANNED | 2019-01-01 | 2015-09-04 | SOLAR | PV | 150 | 2019 | TRUE
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2019-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2019 | TRUE
16INR0065a | Castle Gap Solar 2 | Upton | PLANNED | 2020-01-01 | 2015-09-04 | SOLAR | PV | 30 | 2020 | TRUE
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE
17INR0020e | RE Maplewood 2e Solar | Pecos | PLANNED | 2020-12-31 | 2016-02-03 | SOLAR | PV | 100 | 2020 | TRUE