## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
August 16, 2018

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
    NPRR833 Update
  2018 Release Targets
  Planned Project Starts
  2018 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Appendix
  Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2018 August Release – 8/7/2018 – 8/9/2018 In Flight
  NPRR819 – Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups
  NPRR844 – Clarification to Outage Report
  NPRR854 – NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage
  SCR791 – Correction of 60-day SCED GRD Disclosure Report
Release Target Update In Flight
  NPRR833 – Modify PTP Obligation Bid Clearing Change
    R5 (late October 2018)
      DAM changes
    R6 (mid-December 2018)
      SCED changes
    Defer CRR changes until CRR Upgrade completes
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/6 – 2/8 | April 4/5 – 4/9 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/23 – 10/25 | December 12/11 – 12/13
NPRR659 NPRR683 NPRR743 NPRR760 NPRR800 NPRR810 PGRR042 NPRR846 | NPRR562(b) SCR792 | NPRR768 NPRR815 OBDRR002 NPRR776 NOGRR167 | NPRR819 NPRR844 NPRR854 SCR791 GINR Go-Live (Interconnecting Entities only) | NPRR833(a) NPRR843 NPRR854 NPRR864 RRGRR015 RRGRR016 SCR795 | NPRR519 NPRR620 NPRR741 NPRR755 PGRR057 NPRR809(b) NPRR833(b) NPRR842 NPRR858 SCR794
8 | 2 | 5 | 4 | 6 | 6
6/1
E
E
E
E
E
E
E
E
E
E
E
E
E
I
NS
E
8/30
CMM Release 1a
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
1/1 & 2/1
NPRR825(a) – NoticeBuilder changes
NPRR562(b) – Reporting/posting system changes
NPRR809(b) – Reporting/posting system changes
NPRR833(a) – DAM system changes
NPRR833(b) – SCED system changes
CMM Release 1b
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NPRR664 | None | SCR781 P | NPRR702 P, SCR777, NPRR831(b), NPRR749 E, NPRR833 E, NPRR825(a), NPRR519, NPR620, NPRR741, NPRR755
1/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR858 – Provide Complete Current Operating Plan (COP) Data | Aug 2018 | 2018-R6 | $25k-$45k | Citigroup Energy
NPRR865 – Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties | Oct 2018 | 2019-R1 | $30k-$40k | DC Energy
SCR793 – SSR Related Telemetry for Transmission Service Provider (TSP) Operators | Oct 2018 | 2019-R1 | $40k-$50k | Cross Texas Transmission
NPRR817 – Create a Panhandle Hub | Jan 2019 | 2019-R3 | $150k-$200k | DC Energy
Aging Items Report | Last Action | Status
NPRR664 – Fuel Index Price for Resource Definition and Real-Time Make-Whole Payments for Exceptional Fuel Cost Events | Board approved on 12/9/2014 | Pending approval of NPRR847
Project Initiations – Next 3 Months
Moved from October start
Moved from September start to provide bandwidth for NPRR833 work

## Slide 6: 2018 Project Spending
2018 PPL Budget = $20.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2018 and 2019, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2018 | 2019
YTD Actuals | $1.00M | 
Approved – In-Flight / Complete | $1.81M | $0.20M
Approved – On Hold | $0.00M | $0.00M
Approved – Not Started | $0.32M | $0.30M
Remaining Funding | $1.87M | $3.50M
Total Allocation | $4.00M | $4.00M
As of 6/30/2018
SCR789
July data not available at time of mailing
No change from last month’s report

## Slide 8: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
 | None |  |  | 
Options for…
PPL Rank Information
Next available 2018 Rank in Business Strategy = 2300
Next available 2019 Rank in Business Strategy = 2550
Next available Rank in Regulatory = 220

## Slide 9
Appendix
  8/1/2018 Project Gantt
    In-flight items sorted by Project End Date
    “Not Started” items sorted by Project Start Date

## Slide 10: Project Portfolio Status – as of 8/1/2018

## Slide 11: Project Portfolio Status – as of 8/1/2018

## Slide 12: Project Portfolio Status – as of 8/1/2018

## Slide 13: Project Portfolio Status – as of 8/1/2018

## Slide 14: Project Portfolio Status – as of 8/1/2018

## Slide 15: Project Portfolio Status – as of 8/1/2018 – On Hold

## Slide 16: Project Portfolio Status – as of 8/1/2018 – Not Started