## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 07/24 - 25/2018
Agenda Item: | Decision / Resolution | Action Items :
June 2018 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will have the notes posted to the June 20, 2018 meeting page.
Retail Market Subcommittee (RMS) Updates
NPRR850, Market Suspension and Restart—Left tabled | The Texas SET Chair provided the update.
Flight Testing | The Texas SET Chair presented the ERCOT provided update.
Proposed 2019 Test Flight Schedule | The Texas SET Chair presented and reviewed the proposed test schedule. Texas SET reached consensus on the schedule. | The Texas SET Chair will present the schedule to RMS and request that they vote to approve.
RMS Assignments
Mass Transition Yearly / Biennial Testing Needs--Scripts | Texas SET began to analyze and create the process flows to assist in developing the test scripts. 1. Discussion was related to how complex the scripts should be. 2. Some attendees expressed a need for a basic script; then develop a separate more complex script that contains competitive switches. 3. Texas SET agreed to continue the discussions at the August meetings. 4. Texas SET agreed that the biennial testing should be conducted during March of the required tesing year. | The Texas SET Chair will send out the updated draft of process flows.
MISP Workshop Action Items • Draft market communications processes/requirements for extended unplanned outages - language should highlight the responsibility of CR or MISP acting on behalf of CR (RMGRR) • Add a MISP definition in RMG (RMGRR) • Look at whether the established/non-established designation need to be removed for MISPs in the TMTP (possible revision request) • Revisit testing worksheet – update required contact information and discuss schedule for required updates • Codify impacted processes for extended unplanned outages in 7.10 and add language regarding post start reconciliation processes (RMGRR) | See notes contained in the RMSAssignmentToTXSETMISPAndMassTransBiennialTesting_07242018 file separately attached. | The Texas SET Chair will send out the draft documents for review and feedback.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Discussion Items
Construction Hold--ONCOR | Texas SET reviewed the draft change control presented for premises in the ONCOR territory where a move in is scheduled; then put on hold due to construction reasons. 1, Texas SET suggested that a code be used in the 814_04 as opposed to a new code for the 814_28. It was noted that the 814_28 closes out the move in request where the 814_04 would allow the order to stay open. 2. ONCOR will take back internally to review and return with an update to the August 22 meeting. | ONCOR to bring back feedback next month.
Proposed Texas SET Release Changes.-Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix. | This agenda item is posponed until the August meeting
Counties and Their Relationship with ESI IDs In the TDSPs' Systems--TDSP feedback | Texas SET discussed the TDSP feedback. 1. TDSPs stated that they would not be able to provide zip codes by county in Weather Moratorium notifications due to, but not limited to overlap of zip codes between counties. 2, TDSPs stated that they would not be able to provide GPS locations for ESI IDs due to accuracy concerns. 3. Texas SET agreed that it might be possible to add a county code to the ESI ID attributes passed in the transactions. The change would be for a future Texas SET release. 4. Texas SET discussed alternative methods of providing notice to the market besides the email notifications used by the TDSPs today. | The Texas SET Chair will add this topic to the Proposed Texas SET Release changes documents. Texas SET will continue discussion at the August meeting.
Automate the Inadvertent Gain process by replacing MarkeTrak with EDI transactions--Proposal | Texas Data Transport and MarkeTrak Systems (TDTMS) leadership requested that Texas SET review and analyze a possible solution for using EDI transactions as opposed to MarkeTrak. | The Texas SET Chair will add this topic to the August agenda.
Parking Lot
REP Certification Matrix—Long-term solution | On Hold
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS PUCT Staff has under rule review | Oh Hold until 2018
Next Meeting--ERCOT MET Center | August 22 - 23, 2018
Attendees F-T-F
2018-07-24
Diana Rehfeldt TNMP | Rebecca Zerwas NRG
Kaci Jacobs TXUE | Lindsay Butterfield ERCOT
Same Pak ONCOR | Kathy Scott CNP
Carolyn Reed CNP | Jim Lee AEP
Kyle Patrick NRG | Ivan Velaszuez ONCOR
Attendees Webex
2018-07-24
Deb Belin Marketwise | Matt Hansen Gexa | Deborah Croces ECInfoSystems
Dave Michelsen ERCOT | Mike Woolsey ONCOR
Henry Hewy Big Data Energy | Toni Marks
Kathryn Thurman ERCOT | Connie Herrmes NEC
Phil Bracy ERCOT | Kim Wall Hansen Technologies
Sheri Wiegand TXUE | Mary Sithihou Stream Energy
Teresa Rodriquez Stream Energy | William Hardee Big Data Energy
Attendees F-T-F
2018-07-25
Diana Rehfeldt TNMP | Rebecca Zerwas NRG
Kaci Jacobs TXUE | Lindsay Butterfield ERCOT
Same Pak ONCOR | Kathy Scott CNP
Carolyn Reed CNP | Jim Lee AEP
Kyle Patrick NRG
Attendees Webex
2018-07-25
Deb Belin Marketwise | Matt Hansen Gexa | Deborah Croces ECInfoSystems
Dave Michelsen ERCOT | Mike Woolsey ONCOR | Tracie Gaetano IGS Accent Energy
Henry Hewy Big Data Energy | Toni Marks | Ted Hailu ERCOT
Kathryn Thurman ERCOT | Connie Herrmes NEC
Phil Bracy ERCOT | Kim Wall Hansen Technologies
Sheri Wiegand TXUE | Mary Sithihou Stream Energy
Teresa Rodriquez Stream Energy | William Hardee Big Data Energy