## Slide 1
ERCOT MET Center
7620 Metro Center Dr
Austin, TX 78744
Sept 18, 2018
Oncor Far West TX Update

## Slide 2
FWTx1 Project
Notes: ***Utilization of CREZ infrastructure
Focus is on customer communication, quick hit upgrades and maximizing existing capabilities while implementing long-term solutions
Progress is increasingly challenging given the limitations of permissible outages and clearances from ERCOT, and the overall state of congestion.
Capex:
2011/2012 = ~$7M
2013 = ~$44M
2014+ = ~$195M (includes two CCN projects)

## Slide 3
FWTx2 Project/DRD Project
Notes: ***Utilization of CREZ infrastructure
Focus is on customer communication, quick hit upgrades and maximizing existing capabilities while implementing long-term solutions
Progress is increasingly challenging given the limitations of permissible outages and clearances from ERCOT, and the overall state of congestion.
Capex:
2011/2012 = ~$7M
2013 = ~$44M
2014+ = ~$195M (includes two CCN projects)

## Slide 4
Far West Texas Project
  Approved by ERCOT Board of Directors in Jun 2017
  Odessa EVH – Riverton 345 kV Line
  Bakersfield – Solstice 345 kV Line
Far West Texas Project 2
  Approved by ERCOT Board of Directors on June 2018
  Close 345 kV loop and new 138 kV lines
Dynamic Reactive Devices Project
  Approved by ERCOT Board of Directors on June 2018
  Immediate voltage support needs due to load increases
  Expected in-service in 2019
Odessa EHV – Riverton 345 kV Line
  Critical Status approved by ERCOT BOD Feb 2018
  CCN filed at PUC in March 2018
  On 9/14/18 PUC Agenda for discussion/possible approval.
Riverton – Sand Lake – Solstice – Bakersfield 345 kV Lines
  Critical Status approved by ERCOT BOD June 2018
  CCNs planned to be filed Fall 2018
Far West Texas Projects

## Slide 5
  Spring 2018 – In-Service
        Construct New Riverton 138 kV Switch
        Install second circuit on Wink – Culberson 138 kV Line
        Install Pirate Cove 138 kV Capacitors
        Construct New Fullerton 138 kV Switch
        Rebuild Holt 138 kV Switch
  Fall 2018 – Scheduled In-Service
        Install Wink – Yukon 138 kV Line
        Install Holt – Andrews County South/North Andrews 138 kV Line
        Rebuild Yucca (Oncor) – Barilla Junction (AEP) 138 kV Line
        Construct New Littman – Fullerton 138 kV Line
2018 Planned Transmission Projects

## Slide 6
2018 Transmission Improvements

## Slide 7
  Spring 2019 – Scheduled In Service
      Construct New Sand Lake 138 kV Switch
      Construct New Riverton – Sand Lake 138 kV Line
      Construct Horseshoe Springs 138 kV Switch
      Install Horseshoe Springs 138 kV Capacitors
      Install Horseshoe Draw Dynamic Reactive Device
      Install second circuit on Wink – Yukon 138 kV Line
      Rebuild Wink – No Trees 138 kV Line
      Install series reactor at Wolf & Yucca 138 kV Switch
      Install Moss 345/138 kV autotransformer #2
  Fall 2019 – Scheduled In Service
      Construct Quarry Field 138 kV Switch
      Install Quarry Field 138 kV capacitors
      Install Rondo Dynamic Reactive Device
      Construct New Horseshoe Springs – Owl Hills 138 kV Line
      Construct New Owl Hills – Tunstill 138 kV Line
2019 Planned Transmission Projects

## Slide 8
2019 Transmission Improvements

## Slide 9
  Spring 2020 – Scheduled In Service
      Rebuild Cowden North – Odessa North 138 kV Line
      Rebuild Andrews County South – No Trees 138 kV Line
      Construct New Kyle Ranch – Quarry Field 138 kV Line
      Construct New Riverton – Kyle Ranch 138 kV Line
  Fall 2020 – Scheduled In Service
      Construct New Riverton – Odessa EHV / Moss 345 kV Line
      Construct New Riverton 345 kV Switch
      Install Riverton – Sand Lake 345 kV Line
      Construct New Sand Lake 345 kV Switch
      Construct New Sand Lake – Solstice 345 kV Line
2020 Planned Transmission Projects

## Slide 10
2020 Improvements

## Slide 11: QUESTIONS/DISCUSSION