## Slide 1
CRR Update
Carrie Bivens
Manager, Forward Markets
CMWG
September 21, 2018

## Slide 2: Upgrade is Ready for Production
Stability criteria | Status
All test scripts reviewed and approved | 
Full regression test completed, with all functionality tested | 
Zero Priority 1 and zero Priority 2 defects | 
Performance testing complete | 
Auction results do not differ meaningfully from current | 
Complete validation of converted data | 
Penetration testing complete | 
Business procedures completed and approved | 
User documentation updated and available for MPs | 

## Slide 3: Dates to Remember
60-day market notice sent on September 18, 2018
November 12, 2018 is the last day to qualify on current Market User Interface (MUI)
  Any new CRR Account Holders (CRRAHs) or Counter-Parties (CPs) will only be qualified on the new MUI after this date and can start participating in auctions held after the upgrade.
    Currently there are 28 registered CRRAHs that haven’t completed requalification: 9 are not yet qualified on the current system; 6 have said they don’t plan to requalify
November 19, 2018 is MUI implementation go-live
  Any CRRAHs or CPs that have not completed qualification or requalification will not be able to participate in any auctions after this date, until a qualification test is passed.

## Slide 4: Remaining Activities
ERCOT Account Managers will contact CRRAHs that still need to qualify on the upgraded MUI
  Successful requalifications in 2017 are still effective; no need to submit the test again
MOTE remains open and ERCOT encourages re-familiarization with the new MUI
CRR team is considering adding a test auction to MOTE to allow CRRAHs to exercise the full process including downloading results
  Planning a test bid window for Tue 10/23 – Thur 10/25
  November monthly auction
  Expect a market notice next week with details, as well as an “auction notice” on 10/12
  Optional participation

## Slide 5: NPRRs/SCRs
Going live with the upgrade:
SCR777 - Bilateral CRR Interface Enhancement
NPRR648 - Remove References to Flowgate Rights
NPRR831 - Inclusion of Private Use Networks in Load Zone Price Calculations (CRR portion only)
Status of deferred:
NPRR833 - Modify PTP Obligation Bid Clearing (CRR portion only) and NPRR749 - Option Cost for Outstanding CRRs are being replanned
  Will be in the first post-go-live bundle, date TBD
  CRR upgrade stabilization period ends February 27, 2019

## Slide 6: Notable Change
With the framework upgrade, all ratings in CRR pre-auction files (Non-Thermal Constraints and Monitored Elements) will be posted already scaled according to the auction capacity percentage.
  Currently the ratings are NOT scaled in these files, and MPs have to perform the scaling during their own analysis process. This change removes that step.
  The RAW file remain unscaled – that file is produced directly from the Topology Processor
  Will ensure that this is clearly communicated

## Slide 7: Additional Item About Locking Credit
On September 10, 2018, ERCOT sent a reminder Market Notice about allocating credit for CRR auctions
  Contains reminders for steps on how a CRRAH can check if their CP has locked credit yet
As a courtesy, ERCOT has been monitoring situations in which a portfolio has been submitted by the CRRAH but no credit locked by the CP on the bid window close day
  When possible, the ERCOT Account Manager calls the account rep to remind them about the deadline
Concern about strain on ERCOT resources and that MPs are or may start relying on this courtesy
ERCOT will cease this proactivity and encourages Market Participants to plan ahead for tasks necessary on bid window close/credit lock dates
  The CRR Calendar with all the relevant dates are posted far in advance
  A Market Notice is sent for each auction when the credit window opens