## Wind Chart
[5 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[5 empty] | 17INR0104 | Capricorn 4 repower | Coke | 2018-11-01 | 2018-05-01 | Wind | WT | 0 | 2018 | No
[5 empty] | 17INR0068 | Sweetwater 2 repower | Nolan | 2018-11-15 | 2017-11-17 | Wind | WT | 7.3 | 2018 | No
[5 empty] | 17INR0069 | Trent repower | Nolan | 2018-11-28 | 2018-10-19 | Wind | WT | 6.4 | 2018 | No
[5 empty] | 12INR0060 | Wilson Ranch | Schleicher | 2018-12-05 | 2018-05-21 | Wind | WT | 199.5 | 2018 | Yes
[5 empty] | 11INR0054 | Midway Wind | San Patricio | 2018-12-15 | 2017-11-05 | Wind | WT | 162.9 | 2018 | Yes
[5 empty] | 16INR0086 | Cactus Flats Wind | Concho | 2018-12-15 | 2017-03-15 | Wind | WT | 148.4 | 2018 | Yes
[5 empty] | 18INR0068 | Loraine Windpark Phase III | Mitchell | 2018-12-21 | 2018-04-10 | Wind | WT | 100 | 2018 | Yes
[5 empty] | 13INR0010a | Mariah Del Este | Parmer | 2018-12-31 | 2013-01-31 | Wind | WT | 152.5 | 2018 | Yes
[5 empty] | 14INR0045 | Torrecillas Wind | Webb | 2018-12-31 | 2018-04-12 | Wind | WT | 300.5 | 2018 | Yes
[5 empty] | 15INR0035 | Stella 1 Wind | Kenedy | 2018-12-31 | 2017-08-02 | Wind | WT | 201 | 2018 | Yes
[5 empty] | 18INR0069 | Indian Mesa repower | Pecos | 2019-01-01 | 2018-05-29 | Wind | WT | 0 | 2019 | No
[5 empty] | 18INR0025 | Tahoka Wind | Lynn | 2019-01-02 | 2018-01-03 | Wind | WT | 300 | 2019 | Yes
[5 empty] | 18INR0070 | Blue Summit II | Wilbarger | 2019-01-15 | 2018-04-28 | Wind | WT | 102 | 2019 | Yes
[5 empty] | 11INR0062 | Shaffer | Nueces | 2019-04-01 | 2018-04-13 | Wind | WT | 226 | 2019 | Yes
[5 empty] | 12INR0055 | S_Hills Wind | Baylor | 2019-04-01 | 2017-12-04 | Wind | WT | 30.24 | 2019 | Yes
[5 empty] | 17INR0005 | Cabezon Wind | Starr | 2019-04-01 | 2017-08-03 | Wind | WT | 237.6 | 2019 | Yes
[5 empty] | 20INR0011 | Ranchero Wind | Crockett | 2019-06-04 | 2018-05-02 | Wind | WT | 300 | 2019 | Yes
[5 empty] | 18INR0033 | Oveja Wind | Irion | 2019-06-30 | 2018-07-24 | Wind | WT | 300 | 2019 | Yes
[5 empty] | 18INR0067 | Gopher Creek Wind | Scurry | 2019-07-31 | 2018-01-26 | Wind | WT | 158 | 2019 | Yes
[5 empty] | 17INR0037 | Palmas Altas Wind | Cameron | 2019-08-01 | 2017-11-30 | Wind | WT | 144.9 | 2019 | Yes
[5 empty] | 14INR0033 | Goodnight Wind | Armstrong | 2019-08-11 | 2018-03-07 | Wind | WT | 496.8 | 2019 | No
[5 empty] | 19INR0019 | Foard City Wind | Foard | 2019-09-01 | 2018-02-19 | Wind | WT | 350 | 2019 | Yes
[5 empty] | 19INR0099a | Kontiki 1 Wind (ERIK) | Glasscock | 2019-09-01 | 2018-05-07 | Wind | WT | 255.3 | 2019 | Yes
[5 empty] | 13INR0026 | Canadian Breaks Wind | Oldham | 2019-09-13 | 2016-05-20 | Wind | WT | 210 | 2019 | Yes
[5 empty] | 13INR0025 | Northdraw Wind | Randall | 2019-09-30 | 2018-04-25 | Wind | WT | 150 | 2019 | No
[5 empty] | 16INR0062b | Lockett Wind | Wilbarger | 2019-09-30 | 2015-03-31 | Wind | WT | 184 | 2019 | Yes
[5 empty] | 15INR0064b | Harald (BearKat Wind B) | Glasscock | 2019-10-04 | 2018-05-30 | Wind | WT | 162.1 | 2019 | Yes
[5 empty] | 14INR0009 | WKN Amadeus Wind | Kent | 2019-10-31 | 2018-03-15 | Wind | WT | 245.9 | 2019 | No
[5 empty] | 19INR0163 | Sage Draw Wind | Lynn | 2019-10-31 | 2018-01-03 | Wind | WT | 300 | 2019 | No
[5 empty] | 13INR0010def | Scandia Wind DEF | Parmer | 2019-11-01 | 2014-04-25 | Wind | WT | 600.3 | 2019 | No
[5 empty] | 18INR0064 | Silver Star repower | Eastland | 2019-11-01 | 2018-10-16 | Wind | WT | -7.2 | 2019 | No
[5 empty] | 16INR0081 | Mesteno Wind | Starr | 2019-11-30 | 2018-04-25 | Wind | WT | 201.6 | 2019 | Yes
[5 empty] | 16INR0112 | Loma Pinta Wind | La Salle | 2019-11-30 | 2017-12-13 | Wind | WT | 200 | 2019 | No
[5 empty] | 19INR0038 | High Lonesome W | Crockett | 2019-11-30 | 2018-04-17 | Wind | WT | 500 | 2019 | No
[5 empty] | 16INR0037c | Pumpkin Farm Wind | Floyd | 2019-12-01 | 2017-03-24 | Wind | WT | 280.9 | 2019 | Yes
[5 empty] | 18INR0018 | Peyton Creek Wind | Matagorda | 2019-12-01 | 2018-03-19 | Wind | WT | 151.2 | 2019 | Yes
[5 empty] | 18INR0038 | Barrow Ranch | Andrews | 2019-12-01 | 2018-06-26 | Wind | WT | 160 | 2019 | Yes
[5 empty] | 19INR0051 | Vera Wind | Knox | 2019-12-01 | 2018-07-10 | Wind | WT | 242.8 | 2019 | No
[5 empty] | 17INR0027b | Coyote Wind | Scurry | 2019-12-02 | 2016-08-09 | Wind | WT | 242.5 | 2019 | Yes
[5 empty] | 18INR0059 | Raymond Wind | Willacy | 2019-12-15 | 2018-09-18 | Wind | WT | 201.6 | 2019 | Yes
[5 empty] | 19INR0052 | TG East Wind | Knox | 2019-12-15 | 2018-10-22 | Wind | WT | 275.6 | 2019 | No
[5 empty] | 12INR0029 | Comanche Run Wind | Swisher | 2019-12-31 | 2013-07-24 | Wind | WT | 500 | 2019 | No
[5 empty] | 18INR0014 | Karankawa Wind | San Patricio | 2019-12-31 | 2017-11-30 | Wind | WT | 200 | 2019 | Yes
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security | 18INR0016 | RTS 2 Wind | McCulloch | 2019-12-31 | 2017-11-21 | Wind | WT | 179.8 | 2019 | Yes
2000 | 116 | 116 | 0 | 0 | 18INR0023 | Darmstadt | Schleicher | 2019-12-31 | 2018-05-11 | Wind | WT | 200.9 | 2019 | No
2001 | 816 | 816 | 0 | 0 | 19INR0074 | Karankawa 2 Wind | San Patricio | 2019-12-31 | 2018-03-02 | Wind | WT | 200 | 2019 | Yes
2002 | 977 | 977 | 0 | 0 | 19INR0112 | Cranel Wind | Refugio | 2019-12-31 | 2018-10-12 | Wind | WT | 220 | 2019 | Yes
2003 | 1173 | 1173 | 0 | 0 | 18INR0029 | Armstrong Wind | Armstrong | 2020-03-31 | 2018-08-31 | Wind | WT | 253 | 2020 | No
2004 | 1385 | 1385 | 0 | 0 | 19INR0100 | Prairie Hill Wind | Limestone | 2020-06-01 | 2018-09-17 | Wind | WT | 300 | 2020 | Yes
2005 | 1854 | 1854 | 0 | 0 | 18INR0043 | Edmondson Ranch Wind | Glasscock | 2020-06-26 | 2017-10-04 | Wind | WT | 292.5 | 2020 | Yes
2006 | 2875 | 2875 | 0 | 0 | 18INR0030 | Canyon Wind | Scurry | 2020-06-30 | 2018-09-20 | Wind | WT | 360 | 2020 | No
2007 | 4785 | 4785 | 0 | 0 | 19INR0099b | Kontiki 2 Wind | Glasscock | 2020-09-01 | 2018-05-07 | Wind | WT | 255.3 | 2020 | Yes
2008 | 8005 | 8005 | 0 | 0 | 20INR0045 | Maverick Creek I | Concho | 2020-09-01 | 2018-07-31 | Wind | WT | 252 | 2020 | No
2009 | 8916 | 8916 | 0 | 0 | 20INR0046 | Maverick Creek II | Concho | 2020-09-01 | 2018-07-31 | Wind | WT | 252 | 2020 | No
2010 | 9400 | 9400 | 0 | 0 | 17INR0035 | Las Majadas Wind | Willacy | 2020-10-01 | 2018-04-13 | Wind | WT | 272.8 | 2020 | No
2011 | 9604 | 9604 | 0 | 0 | 12INR0002a | Silver Canyon Wind A | Briscoe | 2020-10-31 | 2016-06-22 | Wind | WT | 200 | 2020 | No
2012 | 10407 | 10407 | 0 | 0 | 15INR0063 | Easter Wind | Castro | 2020-10-31 | 2018-06-01 | Wind | WT | 307.5 | 2020 | No
2013 | 11065 | 11065 | 0 | 0 | 20INR0019 | Trinity Hills Wind repower | Young | 2020-11-01 | 2018-10-17 | Wind | WT | -27 | 2020 | No
2014 | 12470 | 12470 | 0 | 0 | 14INR0030c | Panhandle Wind 3 | Carson | 2020-12-01 | 2014-08-25 | Wind | WT | 248 | 2020 | Yes
2015 | 15764 | 15764 | 0 | 0 | 20INR0042 | Chalupa Wind | Cameron | 2020-12-21 | 2018-09-28 | Wind | WT | 174 | 2020 | Yes
2016 | 17604 | 17604 | 0 | 0 | 13INR0038 | Wildrose Wind | Swisher | 2020-12-30 | 2015-09-06 | Wind | WT | 302.5 | 2020 | Yes
2017 | 20682 | 20682 | 0 | 0 | 16INR0033 | Hart Wind | Castro | 2020-12-31 | 2018-08-06 | Wind | WT | 150 | 2020 | No
2018 | 22828.5 | 21550 | 1264.8 | 13.7
2019 | 31531.34 | 21550 | 6262.54 | 3718.8
2020 | 35123.94 | 21550 | 7834.84 | 5739.1

## Solar Chart
[5 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[5 empty] | 12INR0059b | HOVEY (Barilla Solar 1B) | Pecos | 2018-09-22 | 2013-12-26 | Solar | PV | 7.4 | 2018 | Yes
[5 empty] | 16INR0019 | BlueBell Solar | Coke | 2018-12-01 | 2015-08-19 | Solar | PV | 30 | 2018 | Yes
[5 empty] | 16INR0115 | Waymark Solar | Pecos | 2018-12-12 | 2016-09-23 | Solar | PV | 182 | 2018 | Yes
[5 empty] | 16INR0023b | Lamesa Solar B (Phase II) IVORY | Dawson | 2018-12-31 | 2016-07-28 | Solar | PV | 50 | 2018 | Yes
[5 empty] | 19INR0029 | Phoebe Solar | Winkler | 2019-10-01 | 2018-03-05 | Solar | PV | 250 | 2019 | Yes
[5 empty] | 19INR0092 | Prospero Solar | Andrews | 2019-10-01 | 2018-04-20 | Solar | PV | 300 | 2019 | No
[5 empty] | 18INR0045 | Misae Solar | Childress | 2019-11-29 | 2018-07-18 | Solar | PV | 240.8 | 2019 | Yes
[5 empty] | 19INR0102 | Queen Solar | Upton | 2019-11-30 | 2018-09-27 | Solar | PV | 400 | 2019 | No
[5 empty] | 15INR0059 | Emerald Grove Solar | Pecos | 2019-12-01 | 2018-06-27 | Solar | PV | 108 | 2019 | Yes
[5 empty] | 16INR0114 | Upton Solar | Upton | 2019-12-01 | 2015-12-04 | Solar | PV | 102 | 2019 | Yes
[5 empty] | 14INR0044 | West of Pecos Solar | Reeves | 2019-12-15 | 2017-02-27 | Solar | PV | 100 | 2019 | Yes
[5 empty] | 19INR0083 | Oberon Solar | Ector | 2019-12-15 | 2018-10-11 | Solar | PV | 180 | 2019 | No
[5 empty] | 19INR0114 | Rambler Solar | Tom Green | 2019-12-30 | 2018-10-11 | Solar | PV | 150 | 2019 | No
[5 empty] | 15INR0090 | Pflugerville Solar | Travis | 2019-12-31 | 2017-06-13 | Solar | PV | 144 | 2019 | No
[5 empty] | 17INR0020a | RE Maplewood 2a Solar | Pecos | 2019-12-31 | 2016-02-03 | Solar | PV | 100 | 2019 | Yes
[5 empty] | 17INR0020b | RE Maplewood 2b Solar | Pecos | 2019-12-31 | 2016-02-03 | Solar | PV | 100 | 2019 | Yes
[5 empty] | 17INR0020c | RE Maplewood 2c Solar | Pecos | 2019-12-31 | 2016-02-03 | Solar | PV | 100 | 2019 | Yes
[5 empty] | 18INR0022 | Winkler Solar | Winkler | 2019-12-31 | 2018-01-23 | Solar | PV | 150 | 2019 | No
[5 empty] | 16INR0049 | Nazareth Solar | Castro | 2020-05-01 | 2018-05-10 | Solar | PV | 201 | 2020 | No
[5 empty] | 18INR0055 | Long Draw Solar | Borden | 2020-06-30 | 2018-08-16 | Solar | PV | 225 | 2020 | Yes
[5 empty] | 18INR0040 | Soda Lake Solar 1 | Crane | 2020-07-01 | 2018-08-20 | Solar | PV | 200 | 2020 | No
[5 empty] | 19INR0088 | Aragorn Solar | Culberson | 2020-07-31 | 2018-05-31 | Solar | PV | 186.3 | 2020 | No
[5 empty] | 17INR0020d | RE Maplewood 2d Solar | Pecos | 2020-12-31 | 2016-02-03 | Solar | PV | 100 | 2020 | Yes
[5 empty] | 17INR0020e | RE Maplewood 2e Solar | Pecos | 2020-12-31 | 2016-02-03 | Solar | PV | 100 | 2020 | Yes
[5 empty] | 20INR0143 | Soda Lake Solar 2 | Crane | 2020-12-31 | 2018-08-20 | Solar | PV | 200 | 2020 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security
2010 | 15 | 15 | 0 | 0
2011 | 42 | 42 | 0 | 0
2012 | 82 | 82 | 0 | 0
2013 | 121 | 121 | 0 | 0
2014 | 193 | 193 | 0 | 0
2015 | 287.7 | 287.7 | 0 | 0
2016 | 556 | 556 | 0 | 0
2017 | 1000 | 1000 | 0 | 0
2018 | 1756.4 | 1487 | 269.4 | 0
2019 | 4181.2 | 1487 | 1370.2 | 1324
2020 | 5393.5 | 1487 | 1795.2 | 2111.3

## Battery Chart
[5 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security
2012 | 36 | 36 | 0 | 0
2013 | 36 | 36 | 0 | 0
2014 | 36 | 36 | 0 | 0
2015 | 36 | 36 | 0 | 0
2016 | 37 | 37 | 0 | 0
2017 | 69 | 69 | 0 | 0
2018 | 89 | 89 | 0 | 0

## Gas-Combined Cycle Chart
[5 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[5 empty] | 16INR0054 | NA | Harris | 2018-09-01 | 2016-10-27 | Gas | CC | 12 | 2018 | Yes
[5 empty] | 16INR0010 | FGE Texas 1 Gas | Mitchell | 2021-04-30 | 2016-08-31 | Gas | CC | 742.9 | 2021 | No
[5 empty] | 17INR0010 | FGE Texas 2 Gas | Mitchell | 2022-05-25 | 2015-06-02 | Gas | CC | 742.9 | 2022 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security
1999 | 2867 | 2867 | 0 | 0
2000 | 7381 | 7381 | 0 | 0
2001 | 13967 | 13967 | 0 | 0
2002 | 18443 | 18443 | 0 | 0
2003 | 24141 | 24141 | 0 | 0
2004 | 25641 | 25641 | 0 | 0
2005 | 25539 | 25539 | 0 | 0
2006 | 26258 | 26258 | 0 | 0
2007 | 26815 | 26815 | 0 | 0
2008 | 27376 | 27376 | 0 | 0
2009 | 28309 | 28309 | 0 | 0
2010 | 29770 | 29770 | 0 | 0
2011 | 30488 | 30488 | 0 | 0
2012 | 30488 | 30488 | 0 | 0
2013 | 30538 | 30538 | 0 | 0
2014 | 33080 | 33080 | 0 | 0
2015 | 33897 | 33897 | 0 | 0
2016 | 33515 | 33515 | 0 | 0
2017 | 35465 | 35465 | 0 | 0
2018 | 35477 | 35465 | 12 | 0
2019 | 35477 | 35465 | 12 | 0
2020 | 35477 | 35465 | 12 | 0
2021 | 36219.9 | 35465 | 12 | 742.9
2022 | 36962.8 | 35465 | 12 | 1485.8

## Gas-Other Chart
[5 empty] | INR | Project Name | County | Projected COD | IA Signed | Fuel | Technology | Capacity (MW) | Year | Financial Security
[5 empty] | 13INR0049 | FEGC | Harris | 2018-11-15 | 2015-09-23 | Gas | GT | 129 | 2018 | Yes
[5 empty] | 17INR0045 | VictPort | Calhoun | 2018-11-23 | 2018-03-06 | Gas | GT | 100 | 2018 | Yes
[5 empty] | 17INR0022 | MIRAGE | Harris | 2019-01-04 | 2016-08-31 | Gas | GT | 11 | 2019 | Yes
[5 empty] | 16INR0076 | Hudson (Ineos/Brazoria) | Brazoria | 2019-01-31 | 2017-12-05 | Gas | GT | 96 | 2019 | Yes
[5 empty] | 18INR0035 | CityVict | Refugio | 2019-04-01 | 2018-03-06 | Gas | GT | 100 | 2019 | Yes
[5 empty] | 16INR0003 | LEVEE (Freeport LNG) | Brazoria | 2019-08-01 | 2014-01-13 | Gas | GT | 11 | 2019 | Yes
[5 empty] | 16INR0044 | Halyard Wharton | Wharton | 2020-06-01 | 2016-01-26 | Gas | GT | 397.8 | 2020 | No
[5 empty] | 16INR0045 | Halyard Henderson | Henderson | 2021-05-01 | 2016-04-01 | Gas | GT | 484 | 2021 | No
Year | Cumulative Installed, No FS, and FS Posted | Cumulative MW Installed | IA Signed-Financial Security Posted | IA Signed-No Financial Security
1999 | 33703 | 33703 | 0 | 0
2000 | 33703 | 33703 | 0 | 0
2001 | 34170 | 34170 | 0 | 0
2002 | 34170 | 34170 | 0 | 0
2003 | 34118 | 34118 | 0 | 0
2004 | 32616 | 32616 | 0 | 0
2005 | 31217 | 31217 | 0 | 0
2006 | 30774 | 30774 | 0 | 0
2007 | 29048 | 29048 | 0 | 0
2008 | 28681 | 28681 | 0 | 0
2009 | 23651 | 23651 | 0 | 0
2010 | 20937 | 20937 | 0 | 0
2011 | 20575 | 20575 | 0 | 0
2012 | 20551 | 20551 | 0 | 0
2013 | 20026 | 20026 | 0 | 0
2014 | 19917 | 19917 | 0 | 0
2015 | 18538 | 18538 | 0 | 0
2016 | 19564 | 19564 | 0 | 0
2017 | 18818 | 18818 | 0 | 0
2018 | 19662 | 19433 | 229 | 0
2019 | 19880 | 19433 | 447 | 0
2020 | 20277.8 | 19433 | 447 | 397.8
2021 | 20761.8 | 19433 | 447 | 881.8