## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
January 17, 2019

## Slide 2
Project Portfolio Update p. 3-10
  Recent / Upcoming Project Implementations
  2018 Release Targets
  2019 Release Targets
  Planned Project Starts
  2018 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2018 December Release – 12/11/2018 – 12/13/2018 Complete
  NPRR843(b) – Short-Term System Adequacy & AS Offer Disclosure Reports Additions
    60 day reports
  PGRR063 – Transmission Interconnection Study
1/22/2019 In Flight
  PGRR057(b) – Responsibilities for Performing GMD Vulnerability Assessments
    Resource Entities and TSPs provide their GMD event-caused outages to ERCOT by 3/31/2019
2019 February Release – 2/5/2019 – 2/7/2019 In Flight
  NPRR833 – Modify PTP Obligation Bid Clearing Change
  NPRR842 – Study Area Load Information
  NPRR858 – Provide Complete Current Operating Plan (COP) Data
  NPRR878 – ERS Obligation Report for TDSPs
  SCR794 – Update SCED Limit Calculation
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/6 – 2/8 | April 4/5 – 4/9 | May 5/29 – 5/31 | August 8/7 – 8/9 | October 10/23 – 10/25 | December 12/11 – 12/13
NPRR659 NPRR683 NPRR743 NPRR760 NPRR800 NPRR810 PGRR042 NPRR846 | NPRR562(b) SCR792 NPRR776 NOGRR167 | NPRR768 NPRR815 OBDRR002 PGRR057(a) | NPRR819 NPRR844 NPRR854 SCR791 NPRR702 (partial implementation) NPRR825(a) | NPRR843(a) NPRR864 NPRR875 SCR795 RRGRR015 | NPRR843(b) PGRR063 NPRR831(b) SCR777
7/2
9/1
CMM Release 1a
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
1/1 & 2/1
NPRR825(a) – NoticeBuilder changes
NPRR825(b) –
NPRR562(b) – Reporting/posting system changes
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR843(a) – CDR, 48 hour, & 7 day reports
NPRR843(b) – 60 day reports
PGRR057(a) – Preliminary posting
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017 | 2018
NPRR664 | None | SCR781 P | NPRR702 P, NPRR829 | RRGRR016, NOGRR154, NPRR825(b), NPRR867, NPRR884, NPRR895, PGRR066
1/1
2/1
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
11/1
ü
11/19
6/1
ü
ü
ü
ü
ü
ü
10/1
ü
ü
ü
ü
ü
ü

## Slide 5: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR833(a/b) NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) | NPRR749 NPRR817 NPRR833(c) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 NOGRR174 PGRR061 RRGRR017 VCMRR022 | NPRR809(b) NPRR873 NPRR899 NPRR901 SCR793 SCR796 NPRR519 NPRR620 NPRR741 NPRR755 NPRR821 | NPRR887 RRGRR016 RRGRR018 RRGRR019 SCR797 |  | NPRR841 NPRR856 NPRR877 Ph2
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
PGRR057(b) – List of GMD event contingencies
E
E
E
E
E
E
E
E
E
P
E
P
E
E
E
E
E
NS
NS
I
NS
NS
NS
NS
NS
7/1
E
6/15
E
E
E
E
CMM Release 1b
5/1
NS
NS
NS
NS
NS
1/22
4/15

## Slide 6: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
SCR793 – SSR Related Telemetry for Transmission Service Provider (TSP) Operators | Jan 2019 | 2019-R3 | $40k-$50k | Cross Texas Transmission
SCR796 – Change Validation Rules to Preclude Certain Transactions at Resource Nodes within PUNs | Jan 2019 | 2019-R3 | $35k-$55k | ERCOT
NPRR873 – Posting ERCOT-Wide Intra-Hour Wind Power and Load Forecast on MIS Public | Jan 2019 | 2019-R3 | $60k-$80k | ERCOT
RRGRR016 – Additional Guidance for Solar Data | Jan 2019 | 2019-R4 | <$10k | RDWG
RRGRR018 – Related to NPRR889, RTF-1 Replace Non-Modeled Generator with Settlement Only Generator | Jan 2019 | 2019-R4 | <$10k | ERCOT
RRGRR019 – Related to NPRR901, Switchable Generation Resource Status Code | Jan 2019 | 2019-R4 | $25k-$35k | ERCOT
NPRR887 – Monthly Posting of Default Uplift Exposure Information | Feb 2019 | 2019-R4 | $50k-$75k | Citigroup
NPRR899 – Digital Certificate and User Security Admin. Clarifications and Opt Out Procedure | Feb 2019 | 2019-R3 | $15k-$25k | ERCOT
SCR797 – Provide Current Operating Plans (COPs) to TSPs | Mar 2019 | 2019-R4 | $30k-$50k | ERCOT
NPRR841 – Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Jun 2019 | 2019-R6 | $60k-$80k | ERCOT
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Jun 2019 | 2019-R6 | $50k-$75k | ERCOT
NPRR877 Phase 2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement | Jul 2019 | 2019-R6 | $25k-$45k | Oncor
Project Initiations – Next 3 Months

## Slide 7: 2018 Project Spending
2018 PPL Budget = $20.0M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 8: Revision Request Funding Placeholder Status
In 2018 and 2019, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2018 | 2019
YTD Actuals | $2.49M | -
Approved – In-Flight / Complete | $2.49M | $1.48M
Approved – Not Started | - | $0.27M
Remaining Funding | $1.51M | $2.25M
Total Allocation | $4.00M | $4.00M
As of 12/31/2018

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR910 | Clarify Treatment of RUC Resource that has a Day-Ahead Market Three-Part Supply Award | 2019 | 2506 | Rank immediately after NPRR901 If approved, the goal is to deliver 910 with 901 in 2019-R3 (May)
NPRR911 | Improved Calculation of Real-Time LMPs at Logical Resource Nodes for On-Line Combined Cycle Generation Resources | 2019 | 2660 | Add to end of 2019 list and work into the plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2660
Next available Rank in Regulatory = 220