## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
February 14, 2019

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
  2019 Release Targets
  Planned Project Starts
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2019 February Release – 2/5/2019 – 2/7/2019 Complete
  NPRR833(a/b) – Modify PTP Obligation Bid Clearing Change Targeting off-cycle before R2
  NPRR842 – Study Area Load Information
  NPRR858 – Provide Complete Current Operating Plan (COP) Data
  NPRR878 – ERS Obligation Report for TDSPs
  SCR794 – Update SCED Limit Calculation
2019 April Release – 4/2/2019 – 4/4/2019 In Flight
  NPRR749 – Option Cost for Outstanding CRRs
  NPRR817 – Create a Panhandle Hub
  NPRR833(c) – Modify PTP Obligation Bid Clearing Change
    CRR system changes
  NPRR845 – RMR Process and Agreement Revisions
  NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap
  NPRR865 – Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties
  NPRR866 – Mapping Registered DG and Load Resources to Transmission Loads in the Network Model
  NPRR880 – Publish RTM Shift Factors for Private Use Network Settlement Points
  NOGRR174 – AVR and PSS Testing Requirements
  PGRR061 – Related to NPRR866, Map Reg. DG and Load Resources to Transmission Loads in Network Model
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR833(a/b) NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) PGRR062 | NPRR749 NPRR817 NPRR833(c) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 NOGRR174 PGRR061 RRGRR017 VCMRR022 | NPRR809(b) NPRR873 NPRR889 NPRR899 NPRR901 SCR793 SCR796 NOGRR174 NPRR519 NPRR620 NPRR741 NPRR755 NPRR821 | NPRR887 RRGRR016 RRGRR018 RRGRR019 SCR793 SCR797 | NPRR887 | NPRR841 NPRR856 NPRR877 Ph2
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
PGRR057(b) – List of GMD event contingencies
E
E
E
E
E
E
E
E
E
E
E
E
I
NS
P
I
NS
NS
NS
7/1
E
6/15
E
E
E
E
E
CMM Release 1b
5/1
E
E
E
E
NS
1/22
4/15
ü
ü
ü
ü
ü
TBD Items | 2014 | 2016 | 2017 | 2018
 | NPRR664 | SCR781 P | NPRR702 P, NPRR829 | NOGRR154, NPRR825(b), NPRR867, NPRR884, NPRR895, PGRR066
NS
3/1

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR899 – Digital Certificate and User Security Admin. Clarifications and Opt Out Procedure | Feb 2019 | 2019-R3 | $15k-$25k | ERCOT
SCR797 – Provide Current Operating Plans (COPs) to TSPs | Mar 2019 | 2019-R4 | $30k-$50k | ERCOT
NPRR887 – Monthly Posting of Default Uplift Exposure Information | Apr 2019 | 2019-R5 | $50k-$75k | Citigroup
NPRR841 – Real-Time Adjustments to Day-Ahead Make Whole Payments due to Ancillary Services Infeasibility Charges | Jun 2019 | 2019-R6 | $60k-$80k | ERCOT
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Jun 2019 | 2019-R6 | $50k-$75k | ERCOT
NPRR877 Phase 2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement | Jul 2019 | 2019-R6 | $25k-$45k | Oncor
Project Initiations – Next 3 Months
Moved from February start

## Slide 6: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In 2020, ERCOT forecasts $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | TBD | -
Approved – In-Flight / Complete | $1.48M | $0.00M
Approved – Not Started | $0.27M | $0.00M
Remaining Funding | $2.25M | $4.00M
Total Allocation | $4.00M | $4.00M
As of 1/31/2019

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR914 | Addition of Controllable Load Resources to 60-Day Reports | 2019 | 2670 | Add to end of 2019 list and work into the plan without disrupting in-flight projects
SCR798 | PTP Obligation Bid ID Limit | 2019 | 2585 | This Rank will place SCR798 ahead of other “Not Started” projects impacting MMS
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2670
Next available Rank in Regulatory = 220