## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
March 14, 2019

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2019 Release Targets
  Planned Project Starts
  2019 Project Spending Forecast
  Revision Request Funding Placeholder Status
  2018 Impact Analysis Statistics
    Cost Estimate Accuracy
    Duration Estimate Accuracy
    Legend
    Report Exceptions
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2019 February Release – 2/5/2019 – 2/7/2019 Complete
  NPRR842 – Study Area Load Information
  NPRR858 – Provide Complete Current Operating Plan (COP) Data
  NPRR878 – ERS Obligation Report for TDSPs
  SCR794 – Update SCED Limit Calculation
Off-Cycle Release – 3/1/2019 Complete
  OBDRR011 – ORDC OBD Revisions for PUCT Project 48551
2019 April Release – 4/2/2019 – 4/4/2019 In Flight
  NPRR817 – Create a Panhandle Hub
  NPRR845 – RMR Process and Agreement Revisions
  NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap
  NPRR865 – Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties
  NPRR866 – Mapping Registered DG and Load Resources to Transmission Loads in the Network Model
  NPRR880 – Publish RTM Shift Factors for Private Use Network Settlement Points
  VCMRR021 – Related to NPRR847, Exceptional Fuel Cost Included in the Mitigated Offer Cap
  RRGRR017 – Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) PGRR062 OBDRR011 NPRR833(a/b) RMGRR156 | NPRR749 NPRR817 NPRR833(c) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 PGRR061 VCMRR021 RRGRR017 RRGRR017 VCMRR022 | NPRR809(b) NPRR873 NPRR889 NPRR899 NPRR901 NPRR910 SCR796 NOGRR174 OBDRR010 NPRR519 NPRR620 NPRR741 NPRR755 NPRR821 | NPRR873 NPRR899 RRGRR016 RRGRR018 RRGRR019 SCR793 SCR796 SCR797 OBDRR003 | NPRR887 PGRR061 | NPRR841 NPRR856 NPRR877 Ph2
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
PGRR057(b) – List of GMD event contingencies
E
E
E
E
E
E
E
E
E
E
E
E
NS
NS
NS
7/1
E
6/15
E
E
E
E
E
E
CMM Release 1b
5/1
P
NS
E
E
E
E
P
NS
P
1/22
4/15
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2014 | 2016 | 2017 | 2018
 | NPRR664 | SCR781 P | NPRR702 P, NPRR829 | NOGRR154, NPRR825(b), NPRR867, NPRR884, NPRR895, PGRR066, NPRR856, NPRR841, NPRR887
NS
E
3/1
3/5
Additional Go-Live Targets
NPRR833(a/b) R2 (4/2 – 4/4)
NPRR833(c) Late April / Early May
NPRR749 Late April
PGRR062 March 26

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR899 – Digital Certificate and User Security Admin. Clarifications and Opt Out Procedure | Mar 2019 | 2019-R4 | $15k-$25k | ERCOT
SCR797 – Provide Current Operating Plans (COPs) to TSPs | Mar 2019 | 2019-R4 | $30k-$50k | ERCOT
NPRR887 – Monthly Posting of Default Uplift Exposure Information | May 2019 | 2019-R5 | $50k-$75k | Citigroup
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Jun 2019 | 2019-R6 | $50k-$75k | ERCOT
NPRR877 Phase 2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement | Jul 2019 | 2019-R6 | $25k-$45k | Oncor
Project Initiations – Next 3 Months
Moved from February start
Moved from April start
Additional Q2 project starts will be scheduled at the end of March

## Slide 6: 2019 Project Spending
2019 PPL Budget = $20.4M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In 2020, ERCOT forecasts $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | $0.61M | -
Approved – In-Flight / Complete | $1.97M | $0.00M
Approved – Not Started | $0.38M | $0.21M
Remaining Funding | $1.65M | $3.79M
Total Allocation | $4.00M | $4.00M
As of 1/31/2019

## Slide 8: Variance from IA Cost Range – Revision Request Projects
10
Exceeds IA Range
15 Projects
Below IA Range
18 Projects
Within IA Range
8 Projects
If actual spend falls within the IA range the variance is 0
Actual $ Variance from IA Range
2016
11 Projects
18 Revision Requests
2017
17 Projects
22 Revision Requests
2018
13 Projects
14 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
2
3
4
5
6
7
8
9
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
35
36
37
38
39
31
32
33
30
34
40
41
Chart: 
| -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | -$18,649 | -$109,501 | -$24,103 | -$2,635 | -$6,979 | $0 | $0 | $27,046 | $0 | $19,236 | $23,113 | -$3,385 | $0 | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | No | Yes | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | $6,351 | $10,499 | $15,897 | $17,365 | $18,021 | $19,780 | $29,623 | $67,046 | $83,360 | $109,236 | $123,113 | $146,615 | $189,937 | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 1 - Less than $50k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $15,000 | $40,000 | $20,000 | $10,000 | $10,000 | $10,000 | $25,000 | $10,000 | $20,000 | $20,000 | $30,000 | $50,000 | $60,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $40,000 | $160,000 | $60,000 | $30,000 | $35,000 | $25,000 | $50,000 | $40,000 | $90,000 | $90,000 | $100,000 | $200,000 | $190,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $32,500 | $140,000 | $50,000 | $25,000 | $30,000 | $20,000 | $37,500 | $35,000 | $80,000 | $80,000 | $85,000 | $175,000 | $160,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | $25,000 | $120,000 | $40,000 | $20,000 | $25,000 | $15,000 | $25,000 | $30,000 | $70,000 | $70,000 | $70,000 | $150,000 | $130,000 | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | Market | ERCOT | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | NPRR810 | NPRR830 | SCR792 | NPRR854 | SCR791 | NPRR844 | NPRR819 | SCR795 | NPRR815 | NPRR843 | NPRR776 | NPRR864 | OBDRR002, NPRR768 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | Yes | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies | Revision of 4-Coincident Peak Methodology | Enhance Communications of BAAL Exceedances | NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage | Correction of 60-day SCED GRD Disclosure Report | Clarification to Outage Report | Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups | Addition of Intra-Hour Wind Forecast to GTBD Calculation | Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service | Short-Term System Adequacy and AS Offer Disclosure Reports Additions | Voltage Set Point Communication | RUC Modifications to Consider Market-Based Solutions | Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 233-31 | 270-01 | 273-01 | 276-02 | 281-01 | 276-01 | 283-01 | 289-01 | 278-01 | 285-01 | 256-01 | 284-01 | 277-01 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
Actual Variance from IA Estimate Range | -11823.53 | -3391.34 | 49954.86 | -12318 | 0 | 0 | -70696.8 | 43734.23 | 72990.8 | 102533.38 | 104867.87 | -35000 | -36213 | -21105 | -11000.8 | 1119.97 | -5333 | 6568.52 | -5911.38 | -3242 | 11991.1 | 0 | 0 | -61130.26 | 59424.36 | 24677.15 | 0 | 108135 | -18649 | -109500.9 | -24102.73 | -2634.93 | -6979.45 | 0 | 0 | 27046.01 | 0 | 19236.05 | 23113.12 | -3385.08 | 0




## Slide 9: Variance from IA Duration Range – Revision Request Projects
34
12
Exceeds IA Range
18 Projects
Below IA Range
1 Projects
Within IA Range
22 Projects
2016
11 Projects
18 Revision Requests
2017
17 Projects
22 Revision Requests
2018
13 Projects
14 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
Number of Months from IA Range
1
2
3
4
5
6
8
9
10
11
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
35
36
37
38
7
39
41
40
Chart: 
| 1 | 2 | 5 | 6 | 8 | 10 | 11 | 12 | 15 | 17 | 23 | 24 | 25 | 27 | 28 | 29 | 30 | 32 | 33 | 34 | 35 | 36 | 39 | 40 | 48 | 49 | 51 | 60 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 78 | 82 | 83 | 84 | 85 | 87 | -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | -$35,000 | -$36,213 | -$21,105 | -$11,001 | $1,120 | -$5,333 | $6,569 | -$5,911 | -$3,242 | $11,991 | $0 | $0 | -$61,130 | $59,424 | $24,677 | $0 | $108,135 | -$18,649 | -$109,501 | -$24,103 | -$2,635 | -$6,979 | $0 | $0 | $27,046 | $0 | $19,236 | $23,113 | -$3,385 | $0 | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | No | Yes | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | $- | $3,787 | $38,895 | $38,999 | $41,120 | $44,667 | $46,569 | $49,089 | $56,758 | $56,991 | $81,915 | $111,390 | $113,870 | $179,424 | $184,677 | $213,921 | $508,135 | $6,351 | $10,499 | $15,897 | $17,365 | $18,021 | $19,780 | $29,623 | $67,046 | $83,360 | $109,236 | $123,113 | $146,615 | $189,937 | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 3 - $100k to $250k | 4 - $250k to $500k | 1 - Less than $50k | 3 - $100k to $250k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 3 - $100k to $250k | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $5,000 | $10,000 | $20,000 | $25,000 | $20,000 | $25,000 | $10,000 | $20,000 | $30,000 | $10,000 | $30,000 | $50,000 | $60,000 | $20,000 | $15,000 | $50,000 | $100,000 | $15,000 | $40,000 | $20,000 | $10,000 | $10,000 | $10,000 | $25,000 | $10,000 | $20,000 | $20,000 | $30,000 | $50,000 | $60,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $40,000 | $50,000 | $80,000 | $75,000 | $40,000 | $75,000 | $40,000 | $75,000 | $90,000 | $45,000 | $85,000 | $150,000 | $235,000 | $120,000 | $160,000 | $250,000 | $400,000 | $40,000 | $160,000 | $60,000 | $30,000 | $35,000 | $25,000 | $50,000 | $40,000 | $90,000 | $90,000 | $100,000 | $200,000 | $190,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $37,500 | $45,000 | $70,000 | $62,500 | $30,000 | $62,500 | $35,000 | $65,000 | $75,000 | $40,000 | $70,000 | $125,000 | $205,000 | $110,000 | $152,500 | $225,000 | $350,000 | $32,500 | $140,000 | $50,000 | $25,000 | $30,000 | $20,000 | $37,500 | $35,000 | $80,000 | $80,000 | $85,000 | $175,000 | $160,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | $35,000 | $40,000 | $60,000 | $50,000 | $20,000 | $50,000 | $30,000 | $55,000 | $60,000 | $35,000 | $55,000 | $100,000 | $175,000 | $100,000 | $145,000 | $200,000 | $300,000 | $25,000 | $120,000 | $40,000 | $20,000 | $25,000 | $15,000 | $25,000 | $30,000 | $70,000 | $70,000 | $70,000 | $150,000 | $130,000 | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | ERCOT | Market | Market | ERCOT | Market | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Mixed | Market | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | ERCOT | Market | Market | Market | ERCOT | ERCOT | Market | ERCOT | ERCOT | Market | ERCOT | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | NPRR785 | NPRR808 | NPRR789, NPRR797 | NPRR649 | SCR790 | NPRR778 | RMGRR134 | NPRR764 | NPRR782 | NPRR746 | NPRR573, NPRR801 | NPRR831 | RRGRR003, RRGRR006, RRGRR007, RRGRR009 | RMGRR140 | NPRR272 | NPRR744 | NPRR758 | NPRR810 | NPRR830 | SCR792 | NPRR854 | SCR791 | NPRR844 | NPRR819 | SCR795 | NPRR815 | NPRR843 | NPRR776 | NPRR864 | OBDRR002, NPRR768 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes | No | No | No | No | No | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | Yes | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts | Three Year CRR Auction | NPRR797 & NPRR789 Load Forecast Enhancements | Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides | Wind Resource Power Production and Forecast Transparency | Modifications to Date Change and Cancellation Evaluation Window | Allow AMS Data Submittal Process for TDSP-Read Non-Modeled Generators | QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80) | Settlement of Infeasible Ancillary Services Due to Transmission Constraints | Adjustments Due to Negative Load | Implementation of NPRR573 & NPRR801 | Inclusion of Private Use Networks in Load Zone Price Calculations | 2016 RARF Enhancements | Mass Transition/Acquisition Enhancements (MTAQ) | Definition and Participation of Quick Start Generation Resources | RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement | Improved Transparency for Outages Potentially Having a High Economic Impact | Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies | Revision of 4-Coincident Peak Methodology | Enhance Communications of BAAL Exceedances | NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage | Correction of 60-day SCED GRD Disclosure Report | Clarification to Outage Report | Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups | Addition of Intra-Hour Wind Forecast to GTBD Calculation | Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service | Short-Term System Adequacy and AS Offer Disclosure Reports Additions | Voltage Set Point Communication | RUC Modifications to Consider Market-Based Solutions | Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 231-01 | 252-01 | 236-01 | 213-01 | 207-01 | 248-01 | 232-01 | 201-01 | 237-01 | 226-01 | 159-01 | 251-01 | 200-01 | 188-01 | 194-01 | 225-01 | 215-01 | 233-31 | 270-01 | 273-01 | 276-02 | 281-01 | 276-01 | 283-01 | 289-01 | 278-01 | 285-01 | 256-01 | 284-01 | 277-01 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018 | 2018
Actual Variance from IA Duration Range | 0 | 0 | 0.33333 | 2.7667 | 0 | 0 | 0 | 0 | 3.6333 | 4.6 | 0 | 0 | 1.4333 | 0 | 0 | 2.4333 | 0 | 0 | 0.8 | 3.3667 | 0.46667 | 0 | 0 | 0.2 | 4.8 | 5 | 0 | 0 | 1.1667 | -0.066667 | 0 | 0.76667 | 0.63333 | 0.066667 | 0 | 0 | 0 | 1.5 | 0.9 | 0 | 0

## Slide 10: Revision Request Project Legend
SCR788 Addition of Integral ACE Feedback to GTBD Calculation, (M)
NPRR754, Revise Load Distribution Factors Report Posting Frequency, (E)
NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge, (E)
SCR786, Retail Market Test Environment, (M)
NOGRR147, SCR787, NOGRR147 and SCR787 NDCRC Enhancement, (M)
NPRR662 Proxy Energy Offer Curves, (M)
NPRR770, NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor, (V)
NPRR617 and NPRR700 Implementation, (M)
NPRR515 Day-Ahead Market Self-Commitment of Generation Resources, (E)
NPRR588, NPRR615, NPRRs 588 and 615, (M)
NPRR219, SCR783, NOGRR050, 2015 Outage Scheduler Enhancements, (V)
NPRR785, Synchronizing WGR and PVGR COPs with the Short Term Wind and PhotoVoltaic Forecasts, (E)
NPRR808, Three Year CRR Auction, (M)
NPRR797 & NPRR789 Load Forecast Enhancements, (M)
NPRR649, Addressing Issues Surrounding High Dispatch Limit (HDL) Overrides, (E)
SCR790, Wind Resource Power Production and Forecast Transparency, (M)
NPRR778, Modifications to Date Change and Cancellation Evaluation Window, (M)
RMGRR134, Allow AMS Data Submittal Process for TDSP – Read Non-Modeled Generators, (E)
NPRR764, QSE Capacity Short Calculations Based on an 80% Probability of Exceedance (P80), (E)
NPRR782, Settlement of Infeasible Ancillary Services Due to Transmission Constraints, (E)
NPRR746, Adjustments Due to Negative Load, (E)
NPRR573, NPRR801, Implementation of NPRR573 & NPRR801, (E)
NPRR821, Inclusion of Private Use Networks in Load Zone Price Calculations, (E)
RRGRR003, RRGRR006, RRGRR007, RRGRR009, 2016 RARF Enhancements, (V)
RMGRR140, Mass Transition/Acquisition Enhancements (MTAQ), (M)
NPRR272, Definition and Participation of Quick Start Generation Resources, (E)
NPRR744, RUC Trigger for the Reliability Deployment Price Adder and Alignment with RUC Settlement, (E)
NPRR758, Improved Transparency for Outages Potentially having a High Economic Impact, (E)
NPRR810, Applicability of RMR Incentive Factor on Reservation and Transportation Costs Associated with Firm Fuel Supplies, (E)
NPRR830, Revision of 4-Coincident Peak Methodology, (E)
SCR792, Enhance Communications of BAAL Exceedances, (E)
NPRR854, NOIE TDSP Submittal of Meters with Bidirectional Flow Caused by Generation Interconnected at Distribution Voltage, (M)
SCR791, Correction of 60-day SCED GRD Disclosure Report, (M)
NPRR844, Clarification to Outage Report, (M)
NPRR819, Modification of Non-Price Error Resettlement Thresholds and Resettlement Clean-Ups, (E)
SCR795, Addition of Intra-Hour Wind Forecast to GTBD Calculation, (E)
NPRR815, Revise the Limitation of Load Resources Providing Responsive Reserve (RRS) Service, (M)
NPRR843, Short-Term System Adequacy and AS Offer Disclosure Reports Additions, (E)
NPRR776, Voltage Set Point Communication, (E)
NPRR864, RUC Modifications to Consider Market-Based Solutions, (M)
OBDRR002, NPRR768, Revisions to Real-Time On-Line Reliability Deployment Price Adder Categories, (E)
(E) ERCOT Sponsored
(M) Market Sponsored
(V) Various

## Slide 11: Statistics Report Exceptions
Type | Revision Requests | Reason for Exclusion from Report
CMM Phase 1a | NPRR863, NPRR743, NPRR760, NPRR800 | Difficult to apply metrics – multiple RRs in a multi-phase project
O&M Revision Requests | NPRR659, NPRR846, NPRR562(b), NPRR875, PGRR063, NOGRR167, PGRR042 | O&M Revision Requests do not have IA estimates
Project Not Complete | PGRR057(a), RRGRR015 | Early releases of projects that are still in flight
Partial Scope Delivered | NPRR825(a), NPRR702 | Partial scope delivered – Remaining scope to be delivered in future projects
Combined with System Upgrade | SCR777, NPRR831(b) | Small additions to CRR Framework Upgrade project
The following Revision Requests aren’t included in the IA Statistics Report

## Slide 12: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR920 | Change to Ramp Rate Calculation in Resource Limit Calculator | 2019 | 2690 | Add to end of 2019 list and work into the plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2690
Next available Rank in Regulatory = 220