## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2019-02-21
Agenda Item: | Decision / Resolution | Action Items :
January 2019 Meeting Notes | Minor Changes were made to the Janaury notes. | The Texas SET Chair will have the notes posted to the January meeting page.
Flight Update | ERCOT presented the flight update.
FlighTrak Demo--ERCOT | ERCOT presented information related to use of the new FlighTrak tool and provided answers to questions questions from the group. It was noted that the FlighTrak application will be available in the Retail Market Test Environment (RMTE) on Monday February 25 to allow Market Participants access.
MOU02 Script update—Review and Approve | Texas SET agreed to the changes made for the script. | ERCOT will post the updated scripts to the website.
2019 Flight Schedule Changes | ERCOT provided some date changes needed in the June and October test flight schedule, "IN-FLIGHT SIGNUP DEADLINE" section, to allow specific steps more time where needed. Texas SET reached consensus in favor of those changes. | ERCOT will send the updated version to Texas SET leadership in order to have this posted for a vote at the next Retail Market Subcommittee (RMS) meeting.
Banking Scripts--TDSP Feedback | Texas SET reviewed the banking scripts to determine the changes that will be needed in order to allow existing CRs to complete a bank change or change to an existing Market Interface Service Provider (MISP) outside of a Market Test Flight. The group determined that changes will be made to the Texas Market Test Plan (TMTP) as well as the scripts. | NRG agreed to make changes to the TMTP and consult with the ERCOT Flight Administrator to determine how to make changes to the scripts.
Future Flight Schedules Review | Texas SET agreed to review future Flight Schedules (2020 and later) to determine what changes could be made to reduce the timelines at a subsequent Texas SET meeting.
RMS Update
All Working Group and Task Force Leadership Approved | The Texas SET Chair reviewed the RMS discussions and results.
NPRR908, Revisions to Mass Transition Processes (Texas SET WG)—RMS voted to endorse as submitted | The Texas SET Chair reviewed the RMS discussions and results.
RMGRR159, Related to NPRR908, Revisions to Mass Transition Process (Texas SET WG)—RMS voted to approve with the Texas SET comments and RMS desktop edits. | The Texas SET Chair reviewed the RMS discussions and results.
RMGRR158, Revisions to Emergency Operating Procedures for Extended Unplanned System Outages—RMS voted to approve. | The Texas SET Chair reviewed the RMS discussions and results.
Draft NPRR, Allow Use of 814_28, Complete Unexecutable Transaction for Drop to POLR Switches During a Mass Transition Event.—Desktop edits were made; RMS tabled for one month to allow ERCOT time to provide feedback at Texas SET. | The Texas SET Chair reviewed the RMS discussions and results.
Mass Transition Testing Workshop II will be on March 5, 2019 | The Texas SET Chair reviewed the RMS discussions and results.
Summer Preparedness Workshop March 4, 2019 | The Texas SET Chair reviewed the RMS discussions and results.
RMS Assignments
SAC04--Spanish Translation | Texas SET Reviewed the issues related to providing a Spanish Translation version of the SAC04 spreadsheet and discussed how this might be used by CRs. | RMS leadership will revisit the request with PUCT Staff to gain feedback for the next meeting.
Plans for Texas SET Release Update | There is no update to the dates for a new release.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Discussion Items
Draft NPRR Section 15, Customer Registration--15.1.3.1 Mass Transition Process changes to allow TDSPs to send 814_28s for Drop to POLR transactions.--ERCOT Feedback | ERCOT will provide the feedback at a future Texas SET meeting. | The Texas SET Chair will request that RMS leave the NPRR tabled.
RMG Safety NET Timelines PUCT Staff Provides Feedback to Continue Submission of Language Changes--Review Changes from 09/2017 | Texas SET began review of the changes; then determined a smaller group will review the changes in order to provide an updated version for the group to review at the next Texas SET meeting. | AEP, CNP and ERCOT Market Rules volunteered to complete the review.
Construction Hold—ONCOR draft Change Control review | ONCOR stated that this review can be completed at the next TX SET meeting.
Proposed Texas SET Release Changes.— Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix | This discussion item will be reviewed at the next Texas SET meeting.
Parking Lot
REP Certification Matrix—Long-term solution | On Hold
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR) | On Hold waiting for feedback from ERCOT
Next Meeting--ERCOT MET Center 102 | 2019-04-03
Attendees F-T-F (*) denotes attendance both days
Diana Rehfeldt TNMP | David Michelsen ERCOT | David Hunt ONCOR
Becky Taylor CNP | Paul Yockey ERCOT | Kathy Scott CNP
Seri Wiegand TXUE | Kyle Patrick NRG | Tomas Fernandez NRG
Kaci Jacobs TXUE | Jim Lee AEP
Catherine Meiners ERCOT | Eric Blakey Just Energy
Phil Bracy ERCOT | Sam Pak ONCOR
Attendees Webex (*) denotes attendance both days
Kim Wall Hansen Technologies | Mica Eastin Big Data Energy | Mark Ruane ERCOT
Marianne Host ERCOT | Carolyn Reed CNP | Tracie Gaetano Accent Energy
Christy Dvorak Infinite Energy | Crystal Luna Stream Energy | Connie Hermes NEC
Darice Taipalus TNMP | Deborah McKeever ONCOR | Kristen Abbott PUCT
Deb Belin Marketwise | Frank Nunes ECInfoSystems | Rakhee Gupta TNMP
Brian Burress ONCOR | Stephanie McCutcheon TNMP | Teresa Rodriquez Stream Energy
Kathryn Thurman ERCOT | Jacquelene Stevenson ECInfoSystems | Kevin Bunch
Malcolm Ainspan | Roy McAllistor | Adebayo Fapourda