## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
April 11, 2019

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2019 Release Targets
  Planned Project Starts
  Aging Items Report
  2019 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
Off-Cycle Release – 3/26/2019 Complete
  PGRR062 – Updates to Generation Interconnection or Change Request (GINR) Process
2019 April Release – 4/2/2019 – 4/4/2019 Complete
  NPRR809(b) – GTC or GTL for New Generation Interconnection
  NPRR817 – Create a Panhandle Hub
  NPRR833 (a/b) – Modify PTP Obligation Bid Clearing Change (DAM and SCED components)
  NPRR845 – RMR Process and Agreement Revisions
  NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap
  NPRR865 – Publish RTM Shift Factors for Hubs, Load Zones, and DC Ties
  NPRR866 – Mapping Registered DG and Load Resources to Transmission Loads in the Network Model
  NPRR880 – Publish RTM Shift Factors for Private Use Network Settlement Points
  VCMRR021 – Related to NPRR847, Exceptional Fuel Cost Included in the Mitigated Offer Cap
  RRGRR017 – Related to NPRR866, Mapping Registered Distributed Generation and Load Resources to Transmission Loads in the Network Operations Model
Off-Cycle Release – 5/1/2019 In Flight
  VCMRR022 – Determination of Fuel Adder Price for Coal and Lignite Resources
Off-Cycle Release – 5/6/2019 In Flight
  NPRR833 (c) – Modify PTP Obligation Bid Clearing Change (CRR component)
  NPRR749 – Option Cost for Outstanding CRRs
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) OBDRR011 RMGRR156 PGRR062 | NPRR809(b) NPRR817 NPRR833(a/b) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 VCMRR021 RRGRR017 VCMRR022 NPRR833(c) NPRR749 | NPRR809(b) NPRR889 NPRR901 NPRR910 NOGRR174 OBDRR010 RMGRR155 RRGRR018/019 NPRR519 NPRR620 NPRR741 NPRR755 NPRR821 | NPRR873 NPRR899 RRGRR016 RRGRR018 RRGRR019 SCR793 SCR796 SCR797 OBDRR003 | NPRR887 PGRR061 | NPRR841 NPRR856 NPRR877 Ph2 NPRR895 NPRR911 NPRR920 OBDRR007 SCR781(a)
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
PGRR057(b) – List of GMD event contingencies
SCR781(a) – View / Edit capability
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
E
E
E
E
E
E
NS
NS
NS
NS
NS
E
7/1
E
6/15
E
E
E
E
E
E
E
E
CMM Release 1b
5/1
P
E
E
E
P
E
P
1/22
3/26
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2014 | 2016 | 2017 | 2018
 | NPRR664 | SCR781 P | NPRR702 P, NPRR829 | NOGRR154, NPRR825(b), NPRR867, NPRR884, NPRR895, PGRR066, NPRR856, NPRR841, NPRR887
NS
E
3/1
3/5
5/6
Q4
Date TBD
ü

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
SCR798 – PTP Obligation Bid ID Limit | Apr 2019 | 2019-R4 or 2019-R5 | $10k-$20k | ERCOT
NPRR925 – Increasing Minimum Quantity for PTP Obligation Bids |  |  | <$10k O&M | ERCOT
NPRR863 – Creation of ERCOT Contingency Reserve Service and Revisions to Responsive Reserve (FFR portion) | May 2019 | TBD | TBD | STEC
NPRR887 – Monthly Posting of Default Uplift Exposure Information | May 2019 | 2019-R5 | $50k-$75k | Citigroup
NPRR895 – Inclusion of Photo-Voltaic Generation Resources (PVGRs) in Real-Time Ancillary Service Imbalance Payment or Charge | Jun 2019 | 2019-R6 | $10k-$20k | ERCOT
OBDRR007 – Revisions to the ORDC Methodology to Include Photo-Voltaic Generation Resources (PVGRs) |  |  | $20k-$30k | ERCOT
NPRR911 – Improved Calculation of Real-Time LMPs at Logical Resource Nodes for On-Line Combined Cycle Generation Resources | Jun 2019 | 2019-R6 | $50k-$75k | ERCOT
NPRR920 – Change to Ramp Rate Calculation in Resource Limit Calculator | Jun 2019 | 2019-R6 | $25k-$45k | ERCOT
NPRR877 Phase 2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement | Jul 2019 | 2019-R6 | $25k-$45k | Oncor
Project Initiations – Next 3 Months
If Board approves on 4/9/2019
If Board approves on 4/9/2019

## Slide 6: Aging Items Report
Aging Items Report | Last Action | Status
NPRR664 – Fuel Index Price for Resource Definition and Real-Time Make-Whole Payments for Exceptional Fuel Cost Events | Board approved on 12/9/2014 | On 8/7/2018, Board approved NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap ERCOT presented options to WMS in Sept 2018 to resolve remaining gray boxes On 4/3/2019, WMS endorsed a motion asking ERCOT to file an NPRR to remove remaining NPRR664 grey boxes
NPRR484 – Revisions to Congestion Revenue Rights Credit Calculations and Payments - Phase 1b / 2 | Board approved on 3/19/2013 | Candidates for next phase of CMM Upgrade project Potential Q3 2019 start (with NPRR829 and NPRR907) Partial implementation of NPRR484 on 10/21/2013
NPRR867 – Revisions to CRR Auction Credit Lock Amount to Reduce Excess Collateral | Board approved on 6/12/2018 | 
NPRR702 – Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | Board approved on 12/8/2015 | Partial implementation on 9/1/2018 Remaining grey boxes pending decision on Treasury software
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Board approved on 12/12/2017 | Partial implementation on 10/1/2018 Remaining grey boxes expected to be paired with internal ERCOT project (Security Constrained Unit Commitment)
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Board approved on 8/7/2018 | Currently targeted to start in Q3 2019 bundled with NPRR884 – Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle Generation Resources
Aging Items PPL Logic: Project Status = “Not Started” and
Priority < “2019” (current year)

## Slide 7: 2019 Project Spending
2019 PPL Budget = $20.4M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
March actuals not yet available
March-December forecasts are updated

## Slide 8: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | $0.61M | -
Approved – In-Flight / Complete | $1.59M | $0.00M
Approved – Not Started | $0.97M | $0.60M
Remaining Funding | $1.44M | $3.40M
Total Allocation | $4.00M | $4.00M
As of 2/28/2019

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR885 | Must-Run Alternative (MRA) Details and Revisions Resulting from PUCT Project No. 46369, Rulemaking Relating to Reliability Must-Run Service | 2019 | 220 | REGULATORY Add to end of 2019 list and work into the plan without disrupting in-flight projects
SCR799 | ERCOT Outage Study Cases in the System Operations Test Environment (SOTE) | TBD | TBD | Requesting an additional month to complete IA
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2700
Next available Rank in Regulatory = 220