## Sheet1
TX SET Meeting Notes / Action Items
TX SET Meeting Notes / Action Items | 2019-04-03
Agenda Item: | Decision / Resolution | Action Items :
February 2019 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will have the final version posted to the ERCOT February meeting page.
Flight Update | The Texas SET Chair presented the ERCOT provided Flight update.
FlighTrak Q&A | 1. ONCOR requested feedback from meeting attendees for any interest in more testing of the FlighTrak tool. a. ERCOT stated that they received positive feedback from Market Participants on the FlighTrak tool. b. It was determined that there is no need for additional coordinated training prior to the 0619 Flight. 2. ERCOT requested that Market Participants review the FlighTrak user’s guide and provide feedback for any improvements to the guide. a. RMS leadership requested ERCOT to provide any updates received from Market Participants at a Texas SET meeting. b. Centerpoint requested ERCOT provide a date when the final version of the user’s guide will be available. i. ERCOT stated they plan to have an updated version in May. 3. ERCOT also stated that all non-technical documents that used to be located on the ETOD website will reside on the ERCOT Retail Market Testing webpage. a. There is a link in the MarkeTrak tool. | The Texas SET Chair will keep a standing agenda item to provided the chance for any updates to the guide to be discussed during a meeting.
RMS Update
RMS voted to approve the Impact Analysis for RMGRR159, Related to NPRR908, Revisions to Mass Transition Process
2019 Flight Schedule Revision—RMS voted to approve as amended at RMS
OBDRR012, Texas Market Test Plan Updates - ERCOT provided information related to a Texas Market Test Plan Draft OBDRR that updates language related to changes to the Market Testing site.
RMS Assignments
SAC04--Spanish Translation--RMS leadership update. | It was noted that Texas SET has completed their assignment.
OBDRR012, Texas Market Test Plan Updates--Review | Texas SET reviewed the OGDRR and made changes as needed. | The Texas SET Chair will send the updated document to ERCOT Market Rules to provide RMS with the Texas SET comments.
Change Control Call--No Call This Month | Change Controls on the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Issues-No New Issues this Month | Issues on the ERCOT Website http://www.ercot.com/mktrules/issues/txset
Discussion Items
Draft NPRR Section 15, Customer Registration--15.1.3.1 Mass Transition Process changes to allow TDSPs to send 814_28s for Drop to POLR transactions.--Review ERCOT comments | Texas SET reviewed the ERCOT comments and made additional changes as needed. | The Texas SET Chair will send the updated document to ERCOT Market Rules to provide RMS with the Texas SET updates.
RMG Safety NET Timelines Language Changes--Review updated document | Texas SET reviewed the updated language and made additional changes as needed. | The Texas SET Chair will send the updated document to the Texas SET email distribution list for review and feedback to be provided at the May 15, 2019 meeting.
Construction Hold—ONCOR draft Change Control review | ONCOR requested that this item be postponed until the May meeting.
Banking Scripts--NRG Language Changes Review | 1. Texas SET leadership conducted a discussion and reviewed the suggested changes to the Texas Market Test Plan (TMTP). 2. Some of the TDSPs agreed that they could support removing certain bank change scenarios from the Flight Testing and have these conducted between the trading partners. a. Texas SET agreed that only an existing previously tested CR that is only change banks, without changing any method of remittance, (e. g. changing from the Combo method to sending a separate 820_02; changing from sending the separate 820_02 Remittance Advice to the COMBO method; etc.) would qualify. b. Texas SET agreed that only an existing previously tested CR that is changing their Service Provider to an existing previously tested Service Provider would qualify. | • The Texas SET Vice Chair will continue to update the language in the TMTP to reflect the groups agreements. • Texas SET will review the language at the May meeting.
Other Business
Mass Transition Fire Drill Testing-- Q&A | 1. ERCOT sent an email to the testing POLRs that referred to the competitive transactions sent could be either Switches or Move-ins. 2. Texas SET attendees believed that the Fire Drill test scope would only include completive Switches. 3. ERCOT stated that their scope was provided by the ERCOT Board and that they would process either Switches or Move-ins if the CRs send them. 4. CRs attendees stated they intended to only send Switches. 5. ERCOT provided a list of the 5 POLRs that will be in the test. a. Ambit Energy b. Hudson Energy—May be pulled from the test c. Just Energy d. TXU Energy e. Reliant
Parking Lot
Plans for Texas SET Release Update
Future Flight Schedules Review
Proposed Texas SET Release Changes.— Continue Discussion and Review 650 RCxxx and DCxxx Purpose Code Matrix
REP Certification Matrix—Long-term solution
MISP Workshop Action Items • Add a MISP definition in RMG (RMGRR)
Next Meeting--ERCOT MET Center 102 | 2019-05-15
Attendees F-T-F (*) denotes attendance both days
Diana Rehfeldt TNMP | Teresa Turner ONCOR | Mark Ruane ERCOT
Steve Pliler TXUE | Kathy Scott Centerpoint Energy | Kyle Patrick NRG
Kaci Jacobs TXUE | Jim Lee AEP
Bill Reily ONCOR | Eric Blakey Just Energy
Phil Bracy ERCOT | Sam Pak ONCOR
Attendees Webex (*) denotes attendance both days
Deb Belin Marketwise | Frederick | Adebaga Fapohunda
Carolyn Reed Centerpoint Energy | Frank Nunes EcInfoSystems
Crystal Luna Stream Energy | Dave Michelsen ERCOT
Laura Aldis Life Energy | Mukesh
Teresa Rodriquez Stream Energy | Sai Madhun Malladi
Becky Taylor Centerpoint Energy | Sheri Wiegand TXUE