## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
June 13, 2019

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2019 Release Targets
  Planned Project Starts
  Aging Items Report
  2019 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2019 May Release – R3 – 5/28/2019 – 5/30/2019 Complete
  NPRR901 – Switchable Generation Resource Status Code
  NPRR910 – Clarify Treatment of RUC Resource that has a DAM Three-Part Supply Award
  NPRR912 – Settlement of Switchable Gen Resources (SWGRs) Instructed to Switch to ERCOT
  NPRR916 – Mitigated Offer Floor Revisions (-$20 floor)
  NOGRR174 – AVR and PSS Testing Requirements
  OBDRR010 – Related to NPRR910, Clarify Treatment of RUC Resource that has a DAM Three-Part Supply Award
Off-Cycle Release – CMM Release 1b – 6/2/2019 Complete
  NPRR519 – Exemption of ERS-Only QSEs from Collateral and Capitalization Requirements
  NPRR620 – Collateral Requirements for Counter-Parties with No Load or Generation
  NPRR741 – Clarifications to TPE and EAL Credit Exposure Calculations
Off-Cycle Release – CMM Release 1b – 6/15/2019 In Flight
  NPRR755 – Data Agent-Only QSE Registration
  NOGRR154 – Alignment w/NPRR755 and Req. for ERCOT WAN Installation and Exchange of Resource-Specific XML Data
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) OBDRR011 RMGRR156 PGRR062 NPRR916(a) | NPRR809(b) NPRR817 NPRR833(a/b) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 VCMRR021 RRGRR017 VCMRR022 NPRR877 Ph1 NPRR833(c) NPRR749 | NPRR889 NPRR901 NPRR910 NPRR912 NPRR916(b) NOGRR174 OBDRR010 RMGRR155 RRGRR018/019 NPRR519 NPRR620 NPRR741 NPRR755 NOGRR154 | NPRR873 NPRR899 NPRR925 SCR793 SCR796 SCR797 SCR798 OBDRR003 NPRR821 | NPRR887 PGRR061 | NPRR877 Ph2 NPRR895 NPRR911 NPRR914 NPRR920 OBDRR007 SCR781(a) RRGRR016 NPRR889 RMGRR155 RRGRR018 RRGRR019
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
NPRR916(a) – Mitigated Offer Floor to $0/MWh
NPRR916(b) – Mitigated Offer Floor to -$20/MWh
PGRR057(b) – List of GMD event contingencies
SCR781(a) – View / Edit capability
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
NS
E
I
NS
P
E
E
E
E
E
E
E
7/1
6/2
E
E
CMM Release 1b
5/1
E
E
E
E
E
E
E
E
E
1/22
3/26
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2014 | 2017 | 2018
 | NPRR664 | NPRR702 P, NPRR829 | NPRR825(b), NPRR867, PGRR066, NPRR841, NPRR863 Ph1 I
I
E
3/1
3/5
5/6 – 5/7
Q4
Date TBD
ü
R1
R2
R3
R4
R5
R6
ü
4/10
ü
ü
6/15
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR877 Phase 2 – Use of Actual Interval Data for IDR ESI IDs for Initial Settlement | Jul 2019 | 2019-R6 | $25k-$45k | Oncor
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Aug 2019 | 2020-R3 | $50k-$75k | ERCOT
NPRR884 – Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle |  |  | $300k-$400k | ERCOT
NPRR914 – Addition of Controllable Load Resources to 60-Day Reports | Aug 2019 | 2019-R6 | $15k-$25k | ERCOT
Project Initiations – Next 3 Months

## Slide 6: Aging Items Report
Aging Items Report | Last Action | Status
NPRR664 – Fuel Index Price for Resource Definition and Real-Time Make-Whole Payments for Exceptional Fuel Cost Events | Board approved on 12/9/2014 | On 8/7/2018, Board approved NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap On 5/2/2019, ERCOT filed NPRR940 (and VCMRR023) to remove remaining grey boxes
NPRR484 – Revisions to Congestion Revenue Rights Credit Calculations and Payments - Phase 1b / 2 | Board approved on 3/19/2013 | Candidates for next phase of CMM Upgrade project Potential Q3 2019 start (with NPRR829 and NPRR907) Partial implementation of NPRR484 on 10/21/2013
NPRR867 – Revisions to CRR Auction Credit Lock Amount to Reduce Excess Collateral | Board approved on 6/12/2018 | 
NPRR702 – Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | Board approved on 12/8/2015 | Partial implementation on 9/1/2018 Remaining grey boxes pending decision on Treasury software
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Board approved on 12/12/2017 | Partial implementation on 10/1/2018 Remaining grey boxes expected to be paired with internal ERCOT project (Security Constrained Unit Commitment)
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Board approved on 8/7/2018 | Currently targeted to start in Q3 2019 bundled with NPRR884 – Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle Generation Resources
Aging Items PPL Logic: Project Status = “Not Started” and
Priority < “2019” (current year)
Status updates in bold

## Slide 7: 2019 Project Spending
2019 PPL Budget = $20.4M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 8: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | $1.11M | -
Approved – In-Flight / Complete | $2.28M | $0.00M
Approved – Not Started | $0.42M | $0.63M
Remaining Funding | $1.30M | $3.37M
Total Allocation | $4.00M | $4.00M
As of 4/30/2019
May actuals not yet available
Updated to include April actuals

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR904 | Revisions to Real-Time On-Line Reliability Deployment Price Adder for ERCOT-Directed Actions Related to DC Ties and to Correct Design Flaws | TBD | TBD | Market input requested Impact Analysis still in progress at time of mailing – IA expected to be available at June PRS
NPRR935 | Post All Wind and Solar Forecasts | 2019 | 2720 | Add to end of 2019 list and work into the plan without disrupting in-flight projects
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2720
Next available 2020 Rank in Business Strategy = 2810
Next available 2019 Rank in Regulatory = 240
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation