## Principle Concept Development
RTCTF Meetings in 2019
Key Principle | Decision Points and Issues for Developing Principle Concepts | Date Topic was First Presented to the RTC Task Force | Related Principle Concepts under Dicussion (Y, with Principle Concept Number(s), or N)? | Related Principle Concepts Approved by TAC (Y,with Date and Principle Concept Number(s), or N)? | Estimated Date for First/Next Discussion | Estimated Final Meeting for Moving to TAC for Vote | 2019-05-13 | 2019-06-07 | 2019-06-21 | 2019-07-12 | 2019-08-09 | 2019-08-27 | 2019-09-19 | 2019-10-14 | 2019-10-30 | 2019-11-19 | 2019-12-03 | 2019-12-19
Key Principle 1.1 – Ancillary Service Demand Curves and Current Market Price Adders | Determing the shape and price points for for the demand curves for each of the AS products, inlcuding Regulation Down | n/a | N | N | Following discussion at the PUCT on Real-Time AS Demand Curves
| Elimination of the ORDC price adders | n/a | N | N | Principle concept will be developed once dicussion on the demand curves has iniated.
| Continuation of the Reliability Deployment Price Adder process | n/a | N | N | Principle concept will be developed once dicussion on the demand curves has iniated.
Key Principle 1.2 – System-Wide Offer Cap and Power Balance Penalty Curve | New value for SWOC | n/a | N | N | Following discussion at the PUCT on SWOC
| Need for separate SWOC in DAM | n/a | N | N | Following discussion at the PUCT on SWOC
| New value and shape for the PBPC | n/a | N | N | Following discussion at the PUCT on SWOC and Real-Time AS Demand Curves
Key Principle 1.3 - Offering and Awarding of Ancillary Services in Real-Time | Constraint formulation for RTC (e.g., Resource constraints, rules for RRS, ramp sharing, NFRC etc.) | n/a | N | N | 2019-06-21 | 2019-08-27 | bar: 2019-06-21 to 2019-08-27
| Any cases in which AS isn't reawarded in RTC (e.g., discussion on RRS being provided by Load Resources on UFR). | n/a | N | N | 2019-06-21 | 2019-08-27 | bar: 2019-06-21 to 2019-08-27
| Potential use of telemetered emergency ramp rates in Real-Time | n/a | N | N | 2019-06-21 | 2019-08-27 | bar: 2019-06-21 to 2019-08-27
| Method for QSEs to indicate temporary inability to provide AS | n/a | N | N | 2019-06-21 | 2019-08-09 | bar: 2019-06-21 to 2019-08-09
| ERCOT management of cases where AS is infeasible (e.g., deployment of Regulation resulting in physical transmission constraint over-loading) | n/a | N | N | 2019-07-12 | 2019-09-19 | bar: 2019-07-12 to 2019-08-27
| Offer structure for AS offer in Real-Time | 2019-04-30 | N | N | 8/27/2019 (May have to occur following discussion at the PUCT on AS participation rules) | 2019-10-14 | bar: 2019-08-27 to 2019-10-14
| Timeline for submission of AS offers for Real-Time | 2019-04-30 | N | N | 2019-08-27 | 2019-10-14 | bar: 2019-08-27 to 2019-10-14
| Are changes to Verifiable Costs needed? | n/a | N | N | 2019-08-27 | 2019-10-14 | bar: 2019-08-27 to 2019-10-14
Key Principle 1.4 – Systems that Input into the Real-Time Optimization | Changes to RLC calculations | 2019-04-30 | Y (1) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| Telemetry changes associated with any change to the RLC logic, both from the QSEs to ERCOT and from ERCOT to the QSEs | n/a | N | N | 2019-06-21 | 2019-08-09 | bar: 2019-06-21 to 2019-08-09
Key Principle 1.5 – Process for Deploying Ancillary Services | Maintaining of existing RTM clearing timeframe | 2019-04-30 | Y (2) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| Changes to the AS Manager | 2019-05-13 | Y (1) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| LFC - Changes to existing UDBP framework | 2019-04-30 | Y (4, 5) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-07-12
| LFC - Portfolio vs. Resource-specific deployment, particularly for Regulation | 2019-04-30 | Y (3) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-07-12
| LFC - Distribution of Regulation instructions | 2019-04-30 | Y (5, 6) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-07-12
| LFC - Process for deploying RRS | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Details on telemetry changes necessary to accommodate the LFC and AS Manager changes | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Impact of ASDCs | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Removal of the existing process for QSEs to update telemetered AS schedules following manual deployment (specifically for Generation Resource and CLRs) | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Elimination of Non-Spin Offer Floor | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Continued ability of the Real-Time optimization (i.e., RTC) to be executed off-cycle, between regularly scheduled 5-minute executions. | 2019-04-30 | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| RTC failure process | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
Key Principle 1.6 – Ancillary Service Imbalance Settlement with RTC | Potential use of existing energy imbalance calculations as basis | 2019-04-30 | Y (1) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| Separate AS imbalance calculation for each AS product | 2019-04-30 | Y (2) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| Allocation of non-zero AS imbalance amounts | 2019-04-30 | Y (3, 4) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
| Concept of AS Supply Responsibility in Real-Time and removal of current settlement that is no longer needed (failure to provide, infeasibility, etc.) | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Additional details associated with having virtual AS Offers and Bids in the DAM, if needed. | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
Key Principle 2 – Suite of Ancillary Service Products | List of AS products and what type of Resources can provide them | n/a | N | N | Following discussion at the PUCT on the set of AS products under RTC
| Definition of AS products to align with the Real-Time Co-optimization (RTC) framework, specifically time limitations (E.g., can a 10 MWh hour battery offer 120 MW of AS for a 5-minute interval?) | n/a | N | N | Following discussion at the PUCT on the set of AS products under RTC
| Changes to the qualification process with RTC processes and any definition changes | n/a | N | N | Following discussion at the PUCT on the set of AS products under RTC
Key Principle 3 – Reliability Unit Commitment | Functionality and Process Concepts - RUC AS penalties | 2019-05-13 | Y (2) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-06-21
| Functionality and Process Concepts - Details on changes to COP or alternative source of Resource information | 2019-05-13 | Y (3, 4) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-06-21
| Functionality and Process Concepts - Source of AS Offers that RUC will use | 2019-05-13 | Y (5, 6) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-06-21
| Functionality and Process Concepts - Consider qualified OFF and OFFQS Generation Resources when determining non-binding AS awards | 2019-05-13 | Y (7, 8) | N | 2019-06-21 | 2019-07-12 | bar: 2019-05-13 to 2019-06-21
| Functionality and Process Concepts - Current RUC recommendation deferral process | 2019-05-13 | Y (9) | N | 2019-06-21 | 2019-07-12
| Functionality and Process Concepts - Mitigation of the impact to Real Time prices by Resources committed through the RUC process | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| RUC Settlement - Capacity short calculation and allocation of RUC make-whole, , including the potential consideration of QSEs who are short on their AS Supply Responsibility. | n/a | N | N | 2019-06-21 | 2019-08-09 | bar: 2019-06-21 to 2019-08-09
| RUC Settlement - Changes to RUC claw-back and make-whole | n/a | N | N | 2019-06-21 | 2019-08-09 | bar: 2019-06-21 to 2019-08-09
| Process for determining the amount of individual AS products that can be provided by a Resource | n/a | N | N | 2019-06-21 | 2019-08-09 | bar: 2019-06-21 to 2019-08-09
Key Principle 4 – The Supplemental Ancillary Service Market Process | Elimination and replacement of the SASM process | 2019-05-13 | Y (only have Key Principle, no separate Principle Concepts) | N | 2019-06-21 | 2019-06-21 | bar: 2019-05-13 to 2019-06-21
Key Principle 5 – Day-Ahead Market | Functionality and Process Concepts - Ancillary Service Demand Curves (ASDCs) in the DAM | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Functionality and Process Concepts - Ancillary Service (AS) Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Functionality and Process Concepts - AS Bids to Buy | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Functionality and Process Concepts - Changes to the current DAM AS insufficiency process | n/a | N | N | 2019-07-12 | 2019-08-27 | bar: 2019-07-12 to 2019-08-27
| Credit exposure changes associated with any changes to DAM submittals | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Settlement Concepts - Impacts on AS Obligation process for Load-Serving Entities (LSEs) if ASDCs in the DAM | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Settlement Concepts - Settlement of AS Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC
| Settlement Concepts - Settlement of AS Bids to Buy and how those AS Bids would impact the AS Obligation calculation for LSEs | n/a | N | N | Following discussion at the PUCT on changes to DAM under RTC | bar: 2019-10-30 to 2019-12-03
Key Principle 6 – Market-Facing Reports | Posting of Ancillary Service Demand Curves (ASDCs) | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Real-Time Market (RTM) Ancillary Service (AS) awards and prices | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Reports related to system conditions using Resources’ High Ancillary Service Limits (HASLs) | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Day-Ahead Market (DAM) awards information if there are AS Offers that aren’t directly associated with a Resource (“Virtual” or “Financial-only” AS Offers) or AS Bids to Buy | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Changes to RTM and DAM disclosure reporting | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| New Reliability Unit Commitment (RUC) reporting associated with changes in functionality(e.g., on sufficiency of AS-qualified capacity in RUC in optimization) | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| New elements and changes to Settlement extracts | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Changes to performance monitoring reports to align with any changes in performance metrics | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Reports assoicated with AS Supply Responsbility | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Removal of Supplemental Ancillary Service Market (SASM) reporting | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
| Removal of Operating Reserve Demand Curve (ORDC) reporting | n/a | N | N | 2019-10-30 | 2019-12-03 | bar: 2019-10-30 to 2019-12-03
Key Principle 7 – Performance Monitoring | Change in GREDP formulation to account for potential LFC changes | n/a | N | N | 2019-10-14 | 2019-11-19 | bar: 2019-10-14 to 2019-11-19
| Performance related to a release of a Resource's HASL through a change in AS schedule | n/a | N | N | 2019-10-14 | 2019-11-19 | bar: 2019-10-14 to 2019-11-19
| Removal of the concept of AS Responsibility in RT and associated Settlements | n/a | N | N | 2019-10-14 | 2019-11-19 | bar: 2019-10-14 to 2019-11-19
Key Principle 8 – Out of Scope Items | Identifying proposals that are out of scope for the RTC project | n/a | N | N | Discussion will be on-going thoughout the year | 2019-12-19

## Other Raised Issues
Issue | Meeting Raised
Triggers for automatically initiated an off-cycle execution of RTC (e.g., deploying a certain percent of the total Regulation amount, unit trips, etc.) | 5/13/19 RTCTF Meeting