## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
July 17, 2019

## Slide 2
Project Portfolio Update
  Recent / Upcoming Project Implementations
  2019 Release Targets
  Planned Project Starts
  Aging Items Report
  2019 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
Off-Cycle Release – CMM Release 1b – 6/2/2019 Complete
  NPRR519 – Exemption of ERS-Only QSEs from Collateral and Capitalization Requirements
  NPRR620 – Collateral Requirements for Counter-Parties with No Load or Generation
  NPRR741 – Clarifications to TPE and EAL Credit Exposure Calculations
Off-Cycle Release – CMM Release 1b – 6/15/2019 Complete
  NPRR755 – Data Agent-Only QSE Registration
  NOGRR154 – Alignment w/NPRR755 and Req. for ERCOT WAN Installation and Exchange of Resource-Specific XML Data
Off-Cycle Release – 7/1/2019 Complete
  NPRR821 – Elimination of the CRR Deration Process for Resource Node to Hub or Load Zone CRRs
2019 August Release – R4 – 8/6/2019 – 8/8/2019 In Flight
  NPRR873 – Posting of the ERCOT Wide Intra-Hour Wind Power and Load Forecast on the MIS Public
  NPRR925 – Increasing Minimum Quantity for PTP Obligation Bids
  SCR793 – SSR Related Telemetry for Transmission Service Provider (TSP) Operators
  SCR796 – Change Validation Rules to Preclude Certain Transactions at Resource Nodes within PUNs
  SCR798 – PTP Obligation Bid ID Limit
  OBDRR003 – Change Validation Rules to Preclude Certain Transactions at Resource Nodes within PUNs
  OBDRR014 – Change Posting Location for Non-biddable Resource Nodes
Off-Cycle Release – 9/1/2019 In Flight
  NPRR899 – Digital Certificate and User Security Administrator Clarifications and Opt Out Procedure
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2019 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release
(a), (b), etc.: Multiple phase release
February 2/5 – 2/7 | April 4/2 – 4/4 | May 5/28 – 5/30 | August 8/6 – 8/8 | October 10/15 – 10/17 | December 12/10 – 12/12
NPRR842 NPRR858 NPRR878 SCR794 PGRR057(b) OBDRR011 RMGRR156 PGRR062 NPRR916(a) | NPRR809(b) NPRR817 NPRR833(a/b) NPRR845 NPRR847 NPRR865 NPRR866 NPRR880 VCMRR021 RRGRR017 VCMRR022 NPRR877 Ph1 NPRR833(c) NPRR749 | NPRR901 NPRR910 NPRR912 NPRR916(b) NOGRR174 OBDRR010 NPRR909 NPRR519 NPRR620 NPRR741 NPRR755 NOGRR154 | NPRR873 NPRR899 NPRR925 SCR793 SCR796 SCR797 SCR798 OBDRR003 OBDRR014 NPRR821 NPRR899 | NPRR887 PGRR061 | NPRR877 Ph2 NPRR895 NPRR911 NPRR914 NPRR920 OBDRR007 SCR797 SCR781(a) RRGRR016 NPRR889 RMGRR155 RRGRR018 RRGRR019
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
NPRR809(b) – Reporting/posting system changes
NPRR833(a/b) – DAM/SCED system changes
NPRR833(c) – CRR system changes
NPRR916(a) – Mitigated Offer Floor to $0/MWh
NPRR916(b) – Mitigated Offer Floor to -$20/MWh
PGRR057(b) – List of GMD event contingencies
SCR781(a) – View / Edit capability
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
ü
P
E
P
P
P
E
E
E
E
E
E
E
E
7/1
6/2
ü
ü
CMM Release 1b
5/1
E
E
E
E
E
E
E
ü
1/22
3/26
ü
ü
ü
ü
ü
ü
ü
TBD Items | 2014 | 2017 | 2018 | 2019
 | NPRR664 | NPRR702, NPRR829 | NPRR825(b), NPRR867, PGRR066, NPRR841 | NPRR863 Ph1, NPRR885, NPRR887, NPRR929, SCR799, PGRR070
P
E
3/1
3/5
5/6 – 5/7
Q4
Date TBD
ü
R1
R2
R3
R4
R5
R6
ü
4/10
ü
ü
6/15
ü
ü
ü
ü
ü
ü
ü
ü
ü
6/1
E
9/1

## Slide 5: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Aug 2019 | 2020-R3 | $50k-$75k | ERCOT
NPRR884 – Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle |  |  | $300k-$400k | ERCOT
NPRR484 – Revisions to Congestion Revenue Rights Credit Calculations & Payments (remaining grey boxes) | Sept 2019 | TBD | $250k-$500k | Luminant
NPRR829 – Incorporate Real-Time Non-Modeled Telemetered Net Generation by Load Zone into the Estimate of RTL |  |  | $200k-$300k | Enchanted Rock
NPRR867 – Revisions to CRR Auction Credit Lock Amount to Reduce Excess Collateral |  |  | $75k-$100k | CWG
NPRR907 – Revise Definition of M1a to Reflect Actual Calendar Days |  |  | $15k-$35k | ERCOT
Project Initiations – Next 3 Months

## Slide 6: Aging Items Report
Aging Items Report | Last Action | Status
NPRR664 – Fuel Index Price for Resource Definition and Real-Time Make-Whole Payments for Exceptional Fuel Cost Events | Board approved on 12/9/2014 | On 8/7/2018, Board approved NPRR847 – Exceptional Fuel Cost Included in the Mitigated Offer Cap On 5/2/2019, ERCOT filed NPRR940 (and VCMRR023) to remove remaining grey boxes
NPRR484 – Revisions to Congestion Revenue Rights Credit Calculations and Payments - Phase 1b / 2 | Board approved on 3/19/2013 | Included in next phase of CMM Upgrade project Q3 2019 start (with NPRR829 and NPRR907) Partial implementation of NPRR484 on 10/21/2013
NPRR867 – Revisions to CRR Auction Credit Lock Amount to Reduce Excess Collateral | Board approved on 6/12/2018 | 
NPRR702 – Flexible Accounts, Payment of Invoices, and Disposition of Interest on Cash Collateral | Board approved on 12/8/2015 | Partial implementation on 9/1/2018 Remaining grey boxes pending decision on Treasury software
NPRR825 – Require ERCOT to Issue a DC Tie Curtailment Notice Prior to Curtailing any DC Tie Load | Board approved on 12/12/2017 | Partial implementation on 10/1/2018 Remaining grey boxes expected to be paired with internal ERCOT project (Security Constrained Unit Commitment)
NPRR856 – Treatment of OFFQS Status in Day-Ahead Make Whole and RUC Settlements | Board approved on 8/7/2018 | Currently targeted to start in Q3 2019 bundled with NPRR884 – Adjustments to Pricing and Settlement for Reliability Unit Commitments (RUCs) of On-Line Combined Cycle Generation Resources
Aging Items PPL Logic: Project Status = “Not Started” and
Priority < “2019” (current year)
Status updates in bold

## Slide 7: 2019 Project Spending
2019 PPL Budget = $20.4M
“Potential Demand” represents internal ERCOT projects that have not been fully approved
May actuals not yet available
June-December forecasts are updated

## Slide 8: Revision Request Funding Placeholder Status
In 2019, ERCOT forecasted $4.0M for Revision Request work
In ERCOT’s 2020/2021 proposed budget, the following amounts are allocated for Revision Request work
  2020 = $4M
  2021 = $4M
Yearly Revision Request Spending Forecast Summary
Project Status | 2019 | 2020
YTD Actuals | $1.49M | -
Approved – In-Flight / Complete | $2.40M | $0.00M
Approved – Not Started | $0.19M | $0.63M
Remaining Funding | $1.41M | $3.37M
Total Allocation | $4.00M | $4.00M
As of 6/30/2019
May actuals not yet available
Updated to include April actuals

## Slide 9: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR939 | Modification to Load Resources Providing RRS to Maintain Minimum PRC on Generators During Scarcity Conditions | 2019 | 2770 | Add to end of 2019 list and work into the plan without disrupting in-flight projects – target Q4 2019 start
SCR802 | Enhance Communications of System Inertia | TBD | TBD | Market input requested
Options for…
PPL Rank Information
Next available 2019 Rank in Business Strategy = 2770
Next available 2020 Rank in Business Strategy = 2810
Next available 2019 Rank in Regulatory = 240
Note
Items in the Regulatory section of the PPL are not tracked against the market Revision Request funding allocation