## Slide 1
Resource Integration Workshop
Resource Integration Topics
ERCOT
Jay Teixeira
July 30, 2019

## Slide 2: Quarterly Stability Assessment (QSA)
Planning Guide 5.9
Next Deadline for QSA
If a GINR is not included in QSA, its Initial Synchronization date will be automatically delayed to the next quarter
All-Inclusive Generation Resource Initial Synchronization Date | Last Day for an IE to meet prerequisites as listed in paragraph (4) below | Completion of Quarterly Stability Assessment
Upcoming January, February, March | Prior August 1 | End of October
Upcoming April, May, June | Prior November 1 | End of January
Upcoming July, August, September | Prior February 1 | End of April
Upcoming October, November, December | Prior May 1 | End of July

## Slide 3: Quarterly Stability Assessment (QSA)
Planning Guide 5.9, Quarterly Stability Assessment
Issue’s seen in the QSA that had May 1, 2018 deadline
  10 day comment period for FIS
    Needs to be complete before QSA deadline
    TSPs need to plan for it
  Dynamic data validation
    Dependent on FIS Stability study
    Need to meet PG 6.9 15 to 30 days prior to QSA deadline

## Slide 4: Resource Integration and Ongoing Operations – Interconnection Services (RIOO-IS) – Email Notifications
Last Release – July 26, 2019
Email to external entities should be fixed

## Slide 5: PGRR066 - Implementation
Consists of changes to the GIS Report and INR process
  Small changes made to RIOO-IS for GIS Report
  No changes made to RIOO-IS user interface
Manual Implementation – RIOO-IS “Suspended” status will be used for “Inactive” until RIOO-IS implementation. IE’s will see “Suspended for Ownership Determination” in RIOO-IS. TSP’s do not see status.
Implementation Date: August 1, 2019
  IE’s with active INR projects can email ERCOT at ResourceIntegrationDepartment@ercot.com to have ERCOT change the status of their INR (1 per email)
  ERCOT will query database to determine which INR projects should be moved to “Inactive” [5.7.6 (1)]

## Slide 6: PGRR066 – Implementation – GIS Report
GIS Report changes effective with end of August report
  New tab to show all Inactive projects
  Projects will not drop off Inactive tab after one GIS report
When project moves from “Planned” to “Inactive”
  Project disappears from Project Details tab
  Project is added to “Inactive” tab
Opposite occurs when moving from “Inactive” to “Planned”
  Plus new code will appear in column “L” on the first month it becomes “Planned”

## Slide 7: PGRR066 – Implementation – INR Process -> Inactive
Resource Integration will perform monthly queries near the end of the month to determine INR’s that meet criteria to move to “Inactive” [5.7.6 (1)]
  PG 6.9 not met within 2 years of last FIS report posting to MIS Secure
RI Engineer moves status to “Inactive” if IE requests [5.7.6 (1)]
RI Engineer will check to see if PG 6.9 met and remove from models [5.7.6 (2)]

## Slide 8: PGRR066 – Implementation – INR Process -> Planned
IE with INR in “Inactive” will inform ERCOT that they think they meet the condition to move to “Planned” [5.7.6 (3)]
ERCOT will confirm whether the IE meets requirements
RI Engineer will check to see if PG 6.9 met and add back to models [5.7.6 (3)]
ERCOT will check if FIS needs to be redone [5.7.6 (3) and 5.7.6 (6)]

## Slide 9: Active PGRR’s
PGRR062 - Updates to Generation Interconnection or Change Request (GINR) Process – Implemented
PGRR066 - Interconnection Request Cancellation and Creation of Inactive Status – BOD approved December 11, 2018. Implement work around Aug 1, 2019.
PGRR071 - Update Interconnection Process Timetables to Align with NPRR926 – Referred to PLWG by ROS on 7/11/2019. Next PLWG meeting August 21, 2019.
New PGRR – Miscellaneous Updates, with NPRR, NOGRR, and RRGRR submitted for internal review

## Slide 10: Active NPRR’s
NPRR926 - Removal of 90-Day Period Between SSR Study Approval and Synchronization – Board Approved June 11, 2019. Effective July 1, 2019.

## Slide 11: Other Topics
PG 5.4.5 text
Oncor Topics

## Slide 12: Dynamic Case Dispatch in PG 5.4.5 (1) and (2) Edit made from June 20 WS
(1) At the discretion of the TSP(s) or ERCOT, the lead TSP(s) will perform transient stability studies if necessary to meet NERC Reliability Standards, Protocols, this Planning Guide or the Operating Guides applicable to the Generation Resource or the ERCOT System.
(2) If the TSP(s) in charge of these stability studies decides not to conduct the studies, the TSP(s) must provide a written justification in lieu of the study report. When performing such studies, all existing or planned publicly committed Generation Resources in the area of the study will should normally be represented at full net an output if possible and that is reasonable for the conditions being studied, although some Combined Cycle Generation Resources or coal plants might be modeled at full gross output (including auxiliary load). Any resulting increase in generation will be balanced as addressed in the FIS scope agreement.

## Slide 13: Dynamic Case Dispatch in PG 5.4.5 (1) and (2) ERCOT Language
(1) At the discretion of the TSP(s) or ERCOT, the lead TSP(s) will perform transient stability studies if necessary to meet NERC Reliability Standards, Protocols, this Planning Guide or the Operating Guides applicable to the Generation Resource or the ERCOT System. If the lead TSP(s) conducting the stability study decides a study is not required, the lead TSP(s) shall provide a written justification in lieu of the study report.
(2) When performing such studies, all existing or planned Generation Resources of like technology in the area of the study shall be dispatched at full net output. When referring to like technology, nearby IRR generation should be dispatched at full net output if an IRR unit is the type of unit under study and nearby non-IRR generation should be dispatched at full net output if a non-IRR unit is the type of unit under study. The dispatch may be reduced to respect any published stability limits or reach a solution. The technical rationale for the dispatch used shall be provided in the study report. Any resulting increase in generation will be balanced as addressed in the FIS scope agreement.

## Slide 14: Oncor Topics
Process for determining need for restudy of FIS stability due to turbine or inverter change. – Review data with TSP to determine need for re-study.
What capability of an energy storage system do we study in the FIS, 4-hour, 2-hour, 1-hour, or less? For SS, full MW discharge/charge, for SP – appropriate time, Dynamic – first few seconds
Are SSR studies really needed for battery energy storage systems and solar plants given there is no rotating equipment? Yes since there can be SSCI.

## Slide 15: Oncor Topics
How should multiple less than 10 MW resource additions to an existing plant be handled? If made by same developer, treat as multiple phases of an INR. When the aggregated amount exceeds 20 MVA, they need to meet protocol 3.15.
What is the status of notifications to RIOO-IS? It was in the last release, out 7/26/2019
What is the status of generator data export from RIOO-RS? Has not been included yet. If it does get included, it won’t be available until end of 2021.

## Slide 16: Oncor Topics
We are experiencing difficulty getting PSCAD models for some plants to interact properly in SSR studies modeling multiple plants. What is status of better PSCAD models? Not sure what is meant by “better models”. The PSCAD model guidelines are posted (with the dynamic model templates for now for lack of a better place). Are entities submitting the checklist with their PSCAD model as requested? Are there items that should be added to the checklist? Each “difficulty” tends to have its own unique (non-trivial) solution with PSCAD models. At this point, the only solution is to identify the difficulty/improper behavior and work with the model submitter/developer to resolve the issue.

## Slide 17: Oncor Topics
What is the status of previous topics such as generation assumptions for FIS stability study? Will work it into the Miscellaneous PGRR.

## Slide 18: Other contact information
ResourceIntegrationDepartment@ercot.com is distribution list for Resource Integration department

## Slide 19: Questions?
Thank you!